## ProjectSchedule
PROJECT : Repair Application
Client | Blackwhite Technologies
Team | Deepak , Udhayan | Delivery
| Project Start: |  | 2020-11-02
| Display Week: |  | 1 |  |  |  |  | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14 | [6 empty] | 2020-12-21
 | time axis 2020-11-02 to 2020-12-27
TASK | ASSIGNED TO | PROGRESS | START | END | ACTUAL START | ACTUAL END | DAYS | time axis 2020-11-02 to 2020-12-27
Phase 1 : User module
Project concept and initialisation | Udhayan | 100% | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 1
Project definition and planing | Deepak | 100% | 2020-11-03 | 2020-11-10 | 2020-11-03 | 2020-11-04 | 8
DB Design | Deepak | 90% | 2020-11-11 | 2020-11-12 | 2020-11-05 | 2020-11-05 | 2
Git & Project set up | Deepak | 100% | 2020-11-13 | 2020-11-13 | 2020-11-06 | 2020-11-06 | 1
Login / Registration | Udhayan | 100% | 2020-11-16 | 2020-11-18 | 2020-11-16 | 2020-11-18 | 3
User dashboard Design | Deepak | 100% | 2020-11-18 | 2020-11-18 | 2020-11-09 | 2020-11-09 | 1
User Profile Design | Deepak | 100% | 2020-11-19 | 2020-11-19 | 2020-11-10 | 2020-11-11 | 1
User Alerts Design | Deepak | 100% | 2020-11-20 | 2020-11-20 | 2020-11-13 | 2020-11-13 | 1
User History Design | Deepak | 100% | 2020-11-23 | 2020-11-23 | 2020-11-13 | 2020-11-13 | 1
User Track order Design | Deepak | 100% | 2020-11-24 | 2020-11-24 | 2020-11-13 | 2020-11-13 | 1
User Buy parts Design | Deepak | 100% | 2020-11-25 | 2020-11-25 | 2020-11-16 | 2020-11-16 | 1
User Contact Design | Deepak | 100% | 2020-11-26 | 2020-11-26 | 2020-11-16 | 2020-11-16 | 1
User dashboard development | Udhayan | 0% | 2020-11-27 | 2020-11-28 |  |  | 2
User Profile development | Udhayan | 0% | 2020-11-29 | 2020-11-29 |  |  | 1
User Alerts development | Udhayan | 0% | 2020-11-21 | 2020-11-21 |  |  | 1
User History development | Udhayan | 0% | 2020-11-22 | 2020-11-22 |  |  | 1
User Track order development | Udhayan | 0% | 2020-11-23 | 2020-11-24 |  |  | 2
User Buy parts development | Udhayan | 0% | 2020-11-25 | 2020-11-26 |  |  | 2
User Contact development | Udhayan | 0% | 2020-11-27 | 2020-11-27 |  |  | 1
User module testing | Deepak ¦ Udhayan | 0% | 2020-11-28 | 2020-12-01 |  |  | 4
First delivery |  | 0% | 2020-12-02 | 2020-12-02 |  |  | 1 | bar: 2020-11-02 to 2020-12-01