## Release Checklist & Approval
Profield Chat v1 - Release Checklist & Approval
This list contains items that need to be completed before software can be released. Each team may customize this list as appropriate for their specific project. This list also contains items that need to be confirmed for a Release Approval.
Activities | Person In Charge | Done? | Comments
Engineering Activities
Create install and configuration scripts as needed. | Joshy | Yes
Remove debugging and testing code from the software (including disabling assertions). | Joshy | Yes
Create the releasable software media (CD, Pen-Drive,JAR file, etc) required by customer. | Joshy | Yes
Quality Assurance Activities | QA Person
Verify all source code meets coding standard; run Checkstyle or other style-checker and do manual inspection. | Joshy | Yes
Verify all steps in the deployment plan are completed. (security, performance, etc) | Joshy | Yes
Check that all defects on current defect list have been resolved | Joshy | Yes
Smoke test/regression test final build | Test Specialist
Verify that every test in the Test Matrix appears in the Test Script. | Sharon | Yes
Verify all unit tests run automatically on the current build. | N A |  | Project not planned to implement test automation
Verify all system test scripts run automatically on the actual released software | N A
Perform all non-functional system tests manually and document results | Sharon | Yes
Verify installation by installing system on clean machine | Sharon | Yes
Have someone not on your team install and run your system without assistance by following your installation directions. | N A
Install program on machine with older version of program (upgrade install) | Joshy | Yes
Consistency check: SRS, User Manual, System Tests, Staged Delivery Plan, and Software must all match! | Sharon | Yes
Has all formal testing been completed including unit, integration, and system tests? Have build/smoke tests been completed? | QA Manager
Have all walkthroughs, peer reviews, and management reviews been performed throughout the project? | Suraj | Yes
Have all interfaces been tested? (Note: not all interfaces may exist in any of the Test environments, but if the project relies on an untested interface, the risk needs to be identified along with recommendations to mitigate the risk.) | Sharon | Yes
Release Activities
Confirm the release criteria have been met | Release Team Member
Schedule Acceptance Test date with customer | N A
Virus scan all release media | N A
Documentation Activities
Verify that User Documentation matches current Release | Joshy | Yes
Create a "ReadMe" text file with installation instructions (optional) | N A
Write "Known Issues" List. | Joshy/Midhun | Yes
Have training materials been completed for Operations, Support and end-users? | Joshy/Midhun | Yes
Has training been scheduled for support staff, operations, and the client? | N A
Software Configuration Management
Have all required components been placed under control during development? (All files, including Executables, libraries and stored procedure files been placed under control.) | Suraj | Yes
Verify correct version of software has been tested and gone through all checkpoints listed above (unit, integration, user test). | Suraj | Yes
Notifications: Have all impacted parties been notified about the Release Plan and schedule? | Suraj | Yes
Have all components been backed up and a recovery plan been defined? | Suraj | Yes
Has the post-production plan been established? This includes monitoring when the application goes into production. | N A
Other Activities
Project Visiblity Calculations are current and accurate. | Suraj | Yes
Create draft features list for next Staged Delivery Plan. | N A |  | No next release planned
Schedule Project Survival Assessment or Post-Mortem meeting. | N A
Suraj P 06 Jan 2020