## Risks
RISKS
Sl. No. | Project | Risk | Probability of Occurance | Risk Impact | Mitigation Plan
1 | Profield-Chat-v2 | There is no resources to take over the work from current Web developers | High | Any enhancements may not be able to deliver | Plan A: Recruit a developer Plan B: Identify a capable trainee and allocate and induct into the project from the Feb 1st week
2 | Profield-Chat-v2 | There is no resources to take over the work from current IOS developer. | High | Any enhancements may not be able to deliver/ or get delayed. | Plan A: Recruit an IOS developer. Plan B: The Current IOS developer will handle the work from Japan. We have to adjust our plan to suit with the onsite developer's availability
3 | Profield-Chat-v2 | Full day Japanese class for the team starts from 3rd Feb clash with the planned schedule for delivery (13-Feb-2020) | High | Cannot complete the bugs found in system test and it will affect the delivery date | Continue the Japanese class for 2hrs/day until Feb 13th