## Slide 1: Cworks CXF
Presented By: <Suraj P
Issue #:2
Issue date:01-Jan-2018
ICS/FMT/PP

## Slide 2: CWorks CXF (CWorks-CXF -v1)
A data exchange format between AutoCAD system and C-Works CAD system.

## Slide 3: About The Customer
CWorks: A Japanese corporate who is focusing on construction related software products.
They have been using the standard data exchange format of AutoCAD.
Their major product is CWorks CAD
  This system accepts the AutoCAD drawings and process them to create scaffoldings design for the proposed building project and make necessary cost and material estimation for the SCAFFOLDING.
Notes: Make bullet points similar to the example bellow
C-Works: A Japanese corporate who is focusing on construction related software products.
They have been using the standard data exchange format of AutoCAD.
Their major product is C-Works CAD
  This system accepts the AutoCAD drawings and process them to create scaffoldings design for the proposed building project and make necessary cost and material estimation for the SCAFFOLDING.

## Slide 4: About The Project
Now the CWorks CAD system has issues with processing the latest versions of AutoCAD drawing files.
As a solution for the above issue we are going to develop a system which converts the standard AutoCAD file format to a text exchange format (TXF format) along with a neutral exchange format for CWorks (CXF format) and vice versa.
IXF format should contain all properties & values of the objects in the AutoCAD drawing files.
CXF format contains only selected properties & values from the TXF format.
CXF files will be processed by the CWorks CAD system to create scaffold drawings.
Our proposed project interacts with the following software
  AutoCAD System
  CWorks CAD System
Notes: Make bullet points similar to the example bellow. You may need more than one slide:
Currently the C-Works CAD system has issues with processing the latest versions of AutoCAD drawing files.
As a solution for the above issue we are going to develop a system which converts the standard AutoCAD file format to a neutral data exchange format (CXF format) .
Custom format should contain all information about the objects in the AutoCAD drawing files in a simple text format.
The neutral format will be processed by the C-Works CAD system to process the drawing files.
Our proposed project interacts with the following software
  AutoCAD System
  C-WorksCAD System
Reverse conversion from CXF format to drawing files also need to be considered.

## Slide 5: Project Overview
Start Date : 15-10-2017
End Date : 31-03-2018
Total Estimated Effort : 200 man days
PM : Mr. Mohandas .P.M
PL : Mr. Suresh S
Customer Contact : Mr. Masa Yuki
QC Manager : Mr. George Elias
Notes: Fill in the informations

## Slide 6: Project Objectives
Functional objective | Developing a console application for processing drawing files and convert into a neutral text format for further processing in the CWorks CAD System. The system should support reverse conversion from Neutral file to AutoCAD drawings.
Technical objective | Achieve hands on experience in working with AutoCAD system related projects and open a new domain expertise.
Schedule objective | This project has to be commissioned before 31-March-2018
Cost objective | Maximum allocated manpower for this project is 10 man months.
Business objective | We would make this project as a stepping stone to enter into the CAD related domain , which has tremendous opportunities in Japan market.
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 7: Success Factors
System should be able to work with latest versions of AutoCAD files (AutoCAD 2000 and later versions).
The basic structure of CAD files should not be lost after conversion.
System should be completed & installed before the next financial year (before March 2018).
Delivered on time with expected quality.
Passing the UAT at one go by satisfying all the Acceptance Criteria specified in SRS.
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 8: Implementation
Tasks/activities
  Research on AutoCAD file processing API’s.
  Create the design documents for approval.
  Conversion of DWG file to TXF & CXF file.
  Conversion of DXF file to TXF & CXF file.
  Conversion of CXF file to DWG file with reference of TXF file.
  Conversion of CXF file to DXF file with reference of TXF file.
  Overall testing using different versions of AutoCAD drawings (AutoCAD 2000 and later versions).
  Deployment & Release of the CXF Conversion system.
Notes: May require more than one slide
Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 9: Implementation
Procedures
  Research on the CAD file structure & Open Design Alliance utilities.
  Preparation of the project documents based on the research.
  Communication with CWorks for final approval based on the project documents.
  Development of the CXF Conversion system.
  Execute functionality testing using different versions of AutoCAD files.
  Perform final verification in CWorks environment.
Notes: May require more than one slide
Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 10: Project Schedule and Milestones

## Slide 11: Project Schedule and Milestones

## Slide 12: Project Team Roles and Responsibilities
Development
Mohandas P M
Project Manager
Suresh S
Project Leader
Suraj P
Senior Developer
Masa Yuki Communicative Person
Suresh S
Senior Developer
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 13: Project Team Roles and Responsibilities
George Alias
QC Manager
Priska
Testing Person
QC
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 14: Project Team Roles and Responsibilities
Roles | Responsibilities
Project Manager | Planning and Defining Scope. Resource Planning. High level schedule estimation. Cost Estimation. Budget Planning. Risk Management. Project Status Monitoring & Control
Project Leader | Activity Planning and Sequencing. Develop detail Schedule. Activity Time Estimation. Documentation. Risk Identification and Analysis. Monitoring activity status & reporting status/progress to PM.
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 15: Project Team Roles and Responsibilities
Roles | Responsibilities
Senior Developer | System Design & Development Research and evaluate suitable libraries. Design & develop unit testing procedures and activities. Fixing of bugs reported by testing team. Implement best practices, standards and procedures.
Communicative Person | Clarification of doubts regarding the project with client. Conversion of mails from client and explain to the team.
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 16: Project Team Roles and Responsibilities
Roles | Responsibilities
QC Manager | Ensure the CXF conversion system meet acceptable quality standards. Coordinate team member efforts. Defining the scope of testing within the context of each release/delivery. Planning, deploying and managing the testing effort for any given engagement/release. Deciding the testing tools & processes.
Tester | Setting up the testing environment Develop test cases for testing Execute and log the test results, evaluate the results and document issues found.
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 17: Assumptions
Current issues are related to processing the latest versions of AutoCAD files in CWorks CAD System because of the incompatibility of the DXF format for 3D objects.
Proposed system need not support versions of AutoCAD earlier than AutoCAD 2000.
Teigha libraries are bug free as it is being maintained by a huge group of professional programmers and also it is a paid service.
CWorks CAD output will be the original drawing with added scaffolding structure.
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 18: Risk Management Plan

## Slide 19: Quality Management and Performance Measures
Accuracy of information of the objects in AutoCAD drawing files .
System should support conversion of AutoCAD drawing files (AutoCAD 2000 and later versions) to CXF files.
System should support reverse conversion of CXF files to AutoCAD drawing files (AutoCAD 2000 and later versions).
Quality and Accuracy testing on completion of each development phase.
Overall testing on completion of system functionalities.
Processing & Testing the AutoCAD file versions.
Ensure the quality of deliveries in each development phase through client interaction.
Notes: May require more than one slide

## Slide 20: Project Status Monitoring & Reporting
Programmers must report the progress to the PL everyday
PL to report the project progress status to PM every day
Tester to report the status to QC Manager every day
QC Manager to report the progress to PM every day
PM to report the project progress status to CEO every week.
Notes: May require more than one slide

## Slide 21: Tools And Technologies
Visual Studio Dot net 4.5 , C#
AutoCAD 2000 and later versions.
ODA – Open Design Alliance (Teigha library 4.3.11)
Notes: Follow the example given in the slide and provide the actual data corresponds to your project

## Slide 22: Any Questions?

## Slide 23: Thank You All