## Sheet1
Project Work Schedule
Task |  | Assignee | Estimated Start | Estimated Finish | Estimated Work (In Hours)
1 | Create the system prototype for client approval. | Joshy | 2019-06-03 | 2019-06-14 | 88
2 | Product List with search and filter. | Joshy | 2019-06-17 | 2019-07-24 | 248
3 | Product add/delete/update in admin module | Midhun | 2019-06-17 | 2019-06-25 | 64
4 | Product owner add/delete/update and product owner linking with products | Midhun | 2019-06-26 | 2019-07-04 | 54
5 | User(Customer) Registration/Edit/Deregistration and user page creation with chat. | Joshy | 2019-06-26 | 2019-08-13 | 136
6 | Customer and category add/delete/update in admin module | Midhun | 2019-07-05 | 2019-07-11 | 50
7 | View chat messages and deletion of messages - Category wise, Product wise and Customer wise. | Midhun | 2019-07-12 | 2019-07-24 | 80
8 | Product owner and customer page and their functionality. | Joshy | 2019-08-14 | 2019-08-24 | 108
9 | Customer feedback functionality | Gana | 2019-08-24 | 2019-08-29 | 40
10 | API for iOS | Gana | 2019-07-04 | 2019-07-16 | 80
11 | Reply messages | Joshy/Midhun | 2020-01-07 | 2020-02-10 | 90
12 | iOS functionality | Lithin | 2019-07-24 | 2019-09-02 | 264
13 | Application testing and bug fixing | Joshy/Midhun/Gana/Lithin | 2019-09-02 | 2019-09-19 | 128