## Binghan website
BINGHAN - Website |  | PHASE | START | END
|  | 1 | 2020-02-05 | 2020-04-16
LAST UPDATED ON: 30-July-2020 |  | 2 | 2020-03-16 | 2020-04-30
LAST UPDATED BY: Suresh S
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-07-30 | 2020-07-28 | 2020-07-20 | 2020-07-17 | 2020-07-16 | 2020-07-13 | 2020-07-03 | 2020-06-24 | 2020-06-23 | 2020-06-09 | 2020-06-08 | 2020-04-23 | 2020-04-22 | 2020-04-09 | 2020-04-08 | 2020-04-07 | 2020-03-16 | 2020-03-16 | 2020-03-14 | 2020-03-13 | 2020-03-12 | 2020-03-11 | 2020-03-10 | 2020-03-09 | 2020-03-06 | 2020-03-05 | 2020-03-04 | 2020-03-03 | 2020-03-02 | 2020-02-28 | 2020-02-11 | 2020-02-05
1 | Project Management | 1 | COMPLETE | Suresh | 5 | 9 | 2020-02-05 | 2020-02-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | Existing source code study and analysis and documentation | 1 | COMPLETE | Livin | 8 | 9 | 2020-02-28 | 2020-02-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | VIP Login & Administrator settings | 1 | COMPLETE | Livin | 16 | 15 | 2020-03-02 | 2020-03-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
4 | VIP Profile & Product modifications | 1 | COMPLETE | Livin | 16 | 17 | 2020-03-04 | 2020-03-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
5 | VIP Purchase | 1 | COMPLETE | Livin | 24 | 25 | 2020-03-06 | 2020-03-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 35%
6 | Testing & bug fixing (VIP Purchase) | 1 | COMPLETE | Livin | 8 | 8 | 2020-03-11 | 2020-03-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Integration Testing | 1 | COMPLETE | Livin | 32 | 24 | 2020-03-12 | 2020-03-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 65% | 30%
8 | Icon design | 1 | COMPLETE | Eldhose | 1 | 2 | 2020-03-14 | 2020-03-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Deployment of test URL for UAT | 2 | COMPLETE | Livin | 8 | 8 | 2020-03-16 | 2020-03-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Testing & bug fixing (VIP Purchase) | 2 | COMPLETE | Dileep | 4 | 3 | 2020-04-06 | 2020-04-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Modifications requested from the client | 2 | COMPLETE | Livin | 24 | 20 | 2020-04-01 | 2020-04-30 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 55% | 40% | 20%
Total Hours |  |  |  |  | 146 | 140
Change request after 08-06-2020
1 | > Vip Login Page design change > Vip Special Privacy and legal page > VIP Register Form with Validation > Admin-List and Add memberID > Member ID pass to email | 2 | COMPLETE | Livin | 16 | 16 | 2020-06-08 | 2020-06-09 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60%
2 | > VIP registration - Design & Field Changes | 2 | COMPLETE | Livin | 16 | 16 | 2020-06-23 | 2020-06-24 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60%
3 | > Register form pdf convention > Design changes | 2 | COMPLETE | Livin | 8 | 8 | 2020-07-03 | 2020-07-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | > VIP product changes > Design changes | 2 | COMPLETE | Livin | 8 | 8 | 2020-07-13 | 2020-07-13 | 100% | 100% | 100% | 100% | 100% | 100%
5 | > Calculation changes > Bug fixing | 2 | COMPLETE | Livin | 8 | 8 | 2020-07-16 | 2020-07-16 | 100% | 100% | 100% | 100% | 100%
6 | > Excel report changes | 2 | COMPLETE | Livin | 8 | 8 | 2020-07-17 | 2020-07-20 | 100% | 100% | 100% | 50%
7 | > Pop up message change > Registration and privacy legal page - Responsive Design | 2 | COMPLETE | Livin | 8 | 8 | 2020-07-28 | 2020-07-28 | 100% | 100%
8 | > Excel report changes > Home page design changes | 2 | COMPLETE | Livin | 4 | 6 | 2020-07-30 | 2020-07-30 | 100%
9 | > Excel report changes > Home page design changes | 2 | COMPLETE | Livin | 4 | 6 | 2020-07-30 | 2020-07-30 | 100%
10 | > Excel report changes > Home page design changes | 2 | COMPLETE | Livin | 4 | 6 | 2020-07-30 | 2020-07-30 | 100%
11 | > Responsive Design issues > Changes in the email content & bill details | 2 | COMPLETE | Livin | 16
Total Hours |  |  |  |  | 100 | 90