## Summary
Sl No | Start Date | Sheet Name | Expected End Date | Actual End Date | Reason for Delay
1 | 2020-05-13 | #CRM_schedule_1 | 2020-06-19 | 2020-06-24 | #Reason for delay
2 | 2020-05-13 | #CRM_schedule_2 | 2020-06-30 | 2020-06-30
3 | 2020-07-01 | #CRM_schedule_3 | 2020-07-10 | 2020-07-12
4 | 12-07-2020 | #CRM_schedule_4 | 2020-07-25 | 2020-07-25

## CRM_schedule_Rough
CRM - Application |  | PHASE | START | END
|  | 1 | 2020-05-13 | 2020-06-25
LAST UPDATED ON: 18-May-2020
LAST UPDATED BY: LIVIN CJ
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-05-18 | 2020-05-14 | 2020-05-13
1 | Project planning and schedule creation | 1 | COMPLETE | Livin | 8 | 8 | 2020-05-14 | 2020-04-15 | 100% | 100% | 50%
2 | Create SRS | 1 | COMPLETE | Livin | 4 | 4 | 2020-05-18 | 2020-05-18 | 100% | 0% | 0%
3 | Data base design and project enviornment setup | 1 | PLANNED | Livin | 4 |  |  |  |  | 0% | 0%
4 | Dashboard -- Design | 1 | PLANNED | Livin | 24
5 | Dashboard -- backend | 1 | PLANNED | Livin | 12
6 | Master- Branch | 1 | PLANNED | Livin | 4
7 | Master- category | 1 | PLANNED | Livin | 4
8 | Master- Designation && set rights | 1 | PLANNED | Syamily | 8
9 | Profile – Design + backend | 1 | PLANNED | Syamily | 4
Interim Release
10 | Add user – design +code | 1 | PLANNED | Livin | 6
11 | User list & Edit ,Delete ( search with status , name ) + design | 1 | PLANNED | Livin | 8
12 | Product & service + design | 1 | PLANNED | Syamily | 4
13 | Lead – Add lead + Design | 1 | PLANNED | Syamily | 8
14 | Lead List , Edit ,Delete, ( with different type search : date, name ,type , status ) + design | 1 | PLANNED | Syamily | 20
15 | Prospect – Add prospect + Design | 1 | PLANNED | Livin | 6
16 | Prospect List , Edit ,Delete, ( with different type search : date ,type , status ) + design | 1 | PLANNED | Livin | 6
Interim Release
17 | Appointment - Add appointment | 1 | PLANNED | Livin | 4
18 | Appointment - Listing (calender display ,Filtering) | 1 | PLANNED | Livin | 12
19 | Lead form /Customer details form -- Design | 1 | PLANNED | Syamily | 8
20 | Lead form /Customer details form -- backend | 1 | PLANNED | Syamily | 4
21 | Lead Details -- Note section ( APPOINTMENT DETAILS ) | 1 | PLANNED | Livin | 6
Interim Release
22 | Lead Details with Tab section -- Design | 1 | PLANNED | Livin | 8
23 | Lead Details - [ meeting appointment calender ] && calender List -- Design | 1 | PLANNED | Livin | 16
24 | Lead Details - [ meeting appointment calender ] -- backend | 1 | PLANNED | Livin | 4
25 | Load Details – Issue tracker form and listing –- design | 1 | PLANNED | Syamily | 8
26 | Load Details – Issue tracker form and listing –- backend | 1 | PLANNED | Syamily | 4
Interim Release
27 | Dashboard -- Appointment List with filter ( calender filter ) | 1 | PLANNED | Livin | 4
28 | Dashboard -- Issue track list with filter | 1 | PLANNED | Syamily | 4
29 | Load Details – Payment Details | 1 | PLANNED | Livin | 4
30 | Load Details – AMC | 1 | PLANNED | Livin | 4
31 | Weekly report | 1 | PLANNED | Syamily | 4
32 | Master- Configure Mail | 1 | PLANNED | Livin | 4
Interim Release
33 | Admin – assign multiple staff in one project | 1 | PLANNED | Syamily | 4
34 | Admin – change ownership | 1 | PLANNED | Syamily | 4
35 | Prospect – Location tracker (Map) | 1 | PLANNED | Livin | 4
36 | Integration Testing | 1 | PLANNED |  | 0
Total Hours |  |  |  |  | 240 | 12
Current Status : Applcation development planning

## CRM_schedule_1
CRM |  | PHASE | START | END
|  | 1 | 2020-05-13 | 2020-06-19
LAST UPDATED ON: 18-May-2020
LAST UPDATED BY: LIVIN CJ
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-05-18 | 2020-05-14 | 2020-05-13
1 | Project planning and schedule creation | 1 | COMPLETE | Livin | 8 | 8 | 2020-05-14 | 2020-04-15 | 100% | 100% | 50%
2 | Create SRS | 1 | COMPLETE | Livin | 4 | 4 | 2020-05-18 | 2020-05-18 | 100% | 0% | 0%
3 | Data base design and project enviornment setup | 1 | PLANNED | Livin | 4 |  |  |  |  | 0% | 0%
4 | Design prototype creation | 1 | PLANNED | Livin | 32
5 | Dashboard -- Design | 1 | PLANNED | Livin | 24
6 | Dashboard -- backend | 1 | PLANNED | Livin | 12
7 | Master- Branch | 1 | PLANNED | Livin | 6
8 | Master- category | 1 | PLANNED | Livin | 4
9 | Master- Designation && set rights | 1 | PLANNED | Syamili | 8
10 | Profile – Design + backend | 1 | PLANNED | Syamili | 6
Interim Release
11 | Add user – design +code | 1 | PLANNED | Livin | 6
12 | User list & Edit ,Delete ( search with status , name ) + design | 1 | PLANNED | Livin | 8
13 | Product & service + design | 1 | PLANNED | Syamili | 6
14 | Lead – Add lead + Design | 1 | PLANNED | Syamili | 8
15 | Lead List , Edit ,Delete, ( with different type search : date, name ,type , status ) + design | 1 | PLANNED | Syamili | 20
16 | Prospect – Add prospect + Design | 1 | PLANNED | Livin | 6
17 | Prospect List , Edit ,Delete, ( with different type search : date ,type , status ) + design | 1 | PLANNED | Livin | 6
Interim Release
18 | Appointment - Add appointment | 1 | PLANNED | Livin | 4
19 | Appointment - Listing (calender display ,Filtering) | 1 | PLANNED | Livin | 12
20 | Lead form /Customer details form -- Design | 1 | PLANNED | Syamili | 8
21 | Lead form /Customer details form -- backend | 1 | PLANNED | Syamili | 4
22 | Lead Details -- Note section ( APPOINTMENT DETAILS ) | 1 | PLANNED | Livin | 6
Interim Release
23 | Lead Details with Tab section -- Design | 1 | PLANNED | Livin | 8
24 | Lead Details - [ meeting appointment calender ] && calender List -- Design | 1 | PLANNED | Livin | 16
25 | Lead Details - [ meeting appointment calender ] -- backend | 1 | PLANNED | Livin | 4
26 | Load Details – Issue tracker form and listing –- design | 1 | PLANNED | Syamili | 8
27 | Load Details – Issue tracker form and listing –- backend | 1 | PLANNED | Syamili | 4
Interim Release
28 | Dashboard -- Appointment List with filter ( calender filter ) | 1 | PLANNED | Livin | 4
29 | Dashboard -- Issue track list with filter | 1 | PLANNED | Syamili | 6
30 | Load Details – Payment Details | 1 | PLANNED | Livin | 4
31 | Load Details – AMC | 1 | PLANNED | Livin | 4
32 | Weekly report | 1 | PLANNED | Syamili | 4
33 | Master- Configure Mail | 1 | PLANNED | Livin | 4
Interim Release
34 | Admin – assign multiple staff in one project | 1 | PLANNED | Syamili | 4
35 | Admin – change ownership | 1 | PLANNED | Syamili | 4
36 | Prospect – Location tracker (Map) | 1 | PLANNED | Livin | 4
37 | Integration Testing | 1 | PLANNED | Syamili | 32
Total Hours |  |  |  |  | 312 | 12
Current Status : Applcation development planning

## CRM_schedule_2
CRM - Application |  | PHASE | START | END | EXPECTED
|  | 1 | 2020-05-13 | 2020-06-19 | 2020-06-30
LAST UPDATED ON: 25-June-2020
LAST UPDATED BY: Syamili mol k.v
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-14 | 2020-05-13
1 | Project planning and schedule creation | 1 | COMPLETE | Livin | 8 | 8 | 2020-05-14 | 2020-04-15 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | Create SRS | 1 | COMPLETE | Livin | 4 | 4 | 2020-05-18 | 2020-05-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
3 | Data base design and project enviornment setup | 1 | COMPLETE | Livin | 4 | 4 | 2020-05-19 | 2020-05-19 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0%
4 | Data base design and project enviornment setup | 1 | COMPLETE | Syamili | 4 | 6 | 2020-05-21 | 2020-05-21 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
5 | Design prototype creation | 1 | COMPLETE | Livin | 32 | 32 | 2020-05-20 | 2020-05-23 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 50% | 25% | 0% | 0% | 0% | 0%
6 | Design prototype creation | 1 | COMPLETE | Syamili | 12 | 17 | 2020-05-22 | 2020-05-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 50% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
7 | Dashboard -- Design | 1 | COMPLETE | Livin | 24 | 24 | 2020-05-25 | 2020-05-27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 50%
8 | Dashboard -- backend | 1 | COMPLETE | Syamili | 12 | 5 | 2020-06-23 | 2020-06-23 | 100% | 100% | 100%
9 | Master- Branch | 1 | PROGRESS | Livin | 6 | 8 | 2020-05-28 | 2020-05-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Master- category | 1 | PROGRESS | Livin | 4 | 4 | 2020-05-29 | 2020-05-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Master- Designation && set rights | 1 | PROGRESS | Livin | 8 | 16 | 2020-05-29 | 2020-05-30 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0%
12 | Profile – Design + backend | 1 | COMPLETE | Syamili | 6 | 6 | 2020-06-04 | 2020-06-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80%
Interim Release
13 | Add user – design +code | 1 | COMPLETE | Livin | 6 | 16 | 2020-06-01 | 2020-06-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 40%
14 | User list & Edit ,Delete + design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-03 | 2020-06-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0%
15 | Product & service + design | 1 | COMPLETE | Syamili | 6 | 8 | 2020-05-30 | 2020-06-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
16 | Lead – Add lead + Design | 1 | COMPLETE | Syamili | 8 | 8 | 2020-06-02 | 2020-06-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75%
17 | Lead List , Edit ,Delete, ( with different type search : date, name ,type , status ) + design | 1 | COMPLETE | Syamili | 20 | 28 | 2020-06-05 | 2020-06-17 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 80% | 60% |  |  | 40% | 30% |  | 10%
18 | Prospect – Add prospect + Design | 1 | COMPLETE | Livin | 6 | 16 | 2020-06-04 | 2020-06-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
19 | Prospect List , Edit ,Delete, ( with different type search : date ,type , status ) + design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-10 | 2020-06-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | Prospect List , Edit ,Delete, ( with different type search : date ,type , status ) + design | 1 | COMPLETE | Syamili | 6 | 8 | 2020-06-19 | 2020-06-22 | 100% | 100% | 100% | 100% | 80%
Interim Release
21 | Appointment - Add appointment | 1 | COMPLETE | Livin | 4 | 8 | 2020-06-12 | 2020-06-12 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
22 | Appointment - Listing ( Filtering) | 1 | PLANNED | Livin | 12 | 16 | 2020-06-13 | 2020-06-15 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
23 | Lead form /Customer details form -- Design | 1 | PLANNED | Syamili | 8 | 4 | 2020-06-19 | 2020-06-22 | 100% | 100% | 100% | 100% | 50%
24 | Lead form /Customer details form -- backend | 1 | PLANNED | Syamili | 4 | 4 | 2020-06-22 | 2020-06-22 | 100% | 100% | 100% | 100%
25 | Lead Details -- Note section ( APPOINTMENT DETAILS ) | 1 | PLANNED | Livin | 6 | 8 | 2020-06-16 | 2020-06-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Interim Release
26 | Lead Details with Tab section -- Design | 1 | PLANNED | Livin | 8 | 8 | 2020-06-18 | 2020-06-18 | 100% | 100% | 100% | 100% | 100% | 100%
27 | Lead Details - [ meeting appointment calender ] && calender List -- Design | 1 | PLANNED | Livin | 16 | 16 | 2020-06-19 | 2020-06-18 | 100% | 100% | 100% | 100% | 100% | 50%
28 | Lead Details - [ meeting appointment calender ] -- backend | 1 | PLANNED | Livin | 4 | 6 | 2020-06-22 | 2020-06-22 | 100% | 100% | 100% | 100%
29 | Load Details – Issue tracker form and listing –- design | 1 | PLANNED | Syamili | 8
30 | Load Details – Issue tracker form and listing –- backend | 1 | PLANNED | Syamili | 4
Interim Release
31 | Dashboard -- Appointment List with filter | 1 | COMPLETE | Syamili | 4 | 4 | 2020-06-24 | 2020-06-24 | 100% | 100%
32 | Dashboard -- Issue track list with filter | 1 | COMPLETE | Syamili | 6 | 4 | 2020-06-24 | 2020-06-24 | 100% | 100%
33 | Load Details – Payment Details | 1 | PLANNED | Livin | 4 | 4 | 2020-06-25 | 2020-06-25 | 50%
34 | Load Details – AMC | 1 | PLANNED | Livin | 4
35 | Weekly report | 1 | PLANNED | Syamili | 4
36 | Master- Configure Mail | 1 | PLANNED | Livin | 4
Interim Release
37 | Admin – assign multiple staff in one project | 1 | PLANNED | Syamili | 4
38 | Admin – change ownership | 1 | PLANNED | Syamili | 4
39 | Prospect – Location tracker (Map) | 1 | PLANNED | Livin | 4
40 | Integration Testing | 1 | PLANNED |  | 32
Extended Tasks
41 | SRS Modifications | 1 | COMPLETE | Syamili | 8 | 8 | 2020-05-28 | 2020-05-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
42 | CRM User Guide | 1 | PROGRESS | Syamili | 12 | 4 | 2020-06-08 | 2020-06-08 | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25%
43 | Multilanguage | 1 | PLANNED | Syamili | 16 | 5 | 2020-06-18 | 2020-06-18 | 30% | 30% | 30% | 30% | 30% | 30%
44 | Design prototype changes | 1 | COMPLETE | Syamili | 12 | 12 | 2020-06-11 | 2020-06-12 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 25%
45 | Document – Upload + Design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-17 | 2020-06-17 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
46 | Product developers - Add,Edit,Delete and Listing | 1 | PLANNED | Syamili | 4 | 4 | 2020-06-25 | 2020-06-25 | 100%
Total Hours |  |  |  |  | 396 | 357
Current Status : Development In Progress, Delayed due to modifications & Binghan project

## CRM_schedule_3
CRM - Application |  | PHASE | START | END | EXPECTED
|  | 1 | 2020-05-13 | 2020-06-22 | 2020-06-30
LAST UPDATED ON: 07-July-2020 |  | 2 | 2020-06-30 |  | 2020-07-10
LAST UPDATED BY: Syamili mol k.v
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-14 | 2020-05-13
1 | Project planning and schedule creation | 1 | COMPLETE | Livin | 8 | 8 | 2020-05-14 | 2020-04-15 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | Create SRS | 1 | COMPLETE | Livin | 4 | 4 | 2020-05-18 | 2020-05-18 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
3 | Data base design and project enviornment setup | 1 | COMPLETE | Livin | 4 | 4 | 2020-05-19 | 2020-05-19 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0%
4 | Data base design and project enviornment setup | 1 | COMPLETE | Syamili | 4 | 6 | 2020-05-21 | 2020-05-21 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
5 | Design prototype creation | 1 | COMPLETE | Livin | 32 | 32 | 2020-05-20 | 2020-05-23 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 50% | 25% | 0% | 0% | 0% | 0%
6 | Design prototype creation | 1 | COMPLETE | Syamili | 12 | 17 | 2020-05-22 | 2020-05-26 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 50% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
7 | Dashboard -- Design | 1 | COMPLETE | Livin | 24 | 24 | 2020-05-25 | 2020-05-27 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 50%
8 | Dashboard -- backend | 1 | COMPLETE | Syamili | 12 | 9 | 2020-06-23 | 2020-06-29 |  | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50%
9 | Master- Branch | 1 | PROGRESS | Livin | 6 | 8 | 2020-05-28 | 2020-05-28 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Master- category | 1 | PROGRESS | Livin | 4 | 4 | 2020-05-29 | 2020-05-29 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Master- Designation && set rights | 1 | PROGRESS | Livin | 8 | 16 | 2020-05-29 | 2020-05-30 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0%
12 | Profile – Design + backend | 1 | COMPLETE | syamili | 6 | 6 | 2020-06-04 | 2020-06-05 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80%
Interim Release
13 | Add user – design +code | 1 | COMPLETE | Livin | 6 | 16 | 2020-06-01 | 2020-06-02 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 40%
14 | User list & Edit ,Delete + design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-03 | 2020-06-03 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0%
15 | Product & service + design | 1 | COMPLETE | syamili | 6 | 8 | 2020-05-30 | 2020-06-01 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
16 | Lead – Add lead + Design | 1 | COMPLETE | syamili | 8 | 8 | 2020-06-02 | 2020-06-03 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75%
17 | Lead List , Edit ,Delete, ( with different type search : date, name ,type , status ) + design | 1 | COMPLETE | syamili | 20 | 28 | 2020-06-05 | 2020-06-17 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 80% | 60% |  |  | 40% | 30% |  | 10%
18 | Prospect – Add prospect + Design | 1 | COMPLETE | Livin | 6 | 16 | 2020-06-04 | 2020-06-05 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
19 | Prospect List , Edit ,Delete, ( with different type search : date ,type , status ) + design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-10 | 2020-06-10 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | Prospect List , Edit ,Delete, ( with different type search : date ,type , status ) + design | 1 | COMPLETE | syamili | 6 | 8 | 2020-06-19 | 2020-06-22 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80%
Interim Release
21 | Appointment - Add appointment | 1 | COMPLETE | Livin | 4 | 8 | 2020-06-12 | 2020-06-12 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
22 | Appointment - Listing ( Filtering) | 1 | PLANNED | Livin | 12 | 16 | 2020-06-13 | 2020-06-15 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
23 | Lead form /Customer details form -- Design | 1 | PLANNED | syamili | 8 | 4 | 2020-06-19 | 2020-06-22 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
24 | Lead form /Customer details form -- backend | 1 | PLANNED | syamili | 4 | 4 | 2020-06-22 | 2020-06-22 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Lead Details -- Note section ( APPOINTMENT DETAILS ) | 1 | PLANNED | Livin | 6 | 8 | 2020-06-16 | 2020-06-16 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Interim Release
26 | Lead Details with Tab section -- Design | 1 | PLANNED | Livin | 8 | 8 | 2020-06-18 | 2020-06-18 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
27 | Lead Details - [ meeting appointment calender ] && calender List -- Design | 1 | PLANNED | Livin | 16 | 16 | 2020-06-19 | 2020-06-18 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
28 | Lead Details - [ meeting appointment calender ] -- backend | 1 | PLANNED | Livin | 4 | 6 | 2020-06-22 | 2020-06-22 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
29 | Load Details – Issue tracker form and listing –- design | 1 | PLANNED | syamili | 8
30 | Load Details – Issue tracker form and listing –- backend | 1 | PLANNED | syamili | 4
Interim Release
31 | Dashboard -- Appointment List with filter | 1 | COMPLETE | syamili | 4 | 11 | 2020-06-24 | 2020-06-27 |  | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100%
32 | Dashboard -- Issue track list with filter | 1 | COMPLETE | syamili | 6 | 3.5 | 2020-06-24 | 2020-06-24 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
33 | Load Details – Payment Details | 1 | PLANNED | Livin | 4 | 4 | 2020-06-25 | 2020-06-25 |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
34 | Load Details – Payment Details | 1 | COMPLETE | syamili | 2 | 2 | 2020-06-26 | 2020-06-26 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100%
35 | Load Details – AMC | 1 | COMPLETE | syamili | 4 | 2 | 2020-06-26 | 2020-06-26 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100%
36 | Weekly report | 1 | COMPLETE | syamili | 4 | 10 | 2020-06-30 | 2020-07-02
37 | Master- Configure Mail | 1 | PLANNED | Livin | 4
Interim Release
38 | Admin – assign multiple staff in one project | 1 | PLANNED | syamili | 4
39 | Admin – change ownership | 1 | PLANNED | syamili | 4
40 | Prospect – Location tracker (Map) | 1 | PLANNED | Livin | 4
41 | Integration Testing | 1 | PLANNED | syamili | 16 | 11.5 | 2020-06-29 | 2020-06-30 |  | 50% | 50% | 50% | 50% | 50%
41 | Integration Testing | 1 | PLANNED | livin | 16 | 16 | 2020-06-29 | 2020-06-30 |  | 50% | 50% | 50% | 50% | 50%
42 | SRS Modifications | 1 | COMPLETE | syamili | 8 | 8 | 2020-05-28 | 2020-05-28 | [8 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
43 | CRM User Guide | 1 | PROGRESS | syamili | 12 | 4 | 2020-06-08 | 2020-06-08 | [8 empty] | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25%
44 | Language Switching | 1 | PLANNED | syamili | 16 | 5 | 2020-06-18 | 2020-06-18 | [8 empty] | 30% | 30% | 30% | 30% | 30% | 30%
45 | Design prototype changes | 1 | COMPLETE | syamili | 12 | 12 | 2020-06-11 | 2020-06-12 | [8 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 25%
46 | Document – upload + design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-17 | 2020-06-17 | [8 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
47 | Product developers - Add,Edit,Delete and Listing | 1 | PLANNED | syamili | 4 | 4 | 2020-06-25 | 2020-06-25 | [8 empty] | 100%
Changes Requested
48 | Dashboard – Changes | 1 | COMPLETE | livin | 8 | 8 | 2020-06-26 | 2020-06-26 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100%
49 | All lists displayed in the dashboard should be collapsable. | 2 | PLANNED | livin | 3
50 | Reduce the spacing and re-align the controls to include 4 controls in a row. | 2 | PLANNED | livin | 4
51 | While the user edits the client details, client information should be displayed in a collapsible manner and the other information like Notes, Appointments, Documents, Issue Tracker, Payment & AMC details should be visible without scrolling. | 2 | PLANNED | livin | 8
52 | Add one more Contact Number and Email Address. Person In Charge details may not be required. | 2 | COMPLETE | livin | 1 | 1 | 2020-07-06 | 2020-07-06 | 100%
53 | Admin should be able to assign a representative name to a client. | 2 | PLANNED | livin | 3
54 | Prevent duplicate client names. | 2 | PLANNED | livin | 4 | 4 | 2020-07-06 | 2020-07-06 | 100%
55 | Show an alert and confirmation for a duplicate mobile number and email address. | 2 | PLANNED | livin | 1 | 1 | 2020-07-06 | 2020-07-06 | 100%
56 | Notes should not be formatted, need only a plain text area. | 2 | COMPLETE | syamili | 2 | 2 | 2020-07-06 | 2020-07-06 | 100%
57 | Admin should be able to change the Note Created Date and Next Followup Date | 2 | COMPLETE | livin | 2 | 2 | 2020-07-06 | 2020-07-06 | 100%
58 | Add a person in charge for each Issue Tracker. Display the delivery date in the issue list. | 2 | COMPLETE | syamili | 6 | 6 | 2020-07-03 | 2020-07-06 | 100% | 75%
59 | Send mail to the person In charge of assigning an issue. | 2 | PROGRESS | syamili | 4
60 | While the person In charge login he should be able to see the issues and set the resolved status. | 2 | PLANNED | livin | 6
61 | Create reports of customers payment lists based on customers and representatives. | 2 | PLANNED | syamili | 8
Total Hours |  |  |  |  | 338 | 368
Current Status : Development In Progress, Delayed due to design changes & Binghan project
Expected Delivery Date : 10-July-2020

## CRM_schedule_4
CRM - Application |  | PHASE | START | END | EXPECTED | EXPECTED II
|  | 1 | 2020-05-13 | 2020-06-22 | 2020-06-30
LAST UPDATED ON: 24-July-2020 |  | 2 | 2020-06-30 |  | 2020-07-10 | 2020-07-25
LAST UPDATED BY: Syamili mol k.v
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-07-23 | 2020-07-22 | 2020-07-12 | 2020-07-11 | 2020-07-10 | 2020-07-09 | 2020-07-08 | 2020-07-07 | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-14 | 2020-05-13
1 | Project planning and schedule creation | 1 | COMPLETE | Livin | 8 | 8 | 2020-05-14 | 2020-04-15 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | Create SRS | 1 | COMPLETE | Livin | 4 | 4 | 2020-05-18 | 2020-05-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
3 | Data base design and project enviornment setup | 1 | COMPLETE | Livin | 4 | 4 | 2020-05-19 | 2020-05-19 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0%
4 | Data base design and project enviornment setup | 1 | COMPLETE | Syamili | 4 | 6 | 2020-05-21 | 2020-05-21 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
5 | Design prototype creation | 1 | COMPLETE | Livin | 32 | 32 | 2020-05-20 | 2020-05-23 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 50% | 25% | 0% | 0% | 0% | 0%
6 | Design prototype creation | 1 | COMPLETE | Syamili | 12 | 17 | 2020-05-22 | 2020-05-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 50% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
7 | Dashboard -- Design | 1 | COMPLETE | Livin | 24 | 24 | 2020-05-25 | 2020-05-27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 50%
8 | Dashboard -- backend | 1 | COMPLETE | Syamili | 12 | 9 | 2020-06-23 | 2020-06-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50%
9 | Master- Branch | 1 | PROGRESS | Livin | 6 | 8 | 2020-05-28 | 2020-05-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Master- category | 1 | PROGRESS | Livin | 4 | 4 | 2020-05-29 | 2020-05-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Master- Designation && set rights | 1 | PROGRESS | Livin | 8 | 16 | 2020-05-29 | 2020-05-30 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0%
12 | Profile – Design + backend | 1 | COMPLETE | Syamili | 6 | 6 | 2020-06-04 | 2020-06-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80%
Interim Release
13 | Add user – design +code | 1 | COMPLETE | Livin | 6 | 16 | 2020-06-01 | 2020-06-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 40%
14 | User list & Edit ,Delete + design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-03 | 2020-06-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0%
15 | Product & service + design | 1 | COMPLETE | Syamili | 6 | 8 | 2020-05-30 | 2020-06-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
16 | Lead – Add lead + Design | 1 | COMPLETE | Syamili | 8 | 8 | 2020-06-02 | 2020-06-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75%
17 | Lead List , Edit ,Delete, ( with different type search : date, name ,type , status ) + design | 1 | COMPLETE | Syamili | 20 | 28 | 2020-06-05 | 2020-06-17 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 80% | 60% |  |  | 40% | 30% |  | 10%
18 | Prospect – Add prospect + Design | 1 | COMPLETE | Livin | 6 | 16 | 2020-06-04 | 2020-06-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
19 | Prospect List , Edit ,Delete, ( with different type search : date ,type , status ) + design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-10 | 2020-06-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | Prospect List , Edit ,Delete, ( with different type search : date ,type , status ) + design | 1 | COMPLETE | Syamili | 6 | 8 | 2020-06-19 | 2020-06-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80%
Interim Release
21 | Appointment - Add appointment | 1 | COMPLETE | Livin | 4 | 8 | 2020-06-12 | 2020-06-12 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
22 | Appointment - Listing ( Filtering) | 1 | PLANNED | Livin | 12 | 16 | 2020-06-13 | 2020-06-15 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
23 | Lead form /Customer details form -- Design | 1 | PLANNED | Syamili | 8 | 4 | 2020-06-19 | 2020-06-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
24 | Lead form /Customer details form -- backend | 1 | PLANNED | Syamili | 4 | 4 | 2020-06-22 | 2020-06-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Lead Details -- Note section ( APPOINTMENT DETAILS ) | 1 | PLANNED | Livin | 6 | 8 | 2020-06-16 | 2020-06-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Interim Release
26 | Lead Details with Tab section -- Design | 1 | PLANNED | Livin | 8 | 8 | 2020-06-18 | 2020-06-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
27 | Lead Details - [ meeting appointment calender ] && calender List -- Design | 1 | PLANNED | Livin | 16 | 16 | 2020-06-19 | 2020-06-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
28 | Lead Details - [ meeting appointment calender ] -- backend | 1 | PLANNED | Livin | 4 | 6 | 2020-06-22 | 2020-06-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
29 | Load Details – Issue tracker form and listing –- design | 1 | PLANNED | Syamili | 8
30 | Load Details – Issue tracker form and listing –- backend | 1 | PLANNED | Syamili | 4
Interim Release
31 | Dashboard -- Appointment List with filter | 1 | COMPLETE | Syamili | 4 | 11 | 2020-06-24 | 2020-06-27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100%
32 | Dashboard -- Issue track list with filter | 1 | COMPLETE | Syamili | 6 | 3.5 | 2020-06-24 | 2020-06-24 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
33 | Load Details – Payment Details | 1 | PLANNED | Livin | 4 | 4 | 2020-06-25 | 2020-06-25 | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
34 | Load Details – Payment Details | 1 | COMPLETE | Syamili | 2 | 2 | 2020-06-26 | 2020-06-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
35 | Load Details – AMC | 1 | COMPLETE | Syamili | 4 | 2 | 2020-06-26 | 2020-06-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
36 | Weekly report | 1 | COMPLETE | Syamili | 4 | 10 | 2020-06-30 | 2020-07-02
37 | Master- Configure Mail | 1 | PLANNED | Livin | 4
Interim Release
38 | Admin – assign multiple staff in one project | 1 | PLANNED | Syamili | 4
39 | Admin – change ownership | 1 | PLANNED | Syamili | 4
40 | Prospect – Location tracker (Map) | 1 | PLANNED | Livin | 4
41 | Integration Testing | 1 | PLANNED | Syamili | 16 | 16.5 | 2020-06-29 | 2020-07-11 | 75% | 75% | 75% | 75% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
41 | Integration Testing | 1 | PLANNED | livin | 16 | 16 | 2020-06-29 | 2020-06-30 | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
42 | SRS Modifications | 1 | COMPLETE | Syamili | 8 | 8 | 2020-05-28 | 2020-05-28 | [16 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
43 | CRM User Guide | 1 | PROGRESS | Syamili | 12 | 4 | 2020-06-08 | 2020-06-08 | [16 empty] | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25%
44 | Language Switching | 1 | PLANNED | Syamili | 16 | 5 | 2020-06-18 | 2020-06-18 | [16 empty] | 30% | 30% | 30% | 30% | 30% | 30%
45 | Design prototype changes | 1 | COMPLETE | Syamili | 12 | 12 | 2020-06-11 | 2020-06-12 | [16 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 25%
46 | Document – upload + design | 1 | COMPLETE | Livin | 8 | 8 | 2020-06-17 | 2020-06-17 | [16 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
47 | Product developers - Add,Edit,Delete and Listing | 1 | PLANNED | Syamili | 4 | 4 | 2020-06-25 | 2020-06-25 | [16 empty] | 100%
Changes Requested
48 | Dashboard – Changes | 1 | COMPLETE | livin | 8 | 8 | 2020-06-26 | 2020-06-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
49 | All lists displayed in the dashboard should be collapsable. | 2 | COMPLETE | livin | 3 | 3 | 2020-07-10 | 2020-07-10 | 100% | 100% | 100% | 100% | 100%
50 | Reduce the spacing and re-align the controls to include 4 controls in a row. | 2 | COMPLETE | livin | 4 |  | 2020-07-10 | 2020-07-10 | 100% | 100% | 100% | 100% | 100%
51 | While the user edits the client details, client information should be displayed in a collapsible manner and the other information like Notes, Appointments, Documents, Issue Tracker, Payment & AMC details should be visible without scrolling. | 2 | COMPLETE | livin | 6 | 6 | 2020-07-10 | 2020-07-10 | 100% | 100% | 100% | 100% | 100%
52 | Add one more Contact Number and Email Address. Person In Charge details may not be required. | 2 | COMPLETE | livin | 1 | 1 | 2020-07-06 | 2020-07-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
53 | Admin should be able to assign a representative name to a client. | 2 | COMPLETE | livin | 3
54 | Prevent duplicate client names. | 2 | COMPLETE | livin | 4 | 4 | 2020-07-06 | 2020-07-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
55 | Show an alert and confirmation for a duplicate mobile number and email address. | 2 | COMPLETE | livin | 1 | 1 | 2020-07-06 | 2020-07-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
56 | Notes should not be formatted, need only a plain text area. | 2 | COMPLETE | Syamili | 2 | 2 | 2020-07-06 | 2020-07-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
57 | Admin should be able to change the Note Created Date and Next Followup Date | 2 | COMPLETE | livin | 2 | 2 | 2020-07-06 | 2020-07-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
58 | Add a person in charge for each Issue Tracker. Display the delivery date in the issue list. | 2 | COMPLETE | Syamili | 6 | 6 | 2020-07-03 | 2020-07-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75%
59 | Send mail to the person In charge of assigning an issue. | 2 | PROGRESS | Syamili | 4 | 4 | 2020-07-07 | 2020-07-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
60 | While the person In charge login he should be able to see the issues and set the resolved status. | 2 | PLANNED | livin | 6
61 | Create reports of customers payment lists based on customers and representatives. | 2 | COMPLETE | Syamili | 8 | 8 | 2020-07-08 | 2020-07-09 | 100% | 100% | 100% | 100% | 100% | 100% | 50%
| Seperate login for Developer Users login . After login they can only view thier assigned issues. |  | COMPLETE | livin | 16 | 16 | 2020-07-07 | 2020-07-09 | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 1899-12-31
62 | The date reflecting on the dashboard needs to be corrected. Right now the client created date is being reflected. |  | COMPLETE | Syamili | 2 | 2 | 2020-07-10 | 2020-07-10 | 100% | 100% | 100% | 100% | 100%
| Pending followup in dashboard |  | COMPLETE | Syamili | 2 | 2 | 2020-07-10 | 2020-07-10 | 100% | 100% | 100% | 100% | 100%
| Cloud details tab |  | COMPLETE | Syamili | 4 | 4 | 2020-07-11 | 2020-07-11 | 100% | 100% | 100% | 100% | 100%
63 | Whenever a note gets deleted, it should only be soft-deleted, The deleted data should be visible to admin. |  | COMPLETE | Livin | 4 | 4 | 2020-07-10 | 2020-07-10 | 100% | 100% | 100% | 100% | 100%
64 | Spacing should be adjusted in the dashboard such a way that notes can be seen clearly. |  | COMPLETE | Livin | 2 | 2 | 2020-07-11 | 2020-07-11 | 100% | 100% | 100% | 100% | 100%
65 | Correct the Font size. |  | COMPLETE | Livin | 2 | 2 | 2020-07-11 | 2020-07-11 | 100% | 100% | 100% | 100% | 100%
66 | The rep. name should not take much space. Maybe an abbreviation or first name is enough. |  | COMPLETE | Livin | 0.5 | 0.5 | 2020-07-11 | 2020-07-11 | 100% | 100% | 100% | 100% | 100%
67 | There should be 3 boxes for phone numbers for all clients. a)Mobile number, b) Alternate number, c) Landline number. |  | COMPLETE | Livin | 4 | 4 | 2020-07-11 | 2020-07-11 | 100% | 100% | 100% | 100% | 100%
68 | No need to display the person-in-charge section separately. |  | COMPLETE | Livin | 1 | 1 | 2020-07-11 | 2020-07-11 | 100% | 100% | 100% | 100% | 100%
69 | 'Note' entry date does not have to be kept mandatory. putting a pre-date option should be given only to admin. |  | COMPLETE | Livin | 2 | 2 | 2020-07-12 | 2020-07-12 | 100% | 100% | 100% | 100%
70 | In the appointment list "Purpose" should be kept mandatory. |  | COMPLETE | LIVIN | 0.5 | 0.5 | 2020-07-12 | 2020-07-12 | 100% | 100% | 100% | 100%
71 | There should be notification in the dashboard if a followup is not completed, both for the admin and salesperson. |  | COMPLETE | LIVIN | 4 | 4 | 2020-07-12 | 2020-07-12 | 100% | 100% | 100% | 100%
72 | There should be a notification in the dashboard if the client details are not 100% completed. Even if they are able to document the client, 'notification' should be there in the dashboard showing the number of incomplete profiles. |  | complete | Livin | 4 | 4 | 2020-07-12 | 2020-07-12 | 100% | 100% | 100% | 100%
73 | Lead: Add a new feature -- Action Required option -- only for Admin. |  | Pending | Livin | 4 | 4 | 2020-07-24
74 | "DISTRICT" ,"STATE", "COUNTRY" should be drop down list and mandatory. |  | Pending | Livin | 2 | 2 | 2020-07-23
75 | Add new field "City/Town" which is input value.4. Make Address mandatory. |  | Pending | Livin | 1 | 1 | 2020-07-23
76 | Mobile number OR Lan Number is required. Validate and show alert. |  | Pending | Livin | 0.5 | 0.5 | 2020-07-23
77 | Add Lead status (Condition status = NEW, FOLLOWUP, ALL) -- lead status can be changed manually. Not Sure whether 'All' is needed. Created lead should automatically have the status 'New' and then its status is changed once a follow up is done. |  | Pending | Livin | 3 | 3 | 2020-07-24
78 | Change "Report Date" to "Lead Create Date" (only admin can change the date). |  | Completed | Livin | 2 | 2 | 2020-07-22
79 | Add the "Delete" button near the "Update" button. Remove delete option from lead, prospect & customer list. |  | Pending | Livin | 1 | 1 | 2020-07-23
80 | Note Section: Note create design change - Required "+" button for new note. (Required some research) |  | Pending | Livin | 5 | 5 | 2020-07-25
81 | Reduce space ( Reduce space in the client lead details sections. 4 fields in a row at the top. Fields that require more spaces can be kept below. The client name should be present at the top near to "CREATE LEAD" OR that word can be replaced by the NAME itself. |  | Pending | Livin | 1 | 1 | 2020-07-25
82 | Note list should be displayed as date in descending order. (Old date should be at the bottom and always latest note should be at the top. The serial number or follow up a number of the 'notes' should follow the same way) |  | Pending | Livin | 1 | 1 | 2020-07-25
83 | Whille sorting serial number should not be changed (table row number). |  | Pending | Syamili | 1 | 1 | 2020-07-25
84 | Admin need hard delete option in note section |  | Completed | Livin | 3 | 3 | 2020-07-22 | 2020-07-22 | 100% | 100%
85 | Add new feature "ROUGH NOTE". |  | Pending | Livin | 4 | 4 | 2020-07-25
86 | Daily report: Change the "Note created date" to "Followup date". |  | Completed | Syamili | 0.25 | 0.25 | 2020-07-23
87 | Add count of the notes and payments (if possible). |  | Pending
88 | Lead List : Add new columns, lead created date && note created date. The format should be the following way in both "lead list", "prospect list", "customer list" |  | complete | Syamili | 2 | 3 | 2020-07-23 | 2020-07-23 | 100%
89 | Remove the Email column. |  | Completed | Syamili | 0.5 | 1 | 2020-07-23 | 2020-07-23 | 100%
90 | Database report: Change the tile from "Customer Report" to "Database report". |  | Completed |  |  |  | 2020-07-22 | 2020-07-23 | 100%
91 | "Customer" option should be selected in the dropdown by default. |  | Completed | Syamili | 0.25 | 0.25 | 2020-07-23 | 2020-07-23
92 | Create Excel report for the report. |  | Pending | Syamili | 4 | 2 | 2020-07-23 | 2020-07-24
93 | Common: Remove email in every list. |  | completed | Syamili |  |  | 2020-07-23
94 | "Delete" button - required confirmation on delete. |  | completed | Livin | 1 | 1 | 2020-07-22
95 | General search for client. |  | completed | Livin | 4 | 4 | 2020-07-22 | 2020-07-22 | 100% | 100%
96 | Another user can add notes to another user client |  | completed | Livin | 4 | 4 | 2020-07-23 | 2020-07-23 | 100%
97 | Change the field "Representative Name" to "Sales Person" in every list. |  | Completed | Livin | 0.5 | 0.5 | 2020-07-22 | 2020-07-22
98 | Add the next and previous date buttons in the pending follow-up section. To see all the pending follow-up |  | Completed | Syamili | 4 | 4 | 2020-07-25
99 | Add a new column for developers to add issue description in the Issue Report section |  | Completed | Syamili | 3 | 3 | 2020-07-24
100 | Remove the update option for sales users in the notes section |  | Completed | Livin | 1 | 1 | 2020-07-24
101 | Once the lead is deleted, they should not reflect on another list. Right now few deleted leads appear in the appointment list. |  | Completed | Livin | 1 | 1
102 | Except for admin, users should not have the right to delete any leads. |  | Completed | Livin | 1 | 1
103 | Admin/or the manager should be able to put a note to do a followup for a particular client or lead and the salesperson should get it as a notification in their dashboard. Once the follow up is finished sales person can add the status as completed and the same will be reflected in the Admin's dashboard. |  | Pending | Livin | 1 | 1
Total Hours |  |  |  |  | 560 | 562.5
Current Status : Development In Progress, Delayed due to design changes & Binghan project
Expected Delivery Date : 25-July-2020

## Overall MOM
Sl No | Meeting Date | Task | status | Completed Date | EST. HRS | ACT. HRS
1 | 19-05-2020 | Create design (HTML) Prototype | Completed | 26-05-2020 | 44 | 49
2 |  | Suggestions (new feature warm percentage ) | Completed | 26-05-2020 | 0.5 | 0.5
3 | 03-06-2020 | Create the Test Plan Document | Pending | 10-06-2020
4 |  | Create the code review standards (Laravel) | Completed | 10-06-2020
5 |  | Create the code review checklist | Pending
6 |  | Interim Release | Completed | 10-06-2020
7 | 11-06-2020 | Design change in the dashboard. | Completed | 12-06-2020 | 8 | 8
8 |  | Make a single form for lead, prospects, and customer creation. Change the design prototype based on the above. | Completed | 12-06-2020
9 |  | Remove remarks and enquiry fields from the form. | Completed | 12-06-2020
10 |  | Set an option to view the deleted notes to the admin. | Completed | 12-06-2020 | 4 | 4
12 | 24-06-2020 | Overall design changes – remove spacing | Completed | 30-06-2020 | 6 | 6
13 |  | Use Text editor in Note section. | Completed | 30-06-2020
14 |  | Allow special permissions to the admin | Completed | 30-06-2020
15 |  | Add client server hosting details & other information | Completed | 30-06-2020 | 4 | 4
16 |  | Dashboard - more filter options and design changes | Completed | 30-06-2020 | 6 | 6
17 | 01-07-2020 | Dashboard
18 |  | All lists displayed in the dashboard should be collapsable. | Completed | 12-07-2020 | 3 | 3
19 |  | Appointment list should include the Representative Name. | Completed | 12-07-2020 | 0.5 | 0.5
20 |  | Lead/ Prospect/ Customer
21 |  | Reduce the spacing and re-align the controls to include 4 controls in a row. Add accordian in the lead. | Completed | 12-07-2020 | 4
22 |  | While the user edits the client details, client information should be displayed in a collapsible manner and the other information like Notes, Appointments, Documents, Issue Tracker, Payment & AMC details should be visible without scrolling. | Completed | 12-07-2020 | 6 | 6
23 |  | Add one more Contact Number and Email Address. | Completed | 12-07-2020 | 1 | 1
24 |  | Person In Charge details may not be required. | Completed | 12-07-2020
25 |  | Admin should be able to assign a representative name to a client. | Completed | 12-07-2020 | 3 | 2
26 |  | Prevent duplicate client names. | Completed | 12-07-2020 | 4 | 4
27 |  | Show an alert and confirmation for a duplicate mobile number. | Completed | 12-07-2020 | 0.5 | 0.5
28 |  | Show an alert and confirmation for a duplicate email address. | Completed | 12-07-2020 | 0.5 | 0.5
29 |  | Notes should not be formatted, need only a plain text area. | Completed | 12-07-2020 | 2 | 2
30 |  | Admin should be able to change the Note Created Date. | Completed | 05-07-2020 | 1 | 1
31 |  | Admin should be able to change the Next Followup Date. | Completed | 05-07-2020 | 1 | 1
32 |  | Add a person in charge for each Issue Tracker. | Completed | 12-07-2020 | 6 | 6
33 |  | Send mail to the person In charge of assigning an issue. | Completed | 12-07-2020 | 4 | 4
34 |  | While the person In charge login he should be able to see the issues and set the resolved status. | Completed | 12-07-2020 | 6 | 4
35 |  | Display the delivery date in the issue list. | Completed | 12-07-2020 | 8 | 8
36 |  | Reports
37 |  | Create reports of customers' payment lists based on customers and representatives. | Completed | 12-07-2020 | 8 | 8
| 07-07-2020 | Seperate login for Developer Users login . After login they can only view thier assigned issues. | Completed | 12-07-2020 | 16 | 16
38 |  | The date reflecting on the dashboard needs to be corrected. Right now the client created date is being reflected. | Completed | 12-07-2020 | 2 | 2
39 |  | Whenever a note gets deleted, it should only be soft-deleted, The deleted data should be visible to admin. | Completed | 12-07-2020 | 4 | 4
40 |  | Spacing should be adjusted in the dashboard such a way that notes can be seen clearly. | Completed | 12-07-2020 | 2 | 2
41 |  | Correct the Font size. | Completed | 12-07-2020 | 2 | 2
42 |  | The rep. name should not take much space. Maybe an abbreviation or first name is enough. | Completed | 12-07-2020 | 0.5 | 0.5
43 |  | There should be 3 boxes for phone numbers for all clients. a)Mobile number, b) Alternate number, c) Landline number. | Completed | 12-07-2020 | 4 | 4
44 |  | No need to display the person-in-charge section separately. | Completed | 12-07-2020 | 1 | 1
45 |  | 'Note' entry date does not have to be kept mandatory. putting a pre-date option should be given only to admin. | Completed | 12-07-2020 | 2 | 2
46 |  | In the appointment list "Purpose" should be kept mandatory. | Completed | 12-07-2020 | 0.5 | 0.5
47 |  | There should be notification in the dashboard if a followup is not completed, both for the admin and salesperson. | Completed | 12-07-2020 | 4 | 4
48 |  | There should be a notification in the dashboard if the client details are not 100% completed. Even if they are able to document the client, 'notification' should be there in the dashboard showing the number of incomplete profiles. | Completed | 12-07-2020 | 4 | 4
49 | 15-07-2020 | LEAD
50 |  | Add a new feature -- Action Required option -- only for Admin. | completed | 25-07-2020 | 4 | 4
51 |  | "DISTRICT" ,"STATE", "COUNTRY" should be drop down list and mandatory. | completed | 25-07-2020 | 2 | 2
52 |  | Add new field "City/Town" which is input value.4. Make Address mandatory. | completed | 25-07-2020 | 1 | 1
53 |  | Mobile number OR Lan Number is required. Validate and show alert. | completed | 25-07-2020 | 0.5 | 0.5
54 |  | Add Lead status (Condition status = NEW, FOLLOWUP, ALL) -- lead status can be changed manually. Not Sure whether 'All' is needed. Created lead should automatically have the status 'New' and then its status is changed once a follow up is done. | completed | 25-07-2020 | 3 | 3
55 |  | Change "Report Date" to "Lead Create Date" (only admin can change the date). | Completed | 25-07-2020 | 2 | 2
56 |  | Add the "Delete" button near the "Update" button. Remove delete option from lead, prospect & customer list. | completed | 25-07-2020 | 1 | 1
57 |  | Note Section
58 |  | Note create design change - Required "+" button for new note. (Required some research) | completed | 25-07-2020 | 5 | 5
59 |  | Reduce space ( Reduce space in the client lead details sections. 4 fields in a row at the top. Fields that require more spaces can be kept below. The client name should be present at the top near to "CREATE LEAD" OR that word can be replaced by the NAME itself. | completed | 25-07-2020 | 1 | 1
60 |  | Note list should be displayed as date in descending order. (Old date should be at the bottom and always latest note should be at the top. The serial number or follow up a number of the 'notes' should follow the same way) | completed | 25-07-2020 | 1 | 1
61 |  | Whille sorting serial number should not be changed (table row number). | completed | 25-07-2020 | 1 | 1
62 |  | Admin need hard delete option in note section | Completed | 25-07-2020 | 3 | 3
63 |  | Add new feature "ROUGH NOTE". | completed | 25-07-2020 | 4 | 4
64 |  | Daily report
65 |  | Change the "Note created date" to "Followup date". | Completed | 25-07-2020 | 0.25 | 0.25
66 |  | Add count of the notes and payments (if possible).
67 |  | Lead List
68 |  | Add new columns, lead created date && note created date. The format should be the following way in both "lead list", "prospect list", "customer list" | completed | 25-07-2020 | 2 | 3
69 |  | Remove the Email column. | Completed | 25-07-2020 | 0.5 | 1
70 |  | Database report
71 |  | Change the tile from "Customer Report" to "Database report". | Completed | 25-07-2020
72 |  | "Customer" option should be selected in the dropdown by default. | completed | 25-07-2020 | 0.25 | 0.25
73 |  | Create Excel report for the report. | completed | 25-07-2020 | 4 | 2
74 |  | Common
75 |  | "Delete" button - required confirmation on delete. | completed | 25-07-2020 | 1 | 1
76 | 21-07-2020 | General search for client. | completed | 25-07-2020 | 4 | 4
77 |  | Another user can add notes to another user client.They cannot edit each other's notes. | completed | 25-07-2020 | 4 | 4
78 |  | Change the field "Representative Name" to "Sales Person" in every list. | Completed | 25-07-2020 | 0.5 | 0.5
79 |  | Commonly change " created date" to "note created date" in every list. | Completed | 25-07-2020
80 |  | Add the next and previous date buttons in the pending follow-up section. To see all the pending follow-up | completed | 25-07-2020 | 4 | 4
81 |  | Add a new column for developers to add issue description in the Issue Report section | completed | 25-07-2020 | 3 | 3
82 |  | Remove the update option for sales users in the notes section | completed | 25-07-2020 | 1 | 1
83 |  | In the daily report name corresponding to the 'new follow up note' should be of the person who actually enters the notes irrespective of whose client it is. When an admin creates old clients, all the entry should be in Admin's name but when checking the customer details, the assigned person can be seen. | completed | 25-07-2020
84 |  | The date should be reflected in the following way:10-Jan-2020, 2-Sep-2020. This was discussed in the last to last meeting. | completed | 25-07-2020 | 2 | 2
85 |  | Admin/or the manager should be able to put a note to do a followup for a particular client or lead and the salesperson should get it as a notification in their dashboard. Once the follow up is finished sales person can add the status as completed and the same will be reflected in the Admin's dashboard. | Pending | 25-07-2020 | 1 | 1
86 |  | Once the lead is deleted, they should not reflect on another list. Right now few deleted leads appear in the appointment list. | completed | 25-07-2020 | 1 | 1
87 |  | Except for admin, users should not have the right to delete any leads. | completed | 25-07-2020 | 1 | 1
88 |  | The other day 2 'prospects' in the CRM were shown as "new prospect created" in the daily report again. | completed | 25-07-2020
89 | 24-07-2020 | Adjust the space in daily report | completed | 25-07-2020 | 0.5 | 0.5
90 |  | Complete the crm project according to current schedule | completed | 25-07-2020
91 |  | Please check the 3rd point of MOM dated 24th July: Admin/or the manager should be able to put a note to do a followup for a particular client or lead and the salesperson should get it as a notification in their dashboard. Once the follow up is finished sales person can add the status as completed and the same will be reflected in the Admin's dashboard. As per the new update, when the follow up is completed by the assigned person it goes from the admin dashboard but has no option to view what was the follow up which was made. It would be better the result of the follow up reflects corresponding to it. | Pending
92 |  | Keep history of assigned persons | Pending
93
[5 empty] | 231.5 | 229

## Reason for schedule extension
Reason for schedule extension
Schedule I - Create by Livin on May-18-2020
This schedule was created with half day work for Livin and Syamili.
Total Estimated Hours - 240
End Date - 25/06/2020
Please find the attachment for the schedule sheet (CRM_schedule_1.xlsx)
Schedule II - Revised schedule on 22-May-2020
This schedule was recreated with full day work for Livin and half day work for Syamili.
Total Estimated Hours - 312
End Date - 19-June-2020
Please find the attachment for the schedule sheet (CRM_schedule_2.xlsx)
Expected delay in delivery date
Livin was working for the BINGHAN project.
No of days - 4 days (8-June-2020, 9-June-2020, 23-June-2020, 24-June-2020)
After the Meeting on 11-June-2020
Design changes to create the Lead, Prospect & Customer as a single screen.
Estimated days - 1
After the Meeting on 24-June-2020Design changes (reduce the overall spacing)Estimated days - 3 days(CRM_schedule_3.xlsx)
Change History - Schedule Date
Initial End Date - 19-June-2020
+ Binghan - 4 days
+ Changes 11-June-2020 - 1 dayRevised End Date - 26-June-2020+ Changes 24-June-2020- 3 days Expected Delivery Date - 30-June-2020