## 3-12-2020
Sl.No | Task Name | Start Date | End Date | Owner | Status | Hours
1 | Change the color of highlights holiday dates in Calendar shown in the dashboard |  |  | Ayana | In progress | 1
2 | Change Design to avoid scrolling |  |  | Ayana | In progress | 16
3 | Change Edit, Delete Button. |  |  | Tinu | In progress | 1
4 | Change employee details view in admin and HR module |  |  | Tinu | In progress | 14
5 | Change design as tab pane |  |  | Ayana | In progress | 24
6 | Change in add project details in employee module(change technology test field to multiple selection dropdown) |  |  | Tinu | In progress | 24
7 | Change in mail notification, attach page link to approve leave directly |  |  | Ayana | In progress | 16
8 | Change client holiday list add |  |  | Ayana | In progress | 16
9 | Project list dropdown is shown based on the client |  |  | Tinu | In progress | 6
10 | Change submit button to save button |  |  | Tinu | In progress | 1
11 | Client wise leave is allocated to every employees |  |  | Ayana | In progress | 24
12 | Remove Reset button from every pages |  |  | Tinu | In progress | 3
13 | Detailed leave report view |  |  | Tinu | In progress | 8
14 | Change personal information in sidebar to tab view |  |  | Ayana | In progress | 16
15 | Change in SRS document( No need to exclude CRUD in heading) |  |  | Ayana | Completed
16 | Change the structure of SDD document |  |  | Ayana | In progress | 8
17 | Create new SRS Document for HRMIS project. |  |  | Ayana | Completed

## 07-12-2020
Sl. No. | Task Name | Start Date | End Date | Owner | Status | Hours
1 | Change the color of highlights holiday dates in Calendar shown in the dashboard |  |  | Ayana | In progress | 1
2 | Change Design to avoid scrolling |  |  | Ayana | In progress | 16
3 | Change Edit, Delete Button. |  |  | Tinu | In progress | 1
4 | Change employee details view in admin and HR module |  |  | Tinu | In progress | 14
5 | Change design as tab pane |  |  | Ayana | In progress | 24
6 | Change in add project details in employee module(change technology test field to multiple selection dropdown) |  |  | Tinu | In progress | 24
7 | Change in mail notification, attach page link to approve leave directly |  |  | Ayana | In progress | 16
8 | Change client holiday list add |  |  | Ayana | In progress | 16
9 | Project list dropdown is shown based on the client |  |  | Tinu | In progress | 6
10 | Change submit button to save button |  |  | Tinu | In progress | 1
11 | Client wise leave is allocated to every employees |  |  | Ayana | In progress | 24
12 | Remove Reset button from every pages |  |  | Tinu | In progress | 3
13 | Detailed leave report view |  |  | Tinu | In progress | 8
14 | Change personal information in sidebar to tab view |  |  | Ayana | In progress | 16
15 | Change in SRS document( No need to exclude CRUD in heading) |  |  | Ayana | Completed
16 | Change the structure of SDD document |  |  | Ayana | In progress | 8
17 | Create new SRS Document for HRMIS project. |  |  | Ayana | Completed