## ProjectSchedule
PROJECT : Reeps - ARC
Client | ARC |  | Delivery Dates
Team | Suresh, Aslam
| Project Start: |  | 2020-10-21
| Display Week: |  | 1 |  |  |  |  | 2020-10-19 | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07
 | time axis 2020-10-19 to 2020-12-13
TASK | ASSIGNED TO | PROGRESS | PLANNED START DATE | PLANNED END DATE | ACTUAL START DATE | ACTUAL END DATE | DAYS | time axis 2020-10-19 to 2020-12-13
Phase 1 : Department Module
Project Setup and initialisation | ASLAM | 100% | 2020-10-21 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2
Db setup & Restoring | ASLAM | 100% | 2020-10-23 | 2020-10-24 | 2020-10-23 | 2020-10-24 | 2
Indocosmo Git Setup | ASLAM | 100% | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2020-10-27 | 1
Common Validations ( request method, content-type,etc ) | ASLAM | 100% | 2020-10-27 | 2020-10-29 | 2020-10-27 | 2020-10-29 | 3
Listing API coding | ASLAM | 100% | 2020-10-30 | 2020-11-03 | 2020-10-30 | 2020-11-03 | 5
Registration & Updation API coding | ASLAM | 100% | 2020-11-04 | 2020-11-11 | 2020-11-04 | 2020-11-11 | 8
Deletion API coding | ASLAM | 100% | 2020-11-11 | 2020-11-13 | 2020-11-11 | 2020-11-13 | 3
Listing API Unit Test Case Preparation | ASLAM | 100% | 2020-11-14 | 2020-11-16 | 2020-11-14 | 2020-11-16 | 3
Listing API unit test module coding | ASLAM | 90% | 2020-11-17 | 2020-11-19 | 2020-11-17 |  | 3
Registration & Updation API Unit Test Case Preparation | ASLAM | 0% | 2020-11-20 | 2020-11-23 |  |  | 4
Registration & Updation API unit test module coding | ASLAM | 0% | 2020-11-24 | 2020-12-01 |  |  | 8
Deletion API unit test case preparation | ASLAM | 0% | 2020-12-02 | 2020-12-03 |  |  | 2
Deletion API unit test module coding | ASLAM | 0% | 2020-12-04 | 2020-12-07 |  |  | 4
Review |  | 0% | 2020-12-08 | 2020-12-09 |  |  | 2
Modifications or Bug Fixing | ASLAM | 0% | 2020-12-10 | 2020-12-13 |  |  | 4
Final Delivery | ASLAM | 0% | 2020-12-14 | 2020-12-14 |  |  | 1