## Version 0
Carry Park - Basic Version |  | PHASE | START | END
|  | 1 | 2019-12-02 | 2020-04-15
LAST UPDATED ON: 02-May-2020
LAST UPDATED BY: Suresh S
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-05-02 | 2020-05-01 | 2020-04-30 | 2020-04-29 | 2020-04-28 | 2020-04-27 | 2020-04-26 | 2020-04-25 | 2020-04-24 | 2020-04-23 | 2020-04-22 | 2020-04-21 | 2020-04-20 | 2020-04-17 | 2020-04-16 | 2020-04-15 | 2020-04-13 | 2020-04-09 | 2020-04-08 | 2020-04-07 | 2020-04-06 | 2020-04-03 | 2020-04-02 | 2020-04-01 | 2020-03-31 | 2020-03-30 | 2020-03-28 | 2020-03-27 | 2020-03-26 | 2020-03-25 | 2020-03-24
Design & Documentation
1 | System Analysis & Design | COMPLETE | Suresh | 160 | 160 | 2020-12-02 | 2020-12-27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | System Prototype | COMPLETE | Suresh | 160 | 200 | 2020-12-30 | 2020-02-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Documentation | PROGRESS | Suresh | 80 | 80 | 2020-02-03 | 2020-02-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Multilanguage support | PROGRESS | Suresh | 32 | 40 | 2020-02-04 | 2020-09-07 | 100% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
5 | Cloud Settings | PROGRESS | Suresh | 80 | 96 | 2020-02-10 | 2020-02-20 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
User Registration
6 | User Registration - iOS - App | PROGRESS | Outsource | 40 | 40 | 2020-02-10 | 2020-02-20 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | User Registration - Android - App | PROGRESS | Outsource | 40 | 40 | 2020-02-10 | 2020-02-20 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | User Registration - Cloud Server | PROGRESS | Outsource | 24 | 32 | 2020-02-10 | 2020-02-20 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Device Locking
9 | Device Locking - iOS - App | PROGRESS | Outsource | 96 | 112 | 2020-02-21 | 2020-03-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Device Locking - Android - App | PROGRESS | Outsource | 96 | 96 | 2020-02-21 | 2020-03-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Device Locking - Cloud Server | PROGRESS | Outsource | 48 | 56 | 2020-02-21 | 2020-03-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Device Unlocking
12 | Device Unlocking - iOS - App | PROGRESS | Outsource | 96 | 112 | 2020-03-06 | 2020-03-19 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Device Unlocking - Android - App | PROGRESS | Outsource | 96 | 96 | 2020-03-06 | 2020-03-19 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Device Unlocking - Cloud Server | PROGRESS | Outsource | 48 | 56 | 2020-03-06 | 2020-03-19 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Payment Integration
15 | Payment Integration - iOS - App | PROGRESS | Outsource | 80 | 96 | 2020-03-03 | 2020-05-02 | 100% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
16 | Payment Integration - Android - App | PROGRESS | Outsource | 80 | 80 | 2020-03-03 | 2020-05-02 | 100% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
17 | Payment Integration - Cloud Server | PROGRESS | Outsource | 24 | 32 | 2020-03-03 | 2020-05-02 | 100% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Integration Testing
18 | FW Testing | PROGRESS | Lithin | 24 | 40 | 2020-03-05 | 2020-05-02 | 100% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
19 | Modifications , Testing & Bug Fixing | PROGRESS | Outsource | 16 | 80 | 2020-03-06 | 2020-05-02 | 100% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 80% | 80% | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
20 | Release of Phase 1 | PROGRESS | Suresh | 8 | 24 | 2020-03-30 | 2020-05-02 | 100% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
| Total Man Hours |  |  | 1328 | 1568
1 | Project Management - Support | PROGRESS | Suresh | 40 | 21 | 2020-03-23 | 2020-04-10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PHASE 1
2 | Testing & Documentation | PROGRESS | Lithin | 28 | 33 | 2020-03-24 | 2020-03-27 | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 80% | 70% | 40%
PHASE 2
3 | Security Implementation - Server | PROGRESS | Dileep | 32 | 27 | 2020-03-25 |  | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 70% | 60% | 30% | 10% | 0%
4 | Security Implementation - iOS | PROGRESS | Lithin | 40 | 6 | 2020-03-25 |  | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 20% | 10% | 10% | 10% | 0%
5 | Security Implementation - Android | PLANNED | Tinu | 24 |  |  |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0%
6 | Modifications in the current source code - Server | PLANNED | Dileep | 40 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | Modifications in the current source code - iOS | PLANNED | Lithin | 40 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8 | Modifications in the current source code - Android | PLANNED | Tinu | 40 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9 | Testing & Bug fixing | PLANNED | Dileep | 16 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10 | Testing & Bug fixing | PLANNED | Lithin | 16 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11 | Testing & Bug fixing | PLANNED | Tinu | 16 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12 | Release for UAT - Phase 1 | PLANNED | Suresh | 8 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PHASE 2
13 | List the nearby lock devices by location in the app - Server | PLANNED | Dileep | 16 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14 | List the nearby lock devices by location in the app - iOS | PLANNED | Lithin | 16 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15 | List the nearby lock devices by location in the app - Android | PLANNED | Lithin | 16 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16 | Error reporting to the cloud - Server | PLANNED | Dileep | 12 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17 | Error reporting to the cloud - iOS | PLANNED | Lithin | 12 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18 | Error reporting to the cloud - Android | PLANNED | Lithin | 8 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
19 | Dashboard - display the incidents | PLANNED | Dileep | 8 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
20 | Dashboard - display the device usage rate | PLANNED | Dileep | 16 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
21 | Dashboard - display the revenue details | PLANNED | Dileep | 16 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
22 | Testing & Bug fixing | PLANNED | Dileep | 16
23 | Testing & Bug fixing | PLANNED | Lithin | 16
24 | Testing & Bug fixing | PLANNED | Tinu | 16
25 | Release for UAT - Phase 2 | PLANNED | Suresh | 8 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Current Status : Phase 1 Completed, Multilanguage Implementation Pending

## Version 1
Carry Park - Security Process |  | PHASE | START | END
|  | 2 | 2020-03-24 | 2020-04-29
LAST UPDATED ON: 12-June-2020
LAST UPDATED BY: Suresh S
Security Implementation セキューリテイ 関連
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-06-02
Design & Documentation
2 | Design & Documentation | COMPLETE | Suresh | 48 | 48 | 2020-03-24 | 2020-04-27 | 100%
3 | Security Implementation - iOS - App | COMPLETE | Lithin | 40 | 56 | 2020-03-24 | 2020-05-04 | 100%
4 | Security Implementation - Android - App | PROGRESS | Tinu | 40 | 64 | 2020-05-06 | 2020-06-04 | 100%
5 | Security Implementation - Cloud Server | COMPLETE | Dileep | 40 | 48 | 2020-03-24 | 2020-05-04 | 100%
Integration Testing
6 | Integration Testing with FW sample テスト | COMPLETE | Lithin | 32 | 44 | 2020-05-12 | 2020-06-04 | 100%
7 | Release of Phase 2 導入 | PROGRESS | Suresh | 8 | 8 |  |  | 80%
8 | Total Man Hours |  |  | 208 | 268
| Expected Date of Completion | [6 empty] | 2020-06-03
| Actual Date of Completion | [6 empty] | 2020-06-04
Current Status : Phase 2 Android Testing Completed. Waiting for client demo

## Version 2
Carry Park - Screen Changes |  | PHASE | START | END
|  | 3 | 2020-05-30 | 2020-06-12
LAST UPDATED ON: 25-June-2020
LAST UPDATED BY: Suresh S
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-14 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-07 | 2020-06-06 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30
1 | User Registration - iOS (1.Login screen design change, 2.Registration screen design changes, 3.Registration screen popup, 4.Login as new phone, Mac id updste API, 5.Forgot pin hide pin text filed, 6. Login as new phone reset the pin and navigation, 7. Testing) | COMPLETED | Lithin | 8 | 10 | 2020-06-01 | 2020-06-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | User Registration - Android (1.Login screen design change, 2.Registration screen design changes, 3.Registration screen popup, 4.Login as new phone, Mac id updste API, 5.Forgot pin hide pin text filed, 6. Login as new phone reset the pin and navigation, 7. Testing) | COMPLETED | Tinu | 8 | 9 | 2020-06-06 | 2020-06-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | New Scan - iOS ( 1. Design changes) | COMPLETED | Lithin | 8 | 8 | 2020-06-02 | 2020-06-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | New Scan Device Location - iOS (1. Edit current navigation flow, 2.Integrate google map and map functions, 3. API integration for loading devices) | COMPLETED | Lithin | 32 | 35 | 2020-06-03 | 2020-06-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 50% | 25%
5 | New Scan - Android ( 1. Design changes) | COMPLETED | Tinu | 8 | 8 | 2020-06-07 | 2020-06-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | New Scan Device Location - Android (1. Edit current navigation flow, 2.Integrate google map and map functions, 3. API integration for loading devices) | COMPLETED | Tinu | 24 | 12 | 2020-06-08 | 2020-06-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | In Use Section - iOS (1. Design changes, In use device listing) | COMPLETED | Lithin | 8 | 8 | 2020-06-08 | 2020-06-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | In Use Device Location - iOS (1. Edit current navigation flow, 2.Integrate google map and map functions, 3. API integration for loading devices) | COMPLETED | Lithin | 8 | 8 | 2020-06-09 | 2020-06-09 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | In Use Section - Android (1. Design changes, In use device listing) | COMPLETED | Tinu | 8 | 8 | 2020-06-09 | 2020-06-09 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | In Use Device Location - Android (1. Edit current navigation flow, 2.Integrate google map and map functions, 3. API integration for loading devices) | COMPLETED | Lithin | 8 | 12 | 2020-06-10 | 2020-06-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60%
11 | Device Location Master - Cloud (Create a location lookup master and inlcude the location map) | COMPLETED | Dileep | 8 | 8 | 2020-05-30 | 2020-05-30 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | Device Location - Cloud ( Populate the locations from the master to set the device location while adding a new Device in the Cloud - to avoid repetition of goole location setting for each device) | COMPLETED | Dileep | 8 | 8 | 2020-06-01 | 2020-06-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Rate Information Screen - including Video - iOS (1. Design changes) | COMPLETED | Lithin | 8 | 8 | 2020-06-10 | 2020-06-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Rate Information screen including Video - Android (1. Design changes) | COMPLETED | Tinu | 8 | 8 | 2020-06-10 | 2020-06-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Scan QR Code - Changes - iOS (Modifications in the QR code scanning for specific area scan) | COMPLETED | Lithin | 16 | 18 | 2020-06-10 | 2020-06-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
16 | Scan QR Code - Changes - Android (Modifications in the QR code scanning for specific area scan) | COMPLETED | Tinu | 8 | 8 | 2020-06-11 | 2020-06-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
17 | Manage Devices - Cloud (Create / Edit / Delete) - Add Device Type to Devices - ("Normal Device" & "Contract Device". API modifications for the payment bypass - Cloud | COMPLETED | Dileep | 8 | 12 | 2020-06-02 | 2020-06-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
18 | Create Business Customers - Cloud (Create / Edit / Delete) - Create Business Customers in three different categories and assign devices to them | COMPLETED | Dileep | 16 | 24 | 2020-06-05 | 2020-06-09 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 75% | 50% | 25%
19 | Payment Bypass - iOS - (Check the device status and bypass payment for Contract Devices) | COMPLETED | Lithin | 16 | 14 | 2020-06-12 | 2020-06-13 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
20 | Payment Bypass - Android (Check the device status and bypass payment for Contract Devices) | COMPLETED | Tinu | 16 | 15 | 2020-06-12 | 2020-06-13 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
20 | Payment Bypass - Cloud (APIs for bypass payment for Contract Devices) | COMPLETED | Dileep | 16 | 16 | 2020-06-10 | 2020-06-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
21 | Testing & Bug Fixing - iOS | COMPLETED | Lithin | 32 | 37 | 2020-06-13 | 2020-06-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 60% | 30%
22 | Testing & Bug Fixing - Android | COMPLETED | Tinu | 32 | 40 | 2020-06-13 | 2020-06-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 60% | 30%
22 | Testing & Bug Fixing - Cloud | COMPLETED | Dileep | 16 | 20 | 2020-06-13 | 2020-06-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 60% | 30%
Total Man Hours |  |  |  | 328 | 354
Expected Date of Completion | [7 empty] | 2020-06-12
Current Status - Completed the client demo

## Version 3
Maintenance & Dashboard |  | PHASE | START | END - I | END - II
|  | 4 | 2020-06-16 | 2020-07-22 | 2020-07-31
LAST UPDATED ON: 13-August-2020
LAST UPDATED BY: Suresh S
Maintenance App
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09 | 2020-09-08 | 2020-09-07 | 2020-09-05 | 2020-09-04 | 2020-09-03 | 2020-09-02 | 2020-08-28 | 2020-08-27 | 2020-08-26 | 2020-08-25 | 2020-08-24 | 2020-08-22 | 2020-08-21 | 2020-08-20 | 2020-08-19 | 2020-08-18 | 2020-08-17 | 2020-08-14 | 2020-08-13 | 2020-08-12 | 2020-08-11 | 2020-08-10 | 2020-08-08 | 2020-08-07 | 2020-08-06 | 2020-08-05 | 2020-08-04 | 2020-08-02 | 2020-08-03 | 2020-07-31 | 2020-07-30 | 2020-07-29 | 2020-07-28 | 2020-07-27 | 2020-07-25 | 2020-07-24 | 2020-07-23 | 2020-07-22 | 2020-07-21 | 2020-07-20 | 2020-07-17 | 2020-07-16 | 2020-07-15 | 2020-07-14 | 2020-07-13 | 2020-07-11 | 2020-07-10 | 2020-07-09 | 2020-07-08 | 2020-07-07 | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16
12 | Maintenance Screen Design - iOS | COMPLETED | Lithin | 24 | 24 | 2020-07-11 | 2020-06-25 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 70% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
13 | Maintenance Screen Design - Android | COMPLETED | Tinu | 24 | 35 | 2020-06-25 | 2020-06-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 30%
14 | User Login - iOS - Project Setup, Splash screen, login Screen design and API | COMPLETED | Lithin | 16 | 8 | 2020-07-13 | 2020-07-13 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | User Login - Android - Project Setup, Splash screen, login Screen design and API | COMPLETED | Tinu | 16 | 16 | 2020-07-11 | 2020-07-13 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
16 | Task Listing - iOS | COMPLETED | Lithin | 8 | 8 | 2020-07-14 | 2020-07-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
17 | Task Listing - Android | COMPLETED | Tinu | 8 | 8 | 2020-07-14 | 2020-07-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | Menu Items Display - iOS | COMPLETED | Lithin | 8 | 4 | 2020-07-15 | 2020-07-15 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
19 | Menu Items Display - Android | COMPLETED | Tinu | 8 | 8 | 2020-07-15 | 2020-07-15 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | Scan & Device Details (Install) - iOS - Design, API, QR code reading | COMPLETED | Lithin | 12 | 12 | 2020-07-15 | 2020-07-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30%
21 | Scan & Device Details (Install) - Android - Design, API, QR code reading | COMPLETED | Tinu | 12 | 12 | 2020-07-15 | 2020-07-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30%
22 | Upload Images (Install) - iOS - Design, Uploading file, Progress, listing uploaded image listing, Pic multiple image picker from gallery | COMPLETED | Lithin | 24 | 24 | 2020-06-27 | 2020-08-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 75% | 40%
23 | Upload Images (Install) - Android - Design, Uploading file, Progress, listing uploaded image listing, Pic multiple image picker from gallery | COMPLETED | Tinu | 24 | 24 | 2020-06-23 | 2020-08-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 75% | 40%
24 | Work Details & Location (Install) - iOS | COMPLETED | Lithin | 8 | 8 | 2020-06-28 | 2020-06-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Work Details & Location (Install) - Android | COMPLETED | Tinu | 8 | 8 | 2020-06-27 | 2020-06-27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
26 | Summary screen (Install) - iOS | COMPLETED | Lithin | 8 | 8 | 2020-06-29 | 2020-06-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
27 | Summary screen (Install) - Android | COMPLETED | Tinu | 8 | 8 | 2020-06-28 | 2020-06-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
28 | Scan & Device Details (Repair) - iOS | COMPLETED | Lithin | 8 | 8 | 2020-07-20 | 2020-07-20 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
29 | Scan & Device Details (Repair) - Android | COMPLETED | Tinu | 8 | 8 | 2020-07-20 | 2020-07-20 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
30 | Upload Images (Repair) - iOS | COMPLETED | Lithin | 4 | 4 | 2020-08-27 | 2020-08-27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
31 | Upload Images (Repair) - Android | COMPLETED | Tinu | 4 | 4 | 2020-06-28 | 2020-06-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
32 | Work Details & Location (Repair) - iOS | COMPLETED | Lithin | 8 | 8 | 2020-08-08 | 2020-08-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
33 | Work Details & Location (Repair) - Android | COMPLETED | Tinu | 8 | 10 | 2020-06-28 | 2020-06-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
34 | Summary screen (Repair) - iOS | COMPLETED | Lithin | 4 | 4 | 2020-08-12 | 2020-08-12 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
35 | Summary screen (Repair) - Android | COMPLETED | Tinu | 4 | 4 | 2020-06-28 | 2020-06-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
36 | Locking Screen - iOS - BLT integration, BLT connection, Security implimentation | COMPLETED | Lithin | 12 | 12 | 2020-07-21 | 2020-07-21 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
37 | Locking Screen - Android - BLT integration, BLT connection, Security implimentation | COMPLETED | Tinu | 12 | 12 | 2020-07-21 | 2020-07-21 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
38 | Release Latch Screen - iOS | COMPLETED | Lithin | 4 | 4 | 2020-07-22 | 2020-07-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
39 | Release Latch Screen - Android | COMPLETED | Tinu | 4 | 4 | 2020-07-22 | 2020-07-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
40 | Unlocking Screen - iOS | COMPLETED | Lithin | 8 | 8 | 2020-09-02 | 2020-09-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
41 | Unlocking Screen - Android | COMPLETED | Tinu | 8 | 8 | 2020-08-11 | 2020-08-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
42 | Summary Screen (Test Screen) - iOS | COMPLETED | Lithin | 4 | 4 | 2020-08-07 | 2020-08-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
43 | Summary Screen (Test Screen) - Android | COMPLETED | Tinu | 4 | 4 | 2020-08-12 | 2020-08-12 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
44 | Location Search - iOS | COMPLETED | Lithin | 16 | 16 | 2020-09-03 | 2020-09-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
45 | Location Search - Android | COMPLETED | Tinu | 16 | 16 | 2020-08-12 | 2020-09-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20%
46 | Testing & Bug Fixing | COMPLETED | Lithin | 20 | 24 | 2020-09-09 | 2020-09-11 | 100% | 100% | 100% | 100% | 100% | 60% | 30%
47 | Testing & Bug Fixing | COMPLETED | Tinu | 20 | 24 | 2020-09-09 | 2020-09-11 | 100% | 100% | 100% | 100% | 100% | 60% | 30%
Cloud - Maintenance
47 | Maintenance Company - Create maintenance companies and List & search maintenance companies | COMPLETED | Dileep | 8 | 9 | 2020-06-22 | 2020-06-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
48 | Maintenance Person - Create maintenance persons and List & search maintenance persons | COMPLETED | Dileep | 8 | 9 | 2020-06-24 | 2020-06-24 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
49 | Assign Devices to maintenance persons | COMPLETED | Dileep | 8 | 9 | 2020-06-25 | 2020-06-25 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
50 | Assign Tasks to maintenance persons | COMPLETED | Dileep | 8 | 9 | 2020-06-26 | 2020-06-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
51 | Maintenance task entry | COMPLETED | Dileep | 16 | 18 | 2020-06-27 | 2020-06-29 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
52 | Testing & Bug Fixing | COMPLETED | Dileep | 8 | 8 | 2020-07-07 | 2020-07-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cloud - Dashboard
53 | Design Prototype - Charts | COMPLETED | Dileep | 8 | 15 | 2020-07-06 | 2020-07-13 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 90% | 80% | 70% | 70% | 70%
54 | Device Status & Summary | COMPLETED | Dileep | 8 | 8 | 2020-07-22 | 2020-07-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
55 | Usage & Statistics Drilldown Report | COMPLETED | Dileep | 16 | 20 | 2020-07-23 | 2020-07-25 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 30%
56 | Operational Log Report | COMPLETED | Dileep | 8 | 8 | 2020-07-08 | 2020-07-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
57 | Revenue by Location - Show Graph | COMPLETED | Dileep | 8 | 16 | 2020-07-27 | 2020-07-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
58 | Occupancy Rate by Location - Show Graph | COMPLETED | Dileep | 8 | 8 | 2020-07-28 | 2020-07-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
59 | Testing & Bug Fixing | COMPLETED | Dileep | 16 | 18 | 2020-07-29 | 2020-08-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30%
Cloud - Maintenance App APIs
60 | Required APIs for Maintenance Mobile App | COMPLETED | Dileep | 40 | 42 | 2020-06-23 | 2020-09-11 | 100% | 100% | 100% | 100% | 100% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 70% | 70% | 60% | 60% | 60% | 60% | 60% | 60% | 50% | 40% | 30% | 20% | 20% | 20% | 20% | 20% | 20%
61 | Testing & Bug Fixing | PLANNED | Dileep | 16 | 24 | 2020-07-20 | 2020-07-21 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
Total Man Hours |  |  |  | 576 | 622
Date of Completion | [7 empty] | 2020-07-22
Date of Completion (After Rescedule) | [7 empty] | 2020-07-31
Dashboard - Charts
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09 | 2020-09-08 | 2020-09-07 | 2020-09-05 | 2020-09-04 | 2020-09-03 | 2020-09-02 | 2020-08-28 | 2020-08-27 | 2020-08-26 | 2020-08-25 | 2020-08-24 | 2020-08-22 | 2020-08-21 | 2020-08-20 | 2020-08-19 | 2020-08-18 | 2020-08-17 | 2020-08-14 | 2020-08-13 | 2020-08-12 | 2020-08-11 | 2020-08-10 | 2020-08-08 | 2020-08-07 | 2020-08-06 | 2020-08-05 | 2020-08-04 | 2020-08-02 | 2020-08-03 | 2020-07-31 | 2020-07-30 | 2020-07-29 | 2020-07-28 | 2020-07-27 | 2020-07-25 | 2020-07-24 | 2020-07-23 | 2020-07-22 | 2020-07-21 | 2020-07-20 | 2020-07-17 | 2020-07-16 | 2020-07-15 | 2020-07-14 | 2020-07-13 | 2020-07-11 | 2020-07-10 | 2020-07-09 | 2020-07-08 | 2020-07-07 | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16
1 | LineChart - Dashboard | COMPLETED | Dileep | 16 | 21 | 2020-09-07 | 2020-09-09 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 30%
2 | BarChart - Dashboard | COMPLETED | Dileep | 16 | 21 | 2020-09-10 | 2020-09-12 | 100% | 100% | 100% | 100% | 70% | 30%
3 | PieChart - Dashboard | PROGRESS | Dileep | 16
4 | Testing & Bug fixing | PROGRESS | Dileep | 8 | 9 | 2020-09-14 | 2020-09-16 | 80% | 60% | 30%
Total Man Hours |  |  |  | 56 | 51

## Demo Modifications
Demo Modifications
LAST UPDATED ON: 19-October-2020
LAST UPDATED BY: Suresh S
Demo on 23-06-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09 | 2020-09-08 | 2020-09-07 | 2020-09-05 | 2020-09-04 | 2020-09-03 | 2020-09-02 | 2020-08-28 | 2020-08-27 | 2020-08-26 | 2020-08-25 | 2020-08-24 | 2020-08-22 | 2020-08-21 | 2020-08-20 | 2020-08-19 | 2020-08-18 | 2020-08-17 | 2020-08-14 | 2020-08-13 | 2020-08-12 | 2020-08-11 | 2020-08-10 | 2020-08-08 | 2020-08-07 | 2020-08-06 | 2020-08-05 | 2020-08-04 | 2020-08-02 | 2020-08-03 | 2020-07-31 | 2020-07-30 | 2020-07-29 | 2020-07-28 | 2020-07-27 | 2020-07-25 | 2020-07-24 | 2020-07-23 | 2020-07-22 | 2020-07-21 | 2020-07-20 | 2020-07-17 | 2020-07-16 | 2020-07-15 | 2020-07-14 | 2020-07-13 | 2020-07-11 | 2020-07-10 | 2020-07-09 | 2020-07-08 | 2020-07-07 | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16
1 | Japanese caption settings - Cloud | COMPLETED | Dileep | 8 | 9 | 2020-06-16 | 2020-06-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Design & Documentation & Communication | COMPLETED | Suresh | 8 | 20 | 2020-06-16 | 2020-06-30 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 80% | 80% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 50%
3 | Design & Documentation | COMPLETED | Lithin | 8 | 7 | 2020-06-16 | 2020-06-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Design & Documentation | COMPLETED | Dileep | 8 | 8 | 2020-06-17 | 2020-06-17 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | User Manual Documentation - Web Application | COMPLETED | Dileep | 8 | 9 | 2020-06-18 | 2020-06-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Website performance improvement | COMPLETED | Dileep | 8 | 8 | 2020-06-19 | 2020-06-19 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Modifications from the client after demo | COMPLETED | Lithin | 24 | 42 | 2020-06-17 | 2020-06-26 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 90% | 80% | 75% | 60% | 45% | 30% | 15%
8 | Modifications from the client after demo | COMPLETED | Tinu | 24 | 8 | 2020-06-17 | 2020-06-30 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 15%
9 | Testing & Bug Fixing - Multiple Devices - iOS | COMPLETED | Lithin | 16 | 24 | 2020-06-27 | 2020-06-30 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 35%
10 | Testing & Bug Fixing - Multiple Devices - Android | COMPLETED | Tinu | 16 | 19 | 2020-06-26 | 2020-07-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 80% | 80% | 40%
11 | Testing & Bug Fixing - Multiple Devices - Cloud | COMPLETED | Dileep | 8
Total Man Hours |  |  |  | 136 | 154
Demo on 30-06-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09 | 2020-09-08 | 2020-09-07 | 2020-09-05 | 2020-09-04 | 2020-09-03 | 2020-09-02 | 2020-08-28 | 2020-08-27 | 2020-08-26 | 2020-08-25 | 2020-08-24 | 2020-08-22 | 2020-08-21 | 2020-08-20 | 2020-08-19 | 2020-08-18 | 2020-08-17 | 2020-08-14 | 2020-08-13 | 2020-08-12 | 2020-08-11 | 2020-08-10 | 2020-08-08 | 2020-08-07 | 2020-08-06 | 2020-08-05 | 2020-08-04 | 2020-08-02 | 2020-08-03 | 2020-07-31 | 2020-07-30 | 2020-07-29 | 2020-07-28 | 2020-07-27 | 2020-07-25 | 2020-07-24 | 2020-07-23 | 2020-07-22 | 2020-07-21 | 2020-07-20 | 2020-07-17 | 2020-07-16 | 2020-07-15 | 2020-07-14 | 2020-07-13 | 2020-07-11 | 2020-07-10 | 2020-07-09 | 2020-07-08 | 2020-07-07 | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01
1 | Check battery power on QR code scanning (iOS) | COMPLETED | Lithin | 16 | 16 | 2020-07-08 | 2020-07-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 30%
2 | Check battery power on QR code scanning (Android) | COMPLETED | Tinu | 16 | 18 | 2020-07-08 | 2020-07-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 30%
3 | Not discover BLT device - show alert - redirect - error reporting (iOS) | COMPLETED | Lithin | 4 | 4 | 2020-07-08 | 2020-07-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Not discover BLT device - show alert - redirect - error reporting (Android) | COMPLETED | Tinu | 4 | 4 | 2020-07-01 | 2020-07-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | Check the status of locker handle is down and display instruction to use (iOS) | COMPLETED | Lithin | 4 | 4 | 2020-07-01 | 2020-07-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Check the status of locker handle is down and display instruction to use (Android) | COMPLETED | Tinu | 4 | 4 | 2020-07-01 | 2020-07-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Unlock time- Check the handle doesn't return back (iOS) | COMPLETED | Lithin | 4 | 4 | 2020-07-01 | 2020-07-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Unlock time- Check the handle doesn't return back (Android) | COMPLETED | Tinu | 4 | 4 | 2020-07-08 | 2020-07-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | QR Code Screen changes (iOS) | COMPLETED | Lithin | 4 | 4 | 2020-07-02 | 2020-07-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | QR Code Screen changes (Android) | COMPLETED | Tinu | 12 | 9 | 2020-07-03 | 2020-07-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Map screen - Device oder change based on the selection (iOS) | COMPLETED | Lithin | 8 | 6 | 2020-07-02 | 2020-07-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | Map screen - Device oder change based on the selection (Android) | COMPLETED | Tinu | 8 | 5 | 2020-07-02 | 2020-07-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Bottom navigation - tap on in use button to load checkin - check out screen on its child class (iOS) | COMPLETED | Lithin | 8 | 8 | 2020-07-03 | 2020-07-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Testing & Bug Fixing (iOS) | COMPLETED | Lithin | 8 | 12 | 2020-07-10 | 2020-07-09 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
16 | Testing & Bug Fixing (Android) | COMPLETED | Tinu | 8 | 17 | 2020-07-10 | 2020-07-09 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
Total Man Hours |  |  |  | 112 | 119
Date of Completion | [7 empty] | 2020-07-10
Demo on 14-07-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09 | 2020-09-08 | 2020-09-07 | 2020-09-05 | 2020-09-04 | 2020-09-03 | 2020-09-02 | 2020-08-28 | 2020-08-27 | 2020-08-26 | 2020-08-25 | 2020-08-24 | 2020-08-22 | 2020-08-21 | 2020-08-20 | 2020-08-19 | 2020-08-18 | 2020-08-17 | 2020-08-14 | 2020-08-13 | 2020-08-12 | 2020-08-11 | 2020-08-10 | 2020-08-08 | 2020-08-07 | 2020-08-06 | 2020-08-05 | 2020-08-04 | 2020-08-02 | 2020-08-03 | 2020-07-31 | 2020-07-30 | 2020-07-29 | 2020-07-28 | 2020-07-27 | 2020-07-25 | 2020-07-24 | 2020-07-23 | 2020-07-22 | 2020-07-21 | 2020-07-20 | 2020-07-17
1 | iOS 1. Time out error after 3 minutes 2. Enable "Home" button in payment screen 3. Login screen keypad auto display - removed 4. Video files added 5. Customer Care added in "More" menu | COMPLETED | Lithin | 16 | 16 | 2020-07-17 | 2020-07-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | Android 1. Time out error after 3 minutes 2. Enable "Home" button in payment screen 3. Login screen keypad auto display - removed 4. Video files added 5. Customer Care added in "More" menu | COMPLETED | Tinu | 16 | 16 | 2020-07-17 | 2020-07-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
3 | Cloud 1. Time out error after 3 minutes 2. Enable "Home" button in payment screen 3. Login screen keypad auto display - removed 4. Video files added 5. Customer Care added in "More" menu | COMPLETED | Dileep | 8 | 8 | 2020-07-17 | 2020-07-17 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Total Man Hours |  |  |  | 40 | 40
Date of Completion | [7 empty] | 2020-07-18
Demo on 21-07-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09 | 2020-09-08 | 2020-09-07 | 2020-09-05 | 2020-09-04 | 2020-09-03 | 2020-09-02 | 2020-08-28 | 2020-08-27 | 2020-08-26 | 2020-08-25 | 2020-08-24 | 2020-08-22 | 2020-08-21 | 2020-08-20 | 2020-08-19 | 2020-08-18 | 2020-08-17 | 2020-08-14 | 2020-08-13 | 2020-08-12 | 2020-08-11 | 2020-08-10 | 2020-08-08 | 2020-08-07 | 2020-08-06 | 2020-08-05 | 2020-08-04 | 2020-08-02 | 2020-08-03 | 2020-07-31 | 2020-07-30
1 | Screen caption changes - iOS | COMPLETED | Lithin | 8 | 8 | 2020-08-03 | 2020-08-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Screen caption changes - Android | COMPLETED | Tinu | 8 | 8 | 2020-08-03 | 2020-08-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Change Email Address - iOS | COMPLETED | Lithin | 8 | 8 | 2020-08-07 | 2020-08-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Change Email Address - Android | COMPLETED | Tinu | 8 | 8 | 2020-08-08 | 2020-08-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | Change Email Address - Cloud | COMPLETED | Dileep | 4 | 4 | 2020-08-04 | 2020-08-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | De registration / Delete Account - iOS | COMPLETED | Lithin | 4 | 4 | 2020-08-07 | 2020-08-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | De registration / Delete Account - Android | COMPLETED | Tinu | 4 | 4 | 2020-08-08 | 2020-08-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | De registration / Delete Account - Cloud | COMPLETED | Dileep | 4 | 4 | 2020-08-04 | 2020-08-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Condition User scan the QR Code, Done the payment, Did not press the lock button. Action Start the alarm after 5 seconds after showing the alert "Please press the Lock button", Sound alert for 3 minutes, After 3 minutes send mail and return to home screen FOR iOS | COMPLETED | Lithin | 4 | 4 | 2020-08-04 | 2020-08-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Condition User scan the QR Code, Done the payment, Did not press the lock button. Action Start the alarm after 5 seconds after showing the alert "Please press the Lock button", Sound alert for 3 minutes, After 3 minutes send mail and return to home screen FOR Android | COMPLETED | Tinu | 4 | 4 | 2020-08-04 | 2020-08-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Condition User scan the QR Code, Done the payment,Did not press the lock button. Action Start the alarm after 5 seconds after showing the alert "Please press the Lock button", Sound alert for 3 minutes, After 3 minutes send mail and return to home screen FOR Cloud | COMPLETED | Dileep | 4 | 4 | 2020-08-05 | 2020-08-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | Condition User scan the QR Code, Done the payment, Press the lock button, Did not lower the handle. Action After 3 minutes send mail and return to home screen FOR Cloud | COMPLETED | Dileep | 8 | 9 | 2020-08-05 | 2020-08-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Condition 1. User scan the QR Code 2. Done the payment 3. Press the lock button. 4. Did not lower the handle. 5. User leave the app. 6. Return and Re-Scan QR Code Action 1. Skip the payment screen. 2. Skip the lock button screen. 3. Redirect to alert "Please down the handle". 4. Repeat the time out process till reaches 2 hours without lowering the handle. FOR iOS | COMPLETED | Lithin | 8 | 8 | 2020-08-04 | 2020-08-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Condition User scan the QR Code, Done the payment, Press the lock button, Did not lower the handle, User leave the app, Return and Re-Scan QR Code Action Skip the payment screen, Skip the lock button screen, Redirect to alert "Please down the handle", Repeat the time out process till reaches 2 hours without lowering the handle. FOR Android | COMPLETED | Tinu | 8 | 8 | 2020-08-04 | 2020-08-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Condition User scan the QR Code, Done the payment, Press the lock button, Did not lower the handle, User leave the app, Another user Scan after 2 hours. Action After 2 hours another user scan the QR code, He should be able to use the same device. FOR iOS | COMPLETED | Lithin | 16 | 16 | 2020-08-05 | 2020-08-12 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 70% | 70% | 70% | 70% | 70%
16 | Condition User scan the QR Code, Done the payment, Press the lock button, Did not lower the handle, User leave the app, Another user Scan after 2 hours. Action After 2 hours another user scan the QR code, He should be able to use the same device. FOR Android | COMPLETED | Tinu | 16 | 16 | 2020-08-05 | 2020-08-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 70% | 70% | 70%
17 | Condition User scan the QR Code, Done the payment, Press the lock button, Did not lower the handle, User leave the app, Another user Scan after 2 hours. Action After 2 hours another user scan the QR code, He should be able to use the same device. FOR Cloud | COMPLETED | Dileep | 8 | 8 | 2020-08-07 | 2020-08-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | Add new status "Good / Bad" for the lock devices 1. If the device is good to use - Status will be "Good" 2. If the device is not good to use - Status will be "Bad" 3. Display the status in the Device list 4. When the admin clicks the "BAD" status display the detail about the error. 5. When the problem is solved change the status to "Good". FOR iOS | COMPLETED | Lithin | 8 | 8 | 2020-08-11 | 2020-08-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
19 | Add new status "Good / Bad" for the lock devices 1. If the device is good to use - Status will be "Good" 2. If the device is not good to use - Status will be "Bad" 3. Display the status in the Device list 4. When the admin clicks the "BAD" status display the detail about the error. 5. When the problem is solved change the status to "Good". FOR Android | COMPLETED | Tinu | 8 | 8 | 2020-08-10 | 2020-08-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | Add new status "Good / Bad" for the lock devices 1. If the device is good to use - Status will be "Good" 2. If the device is not good to use - Status will be "Bad" 3. Display the status in the Device list 4. When the admin clicks the "BAD" status display the detail about the error. 5. When the problem is solved change the status to "Good". FOR Cloud | COMPLETED | Dileep | 8 | 8 | 2020-08-08 | 2020-08-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
21 | Payment gateway implementation - without redirect URL - iOS | COMPLETED | Lithin | 24 | 24 | 2020-07-30 | 2020-08-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 30%
22 | Payment gateway implementation - without redirect URL - Android | COMPLETED | Tinu | 24 | 24 | 2020-07-30 | 2020-08-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 30%
23 | Payment gateway implementation - without redirect URL - Cloud | COMPLETED | Dileep | 24 | 24 | 2020-07-30 | 2020-08-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 60% | 30%
24 | Help Q&A - redirection to the URL - iOS | COMPLETED | Lithin | 4 | 4 | 2020-08-06 | 2020-08-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Help Q&A - redirection to the URL - Android | COMPLETED | Tinu | 4 | 4 | 2020-08-08 | 2020-08-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
26 | Help Email - Send preset email content to support mail ID - iOS | COMPLETED | Lithin | 4 | 4 | 2020-08-06 | 2020-08-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
27 | Help Email - Send preset email content to support mail ID - Android | COMPLETED | Tinu | 4 | 4 | 2020-08-07 | 2020-08-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
28 | Help Email - Send preset email content to support mail ID - Cloud | COMPLETED | Dileep | 4 | 4 | 2020-08-10 | 2020-08-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
29 | Maintenance App device history - iOS | COMPLETED | Lithin | 16 | 20 | 2020-09-09 | 2020-09-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 40%
30 | Maintenance App device history - Android | COMPLETED | Tinu | 16 | 16 | 2020-09-09 | 2020-09-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 40%
31 | Maintenance App device history - Cloud | COMPLETED | Dileep | 16 | 8 | 2020-09-09 | 2020-09-09 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
32 | Testing & Bug Fixing - iOS | COMPLETED | Lithin | 16 | 18 | 2020-08-08 | 2020-09-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 20% | 10% | 10% | 10%
33 | Testing & Bug Fixing - Android | COMPLETED | Tinu | 16 | 24 | 2020-08-06 | 2020-09-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 30% | 30% | 10% | 10% | 10%
34 | Testing & Bug Fixing - Cloud | COMPLETED | Dileep | 16 | 16 | 2020-08-11 | 2020-09-11 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 40% | 20%
Total Man Hours |  |  |  | 336 | 343
Date of Completion | [7 empty] | 2020-08-12
Demo on 11-08-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09 | 2020-09-08 | 2020-09-07 | 2020-09-05 | 2020-09-04 | 2020-09-03 | 2020-09-02 | 2020-08-28 | 2020-08-27 | 2020-08-26 | 2020-08-25 | 2020-08-24 | 2020-08-22 | 2020-08-21 | 2020-08-20 | 2020-08-19 | 2020-08-18 | 2020-08-17 | 2020-08-14
1 | Device not Discover issue - iOS | COMPLETED | Lithin | 24 | 27 | 2020-08-14 | 2020-08-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 30%
2 | Device not Discover issue - Android | COMPLETED | Tinu | 24 | 30 | 2020-08-14 | 2020-08-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 30%
3 | Japanese Caption - Changes - iOS | COMPLETED | Lithin | 8 | 8 | 2020-08-18 | 2020-08-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Japanese Caption - Changes - Android | COMPLETED | Tinu | 8 | 8 | 2020-08-18 | 2020-08-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | Japanese Caption - Changes - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-08-18 | 2020-08-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Lever Status checking modifications - iOS | COMPLETED | Lithin | 16 | 16 | 2020-08-21 | 2020-08-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
7 | Lever Status checking modifications - Android | COMPLETED | Tinu | 16 | 16 | 2020-08-21 | 2020-08-22 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
8 | Lever Status checking modifications - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-08-21 | 2020-08-21 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Testing the New flow & Bug fixing - iOS | COMPLETED | Lithin | 16 | 18 | 2020-08-22 | 2020-08-24 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
10 | Testing the New flow & Bug fixing - Android | COMPLETED | Tinu | 16 | 20 | 2020-08-22 | 2020-08-24 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
Total Man Hours |  |  |  | 144 | 159
Date of Completion | [7 empty] | 2020-08-24
Demo on 25-08-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09 | 2020-09-08 | 2020-09-07 | 2020-09-05 | 2020-09-04 | 2020-09-03 | 2020-09-02 | 2020-08-28 | 2020-08-27 | 2020-08-26 | 2020-08-25
1 | App Error Log Implemenation - iOS | COMPLETED | Lithin | 16 | 16 | 2020-08-25 | 2020-08-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 80% | 40%
2 | App Error Log Implemenation - Android | COMPLETED | Tinu | 16 | 16 | 2020-08-25 | 2020-08-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 80% | 40%
3 | API for Error Log Implemenation - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-08-25 | 2020-08-25 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | QR Code Design Changes - iOS | COMPLETED | Lithin | 8 | 10 | 2020-09-02 | 2020-09-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
5 | QR Code Design Changes - Android | COMPLETED | Tinu | 8 | 8 | 2020-09-02 | 2020-09-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
Total Man Hours |  |  |  | 56 | 58
Date of Completion | [7 empty] | 2020-09-04
Demo on 08-09-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15 | 2020-09-14 | 2020-09-12 | 2020-09-11 | 2020-09-10 | 2020-09-09
1 | Firmware Testing - iOS (CP & Maintenance) | COMPLETED | Lithin | 24 | 24 | 2020-09-09 | 2020-09-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 40% | 20%
2 | Firmware Testing - Android (CP & Maintenance) | COMPLETED | Tinu | 24 | 24 | 2020-09-09 | 2020-09-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 40% | 20%
3 | Firmware Testing - Cloud (CP & Maintenance) | COMPLETED | Dileep | 8 | 8 | 2020-09-09 | 2020-09-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 40% | 20%
4 | Japanese Caption - Changes - iOS | COMPLETED | Lithin | 8 | 8 | 2020-09-09 | 2020-09-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 40% | 20%
5 | Japanese Caption - Changes - Android | COMPLETED | Tinu | 8 | 8 | 2020-09-09 | 2020-09-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 40% | 20%
6 | Japanese Caption - Changes - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-09-09 | 2020-09-14 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 60% | 40% | 20%
Total Man Hours |  |  |  | 80 | 80
Date of Completion | [7 empty] | 2020-09-14
Demo on 15-09-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15
1 | Redirect QR Code screen - After time out - iOS | COMPLETED | Lithin | 8 | 8 | 2020-09-15 | 2020-09-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | Redirect QR Code screen - After time out - Android | COMPLETED | Tinu | 8 | 8 | 2020-09-15 | 2020-09-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
3 | Japanese Caption - Changes - iOS | COMPLETED | Lithin | 8 | 8 | 2020-09-15 | 2020-09-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 40% | 20%
4 | Japanese Caption - Changes - Android | COMPLETED | Tinu | 8 | 8 | 2020-09-15 | 2020-09-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 40% | 20%
5 | Japanese Caption - Changes - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-09-15 | 2020-09-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 40% | 20%
6 | Firmware Testing & Bug fixing - iOS | COMPLETED | Lithin | 8 | 9 | 2020-09-17 | 2020-09-21 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 40%
7 | Firmware Testing & Bug fixing - Android | COMPLETED | Tinu | 8 | 9 | 2020-09-17 | 2020-09-21 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 40%
8 | Firmware Testing & Bug fixing - Cloud | COMPLETED | Dileep | 8 | 6 | 2020-09-17 | 2020-09-18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
Total Man Hours |  |  |  | 64 | 64
Date of Completion | [7 empty] | 2020-09-22
iOS & Android - Payment Integration
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22 | 2020-09-21 | 2020-09-18 | 2020-09-17 | 2020-09-16 | 2020-09-15
1 | Payment Integration - iOS | PLANNED | Lithin | 24 | 24 | 2020-09-21 | 2020-09-23 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 30% | 100% | 100% | 100% | 100%
2 | Payment Integration - Android | PLANNED | Tinu | 24 | 18 | 2020-09-15 | 2020-09-23 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 70% | 50% | 30% | 30% | 30% | 30%
3 | Payment Integration - Cloud | PLANNED | Dileep | 24 | 16 | 2020-09-22 | 2020-09-23 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 20%
4 | Google Map Integration - Cloud | PLANNED | Dileep | 16 | 12 | 2020-09-30 | 2020-10-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 40%
Total Man Hours |  |  |  | 88 | 70
Demo on 22-09-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30 | 2020-09-29 | 2020-09-28 | 2020-09-26 | 2020-09-25 | 2020-09-24 | 2020-09-23 | 2020-09-22
1 | Firmware Testing & Bug fixing - iOS | COMPLETED | Lithin | 16 | 16 | 2020-09-24 | 2020-09-25 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | Firmware Testing & Bug fixing - Android | COMPLETED | Tinu | 16 | 16 | 2020-09-24 | 2020-09-25 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
3 | Modifications in Chart - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-09-22 | 2020-09-23 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
4 | Firmware Testing & Bug fixing - Cloud | COMPLETED | Dileep | 12 | 12 | 2020-09-25 | 2020-09-28 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 30%
Total Man Hours |  |  |  | 52 | 52
Date of Completion | [7 empty] | 2020-09-29
Demo on 30-09-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07 | 2020-10-06 | 2020-10-05 | 2020-10-01 | 2020-09-30
1 | Payment Integration modifications - iOS | COMPLETED | Lithin | 12 | 12 | 2020-09-30 | 2020-10-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
2 | Payment Integration modifications - Android | COMPLETED | Tinu | 12 | 12 | 2020-09-30 | 2020-10-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
3 | Payment Integration modifications - Cloud | COMPLETED | Dileep | 4 | 4 | 2020-09-30 | 2020-10-01 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Change Phone Number - iOS | COMPLETED | Lithin | 8 | 8 | 2020-10-05 | 2020-10-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | Change Phone Number - Android | COMPLETED | Tinu | 8 | 8 | 2020-10-05 | 2020-10-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Change Phone Number - Cloud | COMPLETED | Dileep | 4 | 4 | 2020-10-05 | 2020-10-05 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Mail functionality during operations - iOS | COMPLETED | Lithin | 4 | 4 | 2020-10-06 | 2020-10-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
8 | Mail functionality during operations - Android | COMPLETED | Tinu | 4 | 4 | 2020-10-06 | 2020-10-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
9 | Mail content changes during operations - iCloud | COMPLETED | Dileep | 4 | 4 | 2020-10-06 | 2020-10-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Total Man Hours |  |  |  | 60 | 60
Date of Completion | [7 empty] | 2020-10-06
Demo on 06-10-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13 | 2020-10-12 | 2020-10-10 | 2020-10-09 | 2020-10-08 | 2020-10-07
1 | Apple Pay Integration - Testing | COMPLETED | Lithin | 8 | 8 | 2020-10-07 | 2020-10-07 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Firmware Testing & Bug fixing - iOS | COMPLETED | Lithin | 8 | 8 | 2020-10-08 | 2020-10-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Firmware Testing & Bug fixing - Android | COMPLETED | Lithin | 8 | 8 | 2020-10-08 | 2020-10-08 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Maintenance App - Changes in work report - iOS | COMPLETED | Lithin | 16 | 16 | 2020-10-09 | 2020-10-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
5 | Maintenance App - Changes in work report - Android | COMPLETED | Tinu | 16 | 16 | 2020-10-09 | 2020-10-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
6 | Maintenance App - Change in work report - Cloud | COMPLETED | Dileep | 8 | 10 | 2020-10-09 | 2020-10-10 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
7 | Area & Landmark in Location - Cloud | COMPLETED | Dileep | 16 | 16 | 2020-10-07 | 2020-10-12 | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 60% | 60% | 30%
Total Man Hours |  |  |  | 80 | 82
Date of Completion | [7 empty] | 2020-10-13
Demo on 13-10-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-19 | 2020-10-16 | 2020-10-15 | 2020-10-14 | 2020-10-13
1 | Apple Store Upload | COMPLETED | Lithin | 24 | 25 | 2020-10-13 | 2020-10-16 | 100% | 100% | 80% | 60% | 40%
2 | Firmware Testing & Bug fixing - iOS | COMPLETED | Lithin | 12 | 14 | 2020-10-13 | 2020-10-19 | 100% | 80% | 80% | 60% | 40%
3 | Firmware Testing & Bug fixing - Android | COMPLETED | Tinu | 4 | 4 | 2020-10-13 | 2020-10-19 | 100% | 80% | 80% | 80% | 80%
4 | Firmware Testing & Bug fixing - Cloud | COMPLETED | Dileep | 4 | 4 | 2020-10-13 | 2020-10-19 | 100% | 80% | 80% | 80% | 80%
5 | Contract Users Operational Changes - Cloud | COMPLETED | Dileep | 4 | 4 | 2020-10-15 | 2020-10-16 | 100% | 100% | 50%
6 | Dashboard filters & changes - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-10-15 | 2020-10-19 | 100% | 80% | 50%
Total Man Hours |  |  |  | 56 | 59
Date of Completion | [7 empty] | 2020-10-20

## Cube
Cube Application
LAST UPDATED ON: 13-November-2020
LAST UPDATED BY: Suresh S
Cloud - Cube Application
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-11-13 | 2020-11-12 | 2020-11-11 | 2020-11-10 | 2020-11-09 | 2020-11-06 | 2020-11-05 | 2020-11-04 | 2020-11-03 | 2020-11-02 | 2020-10-30 | 2020-10-29 | 2020-10-27 | 2020-10-12 | 2020-09-06 | 2020-09-05 | 2020-09-04 | 2020-09-02 | 2020-08-28 | 2020-08-27
1 | Cube Registration - Cloud | COMPLETED | Dileep | 16 | 8 | 2020-08-27 | 2020-08-27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Cube Login & Logout - API | COMPLETED | Dileep | 16 | 16 | 2020-09-05 | 2020-09-06 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
3 | Error Logging - API | COMPLETED | Dileep | 8 | 8 | 2020-10-12 | 2020-10-12 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Locking & Unlocking - API | COMPLETED | Dileep | 16 | 18 | 2020-08-28 | 2020-09-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
5 | Compose Hash - API | COMPLETED | Dileep | 8 | 8 | 2020-09-04 | 2020-09-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Cube Power On - API | COMPLETED | Dileep | 8 | 8 | 2020-10-29 | 2020-10-30 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50%
7 | Log Status - API | COMPLETED | Dileep | 8 | 8 | 2020-11-02 | 2020-11-02 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Log Photo - API | COMPLETED | Dileep | 8 | 8 | 2020-11-03 | 2020-11-03 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Action Query - API | COMPLETED | Dileep | 8 | 8 | 2020-11-04 | 2020-11-04 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Cube Login Module - Cloud | COMPLETED | Dileep | 16 | 16 | 2020-11-05 | 2020-11-06 | 100% | 100% | 100% | 100% | 100% | 100% | 50%
11 | Device Listing Page - Cloud | COMPLETED | Dileep | 8 | 4 | 2020-10-27 | 2020-10-27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | Error Log Listing Page - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-11-09 | 2020-11-09 | 100% | 100% | 100% | 100% | 100%
13 | Photos Display Page - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-11-10 | 2020-11-10 | 100% | 100% | 100% | 100%
14 | Maintenance Dashboard - Cloud | COMPLETED | Dileep | 24 | 18 | 2020-11-11 | 2020-11-12 | 100% | 100% | 50%
15 | Testing & Bug fixing | COMPLETED | Dileep | 16 | 8 | 2020-11-13 | 2020-11-13 | 100%
Total Man Hours |  |  |  | 176 | 152
Date of Completion | [7 empty] | 2020-11-12

## In Progress
CP - Additional Requirements
LAST UPDATED ON: 25-November-2020
LAST UPDATED BY: Suresh S
CP - Cloud
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-10-23 | 2020-10-22 | 2020-10-21 | 2020-10-20 | 2020-10-19
1 | Battery Module Management | COMPLETED | Dileep | 8 | 8 | 2020-10-20 | 2020-10-20 | 100% | 100% | 100% | 100%
2 | Bar Chart - Battery module | COMPLETED | Dileep | 8 | 4 | 2020-10-21 | 2020-10-21 | 100% | 100% | 100%
3 | Line Chart - Battery module | COMPLETED | Dileep | 8 | 4 | 2020-10-21 | 2020-10-21 | 100% | 100% | 100%
4 | Pie Charts | COMPLETED | Dileep | 16 | 16 | 2020-10-22 | 2020-10-23 | 100% | 50%
5 | Payment Management - Maintenance | PENDING | Dileep | 4 | 4 | 2020-10-23 | 2020-10-23 | 100%
Total Man Hours |  |  |  | 44 | 36
Date of Completion | [7 empty] | 2020-10-23
Demo on 10-11-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-11-24 | 2020-11-23 | 2020-11-20 | 2020-11-19 | 2020-11-18 | 2020-11-17 | 2020-11-16 | 2020-11-13 | 2020-11-12
1 | Video Instruction screen - Remove the video player & adding swipeable image collection - iOS | COMPLETED | Lithin | 16 | 16 | 2020-11-12 | 2020-11-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 50%
2 | Video Instruction screen - Remove the video player & adding swipeable image collection - Android | COMPLETED | Tinu | 16 | 16 | 2020-11-12 | 2020-11-16 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 50%
3 | Video Instruction screen - Remove the video player & adding swipeable image collection - Cloud | COMPLETED | Dileep | 8 | 8 | 2020-11-13 | 2020-11-13 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Hash key split - changes in the functional flow - iOS | COMPLETED | Lithin | 24 | 24 | 2020-11-17 | 2020-11-20 | 100% | 100% | 100% | 90% | 60% | 30%
5 | Hash key split - changes in the functional flow - Android | COMPLETED | Tinu | 24 | 24 | 2020-11-17 | 2020-11-20 | 100% | 100% | 100% | 90% | 60% | 30%
6 | Maintenance Task Page a) Adding Area, Location, Landmark filter b) Adding boxes to show the device count c) Changing and adding additional columns in list | COMPLETED | Dileep | 16 | 16 | 2020-11-16 | 2020-11-17 | 100% | 100% | 100% | 100% | 100% | 100% | 50%
7 | Error Log Page a) Adding Area, Location, Landmark filter b) Adding boxes to various count c) Bar Charts to show various error count | COMPLETED | Dileep | 16 | 16 | 2020-11-18 | 2020-11-19 | 100% | 100% | 100% | 100% | 50%
8 | App User Page a) Adding boxes to device count b) Changing and adding additional columns in list | COMPLETED | Dileep | 8 | 8 | 2020-11-20 | 2020-11-20 | 100% | 100% | 100%
9 | Testing & Confirmation | COMPLETED | Team | 16 | 16 | 2020-11-16 | 2020-11-20 | 100% | 50%
Total Man Hours |  |  |  | 144 | 144
Date of Completion | [7 empty] | 2020-11-20
Demo on 17-11-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-11-28 | 2020-11-27 | 2020-11-26 | 2020-11-25 | 2020-11-24 | 2020-11-23
1 | Invoice Generation for users - iOS | COMPLETED | Lithin | 16 | 16 | 2020-11-25 | 2020-11-28 | 100% | 80% | 40% | 20% | 20% | 20%
2 | Invoice Generation for users - Android | COMPLETED | Tinu | 16 | 16 | 2020-11-25 | 2020-11-28 | 100% | 80% | 40% | 20% | 20% | 20%
3 | Invoice Generation for users - Cloud | COMPLETED | Dileep | 4 | 4 | 2020-11-23 | 2020-11-23 | 100% | 100% | 100% | 100% | 100% | 100%
4 | Device Listing Page for Maintenance user Login | COMPLETED | Dileep | 8 | 8 | 2020-11-23 | 2020-11-23 | 100% | 100% | 100% | 100% | 100% | 100%
5 | Search feature in Google map in Location Page | COMPLETED | Dileep | 8 | 8 | 2020-11-24 | 2020-11-24 | 100% | 100% | 100% | 100% | 100%
6 | SMTP(carrypark.com domain) Setup Display password of maintenance user in view page | COMPLETED | Dileep | 8 | 8 | 2020-11-25 | 2020-11-25 | 100% | 100% | 100% | 100%
7 | Display total number boxes in Chart pages | COMPLETED | Dileep | 16 | 16 | 2020-11-26 | 2020-11-27 | 100% | 100% | 50%
8 | Email notification for email address change and when the maximum usage time reach | COMPLETED | Dileep | 8 | 8 | 2020-11-28 | 2020-11-28 | 100%
9 | Testing & Support | COMPLETED | Team | 16 | 20 | 2020-11-23 | 2020-11-28 | 100% | 80% | 60% | 50% | 30% | 20%
Total Man Hours |  |  |  | 100 | 104
Date of Completion | [7 empty] | 2020-11-28
Demo on 24-11-2020 - Task Details
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-11-30
1 | Assign multiple maintenance task at the same time | PENDING | Dileep | 8
2 | Add multiple device at the same time | PENDING | Dileep | 8
3 | Landmark Module (add/edit landmarks) | PENDING | Dileep | 8
4 | Add Location details to Cube devices | PENDING | Dileep | 8
5 | Add contract user filter in all charts | PENDING | Dileep | 8
6 | Display data tables in chart pages | PENDING | Dileep | 16
7 | Location and Date filter in transaction Pages | PENDING | Dileep | 8
8 | Display count in the user pages | PENDING | Dileep | 4
9 | Use same devices for Cube & Mobile App (Changes in Cloud and APIs) | PENDING | Dileep | 8
10 | Testing & Support | PENDING | Lithin / Tinu | 16
Total Man Hours |  |  |  | 92 | 0
Date of Completion | [7 empty] | 2020-12-05