Procedure

Software Design & Development

Revision History

| Version | Author | Date | Remarks |
| --- | --- | --- | --- |
| 1.0 | Mohandas | 20-11-2017 | Initial Version |
| 1.1 | K S Mathew | 27-06-2018 | Process flow & responsibilities modified (sections 5.3, 7) |
| 1.2 | Suraj P | 24-11-2020 | Documents to be followed based on Project size |

Procedure for Software Design and Development

Table of Contents

1	PURPOSE	3

2	SCOPE	3

3	ABBREVIATIONS / DEFINITIONS	4

3.1 Abbreviations	4

3.2 Definitions	4

4	INPUTS	5

5	PROCEDURE	5

5.1 Initiating	5

5.2 Planning	6

5.3 Executing	7

5.4 Monitoring & Controlling	8

5.5 Closing	8

5.6 Agile Methodology	9

5.6.1 Project Initiation	10

5.6.2 Requirement Management	10

5.6.3 Project Planning	10

5.6.4 Project Execution & Control	10

5.6.5 Sprint Closure & Project Closure	11

6	OUTPUTS	11

7	RESPONSIBILITIES	12

8	QUALITY RECORDS	14

9	REFERENCE	14

10	ANNEXURE LIST	14

# PURPOSE

This Procedure for Design and Development describes the processes that are performed throughout the life cycle of a software project to ensure the efficient and effective management and execution of all software projectsat Indocosmo Systems Pvt. Ltd.  and is based on the following generic process flows:

- Initiating – set up goals, expectations and scope of the project

- Planning – develop a specific plan for the tasks and activities to be completed, including schedule and budget

- Executing – carry out the plan

- Monitoring &Controlling – monitor the results of execution, identify changes required, respond to changes, adjust the schedule, goals, and expectations as needed

- Closing – deliver the final project and assess the project and the process

Figure 1. Five process groups in project management (PMBOK)

This approach is based on the universal principles of the Project Management Institute's (PMI) Project Management Body of Knowledge (PMBOK). This approach would be applicable for projects following traditional waterfall model of software development life cycle (SDLC). The process to be followed in case of agile projects are described in section 5.6.

# SCOPE

This Procedure is applicable for all software projects of Indocosmo Systems Pvt. Ltd. Section 5.6 describes specific practices to be followed in case of agile projects.

# ABBREVIATIONS / Definitions

## 3.1 Abbreviations

| Abbreviation | Description |
| --- | --- |
| CCB | Change Control Board |
| CEO | Chief Executive Officer |
| PA | Project Authorization |
| PL | Project Lead |
| PM | Project Manager |
| PP | Project Plan |
| PSR | Project Status Report |
| SDD | Software Design Description |
| SDLC | Software Development Life Cycle |
| SRC | Software Release Committee |
| SRS | Software Requirement Specification |
| TP | Test Plan |
| UN | User Need |
| WBS | Work Break-down Structure |

## 3.2 definitions

| User Need: | A User Need is based on an operational or strategic need that has been identified from within a business unit, usually provided by the business user or customer. A User Need should detail and justify the baseline information about the project such as background, purpose, benefits, and objectives. In case of Japanese customers, the user need comes as an email or document in Japanese which will be translated by the Japanese translator of Indocosmo Systems. |
| --- | --- |
| Change Management: | The activity of managing changes whenever the scope of the project or the user needs or requirements change during the middle of a project, after baselining the scope or requirements. |
| Change Request: | Formal request for change in project scope and user requirements. Change Requests are authorised by Change Control Board (CCB). Approved Change Requests are implemented by the project team. Change requests may result in changes in the project management plan, costs, budgets or time schedules. |
| Project Authorization: | Project Authorization is a formal authorization from top management to the Project Manager to utilize the organizational resources to execute the project. Project Manager initiates or kick-off the project after receiving formal project authorization. |
| Project Plan: | The Project Plan is developed by the project manager through a series of iterative processes with involvement of major stakeholders in the project. Project plan shall be reviewed and agreed upon by the major stakeholders in the project including Project Lead, QA Manager& QA Member. |
| Project Manager: | The person responsible for the day to day management of the project objectives, tasks, progress and project team. |
| Project Team: | Individuals, groups and/or organisations, including all consultants, who are responsible for undertaking project tasks as directed by the Project Manager. |
| Status Report: | A status report provides a high-level overview of the progress of the project against the authorised project management plan baseline. It details recent project activities, resource utilization, milestones and deliverables, forthcoming planned activities, current issues and resolutions and a review of project risks. |
| Work Product: | The complete set or any of the individual items of the set, of computer programs, procedures, associated documentation and data designated for delivery to a customer or end-user. |
| Baseline: | A specification of product that has been formerly reviewed and agreed upon, that there after serves as the basis for further development. This can be changed only through formal change control procedures. |

# inputs

- User Need (UN)

# procedure

## 5.1 initiating

The Initiating Phase begins with the gathering of the user needs by the PM. The User needs can come through various channels like telephone calls from customers, emails from customers or in meetings with the customer or as a user need document received from customer. The user needs are usually received by the PM or CEO of Indocosmo Systems Pvt. Ltd. In case of Japanese customers, the user need is usually in Japanese language which will be translated to English by the Japanese translator of Indocosmo Systems.

The next step is to prepare a Project Authorisation (PA) (Refer Annexure ICS/FMT/PA – Project Authorization Template) by PM and to get the approval from CEO for the same. Project Lead (PL), QA Manager and QA Member for the project shall be identified and documented in Project Authorization. Project Authorization includes the following information:

- Project Code and Project Name

- Start Date and End Date of the project

- High Level Objectives of the project

- Estimated Software Size, Effort and Team Size

- Main stakeholders and their contact details

- Major milestones, deliverables, target dates and responsibility

- Identified Risks, Assumptions and Constraints

Once PA is approved, PL shall prepare a project kick-off presentation and conduct a Kick-Off meeting for the project involving all development team members and testers of the project. PM/PL shall invite all other stakeholders of the project also for the Kick-Off meeting.

Key tasks:

- Get approval in the form of a Project Authorization Document (Refer Annexure ICS/FMT/PA – Project Authorization Template).

- Conduct a Project Kick-off Meeting

## 5.2 planning

The major activity in the Planning Phase is the preparation of the Project Plan. PM is having the full responsibility and authority for the Project Plan. The Project Manager, in consultation with key stakeholders, outlines the intended approach to project governance, executing the work, and managing resources and risk in the Project Plan.PM shall decide the SDLC process model/methodology to be followed in the project and document it in the project plan. In case of Agile methodology, the process described under section 5.6 shall be followed. The PM will do the estimation of the project size, effort, time and resources required for the project using established methods such as Function Point Analysis (Refer Annexure ICS/FMT/FPA – FP Estimation Template) or WBS based Effort Estimation. The High-Level Work Break-down Structure (WBS) will be provided by the PM in the Project Plan based on the estimation. The Project Lead should provide further detail about how the project will be conducted. The major activity by the PL is the addition of detailed Task Schedule to the Project Plan. The PM can decide on the tool to be used to maintain the Task Schedule like Excel or MS Project and should mention the same in Project Plan. All projects will have some risks and identification of risks and planning of risk response mechanisms is an important activity during project planning. Identified risks, their priority and risk mitigation steps shall be documented in Project Plan.

The QA Manager will prepare a Test Plan and submit it to the PM for review and approval. QA member of the project shall plan software quality assurance activities like reviews and audits, which will be documented in the project plan by PM. All planning documents shall be reviewed by QA member of the project also to ensure its compliance with the defined process.

Key tasks:

- Complete FP Estimation or WBS based Effort Estimation based on the User Needs/ requirements.

- Complete Task Schedule within the time bounds mentioned in Project Plan.

- Complete Project Plan (Refer Annexure ICS/FMT/PP – Project Plan Template).

- Complete Test Plan (Refer Annexure of Procedure for Software Testing ICS/FMT/TP – Test Plan Template)

- Create Project repository and grant access permissions for project team members on the project repository

## 5.3 executing

Throughout the project, the project manager will manage risks and issues; communicate regularly with stakeholders (weekly client meetings); manage and support the team (weekly team meetings); report to the top management (Refer Annexure ICS/FMT/PSR – Project Status Report Template); review and rework the project plan if a change request is processed as mentioned in the project plan.

The Project Lead is responsible for configuration management activities in the project. The PL does the Code Review, Unit Test review, Integration, Integration Testing and overall monitoring/tracking of tasks by his/her team members. During the Coding phase of SDLC, the Development team follows coding conventions and standards set by the PM in the Project Plan and also create and executes Unit Test cases.

The Execution Phase focuses on the process of determining how the project outputs will be delivered. PL is primarily responsible for all execution activities in the project and shall get the work done by the project team.

Key tasks:

- Complete detailed requirement elicitation, requirement analysis and prepare Software Requirement Specification (Refer ICS/FMT/SRS – Software Requirement Specification Template) and Requirement Traceability Matrix (Refer ICS/FMT/RTM – Requirement Traceability Matrix Template). PM shall review and approve the SRS and RTM. In case of projects from Japanese customers, the SRS will be translated to Japanese before sharing the document with the customer.

- Once SRS is approved, Tester(s) shall prepare the Test Case (Refer ICS/FMT/TC – Test Case Template) for System Testing. Test Case will be reviewed by PL and approved by PM.

- Complete software design following the Object Oriented Analysis and Design (OOAD) approach using UML and prepare Software Design Description (Refer ICS/FMT/SDD – Software Design Description Template). PM shall review and approve SDD.

- Once SDD is approved, development team shall complete coding based on the SDD following the respective coding standard, write unit test cases and complete the unit testing. PL shall review the code and unit test result.

- Once the coding of all units are complete, PL will do the integration of various units and do integration testing with the help of development team. On successful completion of integration testing, PL will build the integrated system and deploy it in the server with the help of development team.

- Tester(s) will then do the system testing using the test cases prepared. Test results shall be reviewed by the QA Manager, Project Lead and Project Manager.

- Development team shall fix the bugs reported by the testers during system testing and give a new build to the testers for next test iteration. Multiple test iterations may be required for the system to become defect free and ready for release.

- Once the system testing is complete and the software is ready for release, Tester(s) will prepare a release checklist (filling the testing related sections) and send the release checklist & test results to QA Manager with recommendation for releasing the system to customer.

- QA Manager shall review the release checklist & test results and give a go ahead to PM/PL to prepare for release. PL shall update the remaining sections of release checklist, prepare a release note and send to PM for review.

- PM reviews the completed release checklist and release note and send it to Software Release Committee (SRC consists of QA Manager, PM, PL, Tester, QA Member) requesting for release approval. QA Manager is the approving authority of SRC.

- QA Manager may give the approval for release through return email or call for a SRC meeting (in case of major project releases) for approving the release.

- Once SRC approves the release, PL shall deploy the system in the production environment.

- After the deployment, PM shall notify the customer and share the release note to customer.

- PM is responsible for following up with the customer for getting the acceptance of the software after the user acceptance testing by customer.

## 5.4 monitoring & Controlling

The PM holds the major role in Control and Monitoring of the project as a whole. The major activities in controlling and monitoring a project are as follows: -

- Monitor Project Planning Parameters - Monitor actual values of project planning parameters against the project plan

- Monitor Commitments - Monitor commitments of various stakeholders and other departments/groups against those identified in the project plan.

- Monitor Project Risks - Monitor risks against those identified in the project plan and identify & address new risks (if any)

- Monitor Data Management - Monitor the management of project data against the project plan

- Monitor Stakeholder Involvement - Monitor stakeholder involvement against the project plan

- Conduct Progress Reviews - Periodically review the project’s progress, performance, and issues and report the status in weekly meeting with CEO.

- Monitor Software Quality Assurance (SQA) – Monitor SQA activities in the project, review QA Member Report at every milestone and take corrective and preventive actions.

## 5.5 Closing

The Closing Phase is the formal closure of the delivery component of the project. It has three main outcomes:

- The handover of project outputs to the operational areas responsible for ongoing support and maintenance (if applicable to the project); archiving or taking backup of project repository and

- The evaluation of the success of the project and document the lessons learned.

- Release of resources and revoking the access rights granted to the team members on the project repository.

Key tasks:

- Once customer acceptance is received, PL shall prepare a project closure document (Refer ICS/FMT/PCD – Project Closure Document Template) and call for a closure meeting. PM and QA Member shall review the Project Closure Document.

- PM shall send the Project Closure Document to CEO informing about the project completion and approval of project closure

- Document the lessons learnt and include it in the Project Closure Document

- Archive/take backup of project repository

- Release resources and revoke access rights granted to the team members on the project repository.

- Prepare communications to the project stakeholders and the wider community to notify them of the completion of the project.

## 5.6 agile methodology

The PM (acting as the Scrum Master/Internal product owner in Agile Methodology) can decide which methodology to be followed for the project. In case of agile projects, following procedures/practices shall be followed.

If Product requirements cannot be defined in advance and are not repeatable, scrum model of software development can be used. Requirements are accomplished in sprints based on the evolving understanding of the solution being built. Scrum is a lightweight process framework for agile development, and the most widely-used one. Scrum is most often used to manage complex software and product development, using iterative and incremental practices. Project is divided into multiple short time boxes or iterations called sprints, which is typically of 2 to 4 weeks’ duration. A pictorial representation of the Agile Scrum process is given below.

### 5.6.1 Project Initiation

Please refer section 5.1 for project initiation

### 5.6.2Requirement Management

The requirements are collected from the customer by the PM and is maintained in a document called Product Backlog (Refer Annexure ICS/FMT/PBL – Product Backlog Template). Product Backlog is a prioritized list of product features. A subset of features from product backlog is selected by the PM (after discussion with customer) for implementation in every sprint. This is called sprint backlog (Refer Annexure ICS/FMT/SBL – Sprint Backlog Template). The project team do the requirement analysis and prepare a requirement specification for the features in the sprint backlog. These features are then designed, coded, tested and demonstrated by the team during the sprint.

### 5.6.3 Project Planning

PM prepares a release plan and high-level sprint plan (RPHSP)and detailed project plan (PP) for the project. Plan for each sprint is prepared during sprint planning. Sprint planning is done on the first day (for 4-8 hours depending on the duration of sprint) of the sprint. The team decompose the features included in the sprint into tasks and estimation of tasks is done. The scrum board is prepared by pasting the planned tasks slips. Task assignment happens on voluntary basis.

### 5.6.4 Project Execution & Control

The team members do the activities as planned in the sprint. On every day morning, a daily scrum meeting for 15 minutes is convened by PM involving all team members. Team members report the status of the activities and Scrum master plot the burn-down chart showing the remaining hours.

### 5.6.5Sprint Closure & Project Closure

At the end of every sprint, there is a sprint review/demo meeting in which team will demonstrate the working features included in the current sprint. Comments received during the demo will be recorded. After the sprint review, there will be a sprint retrospective meeting in which team reflects back on what went well and what went wrong and take action to improve further (Please refer ICS/FMT/SCD – Sprint Closure Document Template).

Please refer section 5.5 for Project Closure. Project closure activities shall be done after the closure of last sprint of the project. In all other sprints, only the sprint closure activities shall be done.

# outputs

Based on the size of projects, the projects are broadly classified into three categories.

| Project Category | Effort in Man Months |
| --- | --- |
| SMALL | Upto 3 Man months |
| MEDIUM | 3 to 9 months |
| LARGE | > 9 Months |

|  |  | Project Category |  |  |
| --- | --- | --- | --- | --- |
| Sl. No. | Artifacts | SMALL | MEDIUM | LARGE |
| 1 | Client Enquiry | M | M | M |
| 2 | Quote with specifications | M | M | M |
| 3 | Acceptance Mail from the Client | M | M | M |
| 4 | PO from Client | M | M | M |
| 5 | Revision if any | O | O | O |
| 6 | Document Repository Index | M | M | M |
| 7 | Prototype/POC document | O | O | O |
| 8 | Project Authorisation (PA) | M | M | M |
| 9 | Software Requirement Specification (SRS) | M | M | M |
| 10 | Financial estimation | N | M | M |
| 11 | Work project schedule | N | M | M |
| 12 | Project Plan. | M | M | M |
| 13 | Software Design Description (SDD). | M | M | M |
| 14 | Requirement Traceability Matrix (RTM) | N | O | O |
| 15 | Change Request Tracker | N | M | M |
| 16 | Test Plan (TP) &Test Case Documents | N | M | M |
| 17 | Test Case (TC) | M | M | M |
| 18 | Project Status Report (PSR) | M | M | M |
| 19 | Release Check List & Release Notes | N | M | M |
| 20 | Project Closure Document with Learnings | M | M | M |
| 21 | Evaluation of the success (Customer feed back) & document the lessons learned. | M | M | M |
| 22 | Reusable components - identified and added to repository | M | M | M |
| 23 | Project Risk Tracker | M | M | M |
| 24 | User Guide for Client | M | M | M |
| 25 | User Guide for Programmer | M | M | M |

Notation:  Mandatory / Optional / Not required

# responsibilities

Responsibilities regarding the activities and documents throughout the project is depicted in the “ICS Project Process Flow Diagram” given below:

# quality records

- Review &Audit Reports

- Project Closure Document

- Sprint Closure Document

# reference

PMBOK	- Project Management Body of Knowledge by Project Management Institute (PMI, USA)

# annexure list

- ICS/FMT/PA	- Project Authorization Template

- ICS/FMT/FPA 	- FP Estimation Template

- ICS/FMT/TS 	- Task Schedule Template

- ICS/FMT/PP	- Project Plan Template

- ICS/FMT/SRS	- Software Requirement Specification Template

- ICS/FMT/RTM	- Requirement Traceability Matrix Template

- ICS/FMT/SDD	- Software Design Description Template

- ICS/FMT/PSR	- Project Status Report Template

- ICS/FMT/PCD	- Project Closure Document Template

- ICS/FMT/PBL	- Product Backlog

- ICS/FMT/RPHSP    - Release Plan and High-Level Sprint Plan

- ICS/FMT/SBL	- Sprint Backlog

- ICS/FMT/SCD	- Sprint Closure Document