## Tasks
Chat v2 Estimate
Module / Sub module |  | Estimation
|  | TIME (Hours) |  | COST (INR)
|  | Web App | iOS App | Web App | iOS App
Standard Per Hour Rate (Currency INR) |  |  |  | 1150
Admin Module (WEB) |  |  |  | 0 | 0
Products Add/Edit/Delete |  | 64 |  | 73600 | 0
Product Owner Create/Edit//Delete |  | 36 |  | 41400 | 0
Product to Product Owner linking |  | 12 |  | 13800 | 0
Remove Product to Product Owner linking |  | 6 |  | 6900 | 0
View chat messages - Category wise Product wise wise Customer wise |  | 64 |  | 73600 | 0
View deleted products and its chat messages |  | 16 |  | 18400 | 0
Product Owner/Customer Modules
Recent Chat list |  | 28 | 20 | 32200 | 23000
User(Customer) Registration/Edit/Deregistration |  | 16 | 8 | 18400 | 9200
Login / Logout Customer, Product Owner, Manager |  | 20 | 12 | 23000 | 13800
User - Products Card Layout |  | 16 | 16 | 18400 | 18400
User - Product Attributes View |  | 16 | 16 | 18400 | 18400
Display User + Product as in the contact List |  | 24 | 8 | 27600 | 9200
User Chat page with product details |  | 35 | 16 | 40250 | 18400
Product Owner Home page |  | 40 | 24 | 46000 | 27600
Load Product Details and Chat |  | 24 | 8 | 27600 | 9200
Send and receive text, voice and attachment messages |  | 56 |  | 64400 | 0
Close chat (Back to Product list) |  | 16 | 4 | 18400 | 4600
Load products /message based on user action (on mouse scroll) |  | 28 | 4 | 32200 | 4600
Product details loading on more link |  | 16 | 8 | 18400 | 9200
Offline chat feature |  | 80 |  | 92000 | 0
Customer Feedback (with history) |  | 24 | 4 | 27600 | 4600
T O T A L |  | 637 | 148 | 732550 | 170200
|  | 785 Hours |  | 9,02,750 INR
Enhancements
v2 | Reply Feature Implementation | 106 | 32 | 121900 | 36800
| First Name Search to Username Search | 16 | 8 | 18400 | 9200
| Additional Attachment format support | 24 | 8 | 27600 | 9200
v1 | Reply Feature Implementation | 40 | 16 | 46000 | 18400
| First Name Search to Username Search | 8 | 6 | 9200 | 6900
| Additional Attachment format support | 8 | 8 | 9200 | 9200
T O T A L |  | 276 | 78 | 232300 | 89700
|  | 280 Hours |  | 3,22,000 INR