## Sheet1
Project Work Schedule
No | Task | Assignee | Estimated Start | Estimated Finish | Estimated Work (In Hours)
1 | Create new images using Augmentation techniques & Dataset preparation | Amal/Berlin/Blessy | 2020-02-28 | 2020-04-13 | 280
2 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | 2020-02-17 | 2020-07-02 | 600
3 | Extract object image, from the Block with its position, size | Amal/Berlin/Blessy | 2020-03-16 | 2020-04-17 | 288
4 | Test and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | 2020-04-23 | 2020-07-02 | 360
5 | Project Documentation - Requirements, Design documents & Abstract doc | Suraj/Berlin/Blessy | 2020-04-23 |  | 80
6 | Setting up the cloud instance and run the code with all GPUs | Suraj | 2020-05-08 |  | 120
7 | POC for bounding box coordinates for text from image | Amal/Berlin/Blessy | 2020-05-18 | 2020-05-30 | 80
8 | Identify new objects by incrementally learning and without specific training | Amal/Berlin/Blessy | 2020-05-18 |  | 240
9 | Rewrite the code to support the distributed computing | Suraj/Amal/Berlin | 2020-06-15 | 2020-06-29 | 150
10 | Build and train AI model to identify and extract TEXT from the catalog image | Berlin/Blessy | 2020-06-15 | 2020-07-10 | 120
11 | Train and test with the model build using TF v2 | Amal/Berlin/Blessy | 2020-06-13 | 2020-06-29 | 40