## Project Risk Register
PROJECT RISK CHECKLIST
Note: This is a comprehensive list of all probable risks in software development projects and can be used for risk identification. Identification and management of risks in specific projects can be done using this checklist, along with brainstorming within the team, and shall be documented in project plan.
S. No. | Probable Software Project Risks | Impact(s) | Suggested Risk Response or Risk Mitigation Actions | Risk Owner
1 | Shortage of technically trained man power | a) Schedule slippage | 1 (a) Make estimates with a little allowance for initial learning time | PM
|  | b) Effort/Cost increase | 1 (b) Maintain buffers of extra resources | HR
|  | c) Poor quality of deliverables | 1 (c) Define project specific training program | PM
|  |  | 1 (d) Conduct cross-training sessions | HR
2 | Too many requirement changes | a) Schedule slippage | 2 (a) Obtain Sign-off for the initial requirements specification from the client | PM
|  | b) Effort/Cost increase | 2 (b) Convince the client that changes in requirements will affect the schedule | PM
|  |  | 2 (c) Define a procedure to handle requirement changes | QA
|  |  | 2 (d) Follow incremental/iterative or agile development methodology | PM
|  |  | 2 (e) Design to implement abstraction and information hiding | PM
|  |  | 2 (f) Negotiate payment on actual effort | PM
3 | Unclear requirements | a) Schedule slippage | 3 (a) Use experience and logic to make some assumptions and keep the client informed; obtain sign-off | PM
|  | b) Effort/Cost increase | 3 (b) Develop a prototype and have the requirements reviewed by the client | PM
c) Product not meeting the acceptance criteria
4 | Manpower Attrition | a) Schedule slippage | 4 (a) Ensure that multiple resources are assigned on key project areas | HR
|  | b) Poor quality of deliverables | 4 (b) Pair Programming | PM
|  |  | 4 (c) Have team building sessions | HR
|  |  | 4 (d) Rotate jobs among team members | HR
|  |  | 4 (e) Keep extra resources in the project as backup | HR
|  |  | 4 (f) Maintain proper documentation of each individual’s work | PM
|  |  | 4 (g) Follow the configuration management process and guidelines strictly | PM
5 | Externally driven decisions forced on the project | a) Schedule slippage | 5 (a) Outline disadvantages with supporting facts and data and negotiate with the personnel responsible for forcing the decisions | PM
|  | b) Effort/Cost increase | 5 (b) If inevitable, identify the actual risk and follow its mitigation plan | PM
c) Poor quality of deliverables
6 | Not meeting performance requirements | a) Product not meeting the acceptance criteria | 6 (a) Define the performance criteria clearly and have them reviewed by the client | PM
|  |  | 6 (b) Define standards to be followed to meet the performance criteria | PM
|  |  | 6 (c) Prepare the design to meet performance criteria and review it | PM
|  |  | 6 (d) Simulate or prototype performance of critical transactions | PM
|  |  | 6 (e) Test with a representative volume of data where possible | PM
|  |  | 6 (f) Modeling, Prototyping and Tuning | PM
|  |  | 6 (g) Conduct stress tests where possible | PM
7 | Unrealistic schedules & budgets | a) Schedule slippage | 7 (a) Negotiate for a better schedule | PM
|  | b) Effort/Cost increase | 7 (b) Identify parallel tasks | PM
|  |  | 7 (c) Have resources ready early | HR
|  |  | 7 (d) Identify areas that can be automated | PM
|  |  | 7 (e) If the critical path is not within the schedule, negotiate with the client | PM
|  |  | 7 (f) Negotiate payment on actual effort | PM
|  |  | 7 (g) Incremental development | PM
|  |  | 7 (h) Software Re-use | PM
|  |  | 7 (i) Requirement scrubbing | PM
8 | Working on new technology (hardware and software) | a) Schedule slippage | 8 (a) Consider phased delivery | PM
|  | b) Effort/Cost increase | 8 (b) Begin with the delivery of critical modules | PM
|  | c) Poor quality of deliverables | 8 (c) Include time in the schedule for a learning curve | PM
|  |  | 8 (d) Provide training in the new technology | HR
|  |  | 8 (e) Develop a proof-of-concept application | PM
9 | Insufficient business knowledge | a) Product not meeting the acceptance criteria | 9 (a) Increase interaction with the client and ensure adequate knowledge transfer | PM
|  | b) Poor quality of deliverables | 9 (b) Organize domain knowledge training | PM
|  |  | 9 (c) Simulate or prototype the business transaction for the client and get it approved | PM
10 | Incorrect estimates of effort, cost and schedule | a) Schedule slippage | 10 (a) Use standard estimation techniques | PM
|  | b) Effort/Cost increase | 10 (b) Use multiple estimation techniques and compare | PM
|  |  | 10 (c) Re-estimate at the end of every phase | PM
|  |  | 10 (d) Negotiate for re-estimated effort, cost and schedule with the client & management | PM
|  |  | 10 (e ) Recording and analysis past projects and compare the estimation with historical data | PM
|  |  | 10 (f) Incremental/iterative/agile development methodology | PM
|  |  | 10 (g) Negotiate for time & material type of contract (ie. payment on actual effort / time) | PM
11 | Personnel Shortfalls | a) Product not meeting the acceptance criteria | 11 (a) Staffing with top talent | HR
|  | b) Poor quality of deliverables | 11 (b) Job matching during recruitment | HR
|  |  | 11 (c) Team building | HR
|  |  | 11 (d) Key personnel agreements | HR
|  |  | 11 (e) Training | HR
|  |  | 11 (f) Pre-scheduling key people | HR
12 | Shortfalls in externally performed tasks | a) Schedule slippage | 12 (a) Reference checking | PM
|  | b) Poor quality of deliverables | 12 (b) Pre-award audits | PM
|  |  | 12 (c ) Award free contracts first | PM
|  |  | 12 (d) Competetive design or prototyping | PM
|  |  | 12 (e ) Team building | HR
14 | Developing wrong software functions and user interface | a) Product not meeting the acceptance criteria | 14 (a) Organization analysis | PM
|  | b) Poor quality of deliverables | 14 (b) User surveys | PM
|  |  | 14 (c ) Prototyping | PM
|  |  | 14 (d) Scenarios or use case modeling | PM
|  |  | 14 (e) Prepare users manual early and get it reviewed by users | PM
15 | Link failure or slow performance (of communication links) | a) Product not meeting the acceptance criteria | 15 (a) Set proper expectations with the client | PM
|  |  | 15 (b) Plan ahead for the link load test | PM
|  |  | 15 (c) Plan for optimal link usage | PM
16 | Information Security related Risks | a) Unauthorized access to project documents and source code | 16 (a) Set access permissions in project repository (SVN) as per the team members role on request by PM | PM
|  | b) Hacking of web application | 16 (b) Revoke access permissions in project repository (SVN) on project closure on request by PM | PM
|  |  | 16 (c) Conduct vulnerability assessment/Penetration Testing of web application using OWASP compliant security testing tools, once in 3 months. Fix the identified vulnerabilities. | PM

## Sheet3 (hidden)
High | A
Low | B
C
D

## Treatment Options (hidden)
Risk Treatment Options
Depending on the type and nature of the risk, the following options are available:
OPTION | TREATMENT
AVOID | Deciding not to proceed with the activity that introduced the unacceptable risk, choosing an alternative more acceptable activity that meets business objectives, or choosing an alternative less risky approach or process.
REDUCE | Implementing a strategy that is designed to reduce the likelihood or consequence of the risk to an acceptable level, where elimination is considered to be excessive in terms of time or expense.
TRANSFER | Implementing a strategy that shares or transfers the risk to another party or parties, such as outsourcing the management of physical assets, developing contracts with service providers or insuring against the risk. The third-party accepting the risk should be aware of and agree to accept this obligation.
ACCEPT | Making an informed decision that the risk rating is at an acceptable level or that the cost of the treatment outweighs the benefit. This option may also be relevant in situations where a residual risk remains after other treatment options have been put in place. No further action is taken to treat the risk, however, ongoing monitoring is recommended.

## Sheet5 (hidden)
Eliminate
Accept
Reduce/Mitigate
Transfer

## Sheet1 (hidden)
HR
OPS