## sheet1
Repair application-Time estimation
LAST UPDATED ON: 23-Sep-2020
LAST UPDATED BY: Joshy
Assumptions Back end :- Java Spring boot with hibernate Front end :- Bootstrap,jquery Database :- Mysql
User
SLNo | Tasks | Phase | EST. HRS | Assumptions/remarks
| project initilization and setup,server setup | phase 1 | 8
| signup/login/forget password gui | phase 1 | 8
| setup spring security with social login | phase 1 | 24 | assuming that we are using spring boot frame work
| implementation signup/login/forget password features(coding part) | phase 1 | 18
| Form to fill required user details after social login and save it into database( first time only) | phase 1 | 8 | only limited information will get from the social login
| For registering repair request - choose product category,search and choose product from product list | phase 1 | 12
| For registering repair request - add new products if not found in the product list and add to admin's approval list | phase 1 | 12
| repair request form to get the details of product fault from customer and save to the db | phase 1 | 16
| Testing | phase 1 | 24
| dash board for user- recent repair request,notifications, repair hiostory | phase 2 | 28 | if any options newly added to the dashboard then the estimated time will vary
| send email/sms notifications user when the status is updated | phase 2 | 16
| approve the diagnostic report by customer sent by technician | phase 2 | 4
|  | sum | 178
Admin
| list and edit new products submitted by the user and approve /reject the new products | phase 1 | 32
| list/create/update/delete produts gui and coding | phase 1 | 32
| list/create/update/delete category gui and coding | phase 1 | 14
| create/delete technician | phase 2 | 16 | assuming that admin will create and delete technician
| list and assign jobs to the technician | phase 2 | 14
| Testing | phase 1 | 24
|  | sum | 132
Technician
| list the assigned jobs and show details | phase 2 | 16
| update the status of repair jobs | phase 2 | 8
| create/update/delete spare request | phase 2 | 24
| Testing | phase 2 | 8
|  | sum | 56
|  | total | 366