## Tasks
Carrypark Estimate
Module / Sub module | Estimation
| TIME (Hours) |  |  | COST (INR)
| Web App | iOS App | Android App | Web App | iOS App | Android App
Standard Per Hour Rate (Currency INR) |  |  |  | 1150
Design & Documentation
System Analysis & Design | 24 | 72 | 64 | 27600 | 82800 | 73600
System Prototype | 32 | 93 | 75 | 36800 | 106950 | 86250
SRS - Documentation | 16 | 32 | 32 | 18400
User Registration
User Registration and Login Module | 32 | 40 | 40 | 36800 | 46000 | 46000
Multilanguage support | 12 | 24 | 24 | 13800 | 27600 | 27600
Cloud Settings | 96 |  |  | 110400 | 0 | 0
Screen design changes & Login as new device functionality |  | 10 | 9 | 0 | 11500 | 10350
Rate information screen changes & Video implementation |  | 8 | 8 | 0 | 9200 | 9200
Device Management
QR Code scanning & Device locking process | 56 | 112 | 96 | 64400 | 128800 | 110400
Navigation flow changes & Google map Integration |  | 16 | 20 | 0 | 18400 | 23000
Device Location Settings - Cloud | 16 |  |  | 18400 | 0 | 0
QR Code Scan design changes |  | 18 | 8 | 0 | 20700 | 9200
Device unlocking process | 56 | 112 | 96 | 64400 | 128800 | 110400
In Use Device listing & Google map integration |  | 16 | 20 | 0 | 18400 | 23000
Business Customers & Contract Devices |  | 16 | 20 | 0 | 18400 | 23000
Payment Integration
Payment Integration | 32 | 96 | 80 | 36800 | 110400 | 92000
Payment Bypass on Contract Devices | 16 | 14 | 15 | 18400 | 16100 | 17250
Intergated Testing
FW Testing | 32 | 56 | 56 | 36800 | 64400 | 64400
Security Implementation
Design & Documentation | 8 | 24 | 16 | 9200 | 27600 | 18400
Security Implementation | 48 | 56 | 64 | 55200 | 64400 | 73600
FW Testing
Integration Testing with FW sample | 32 | 53 | 56 | 36800 | 60950 | 64400
Maintenance & Dashboard
UI Design |  | 24 | 35 | 0 | 27600 | 40250
Maintenance user login |  | 8 | 16 | 0 | 9200 | 18400
Task Listing - Installation / Maintenance |  | 12 | 16 | 0 | 13800 | 18400
Scanning & Uploading Images |  | 40 | 40 | 0 | 46000 | 46000
Work details & Summary |  | 36 | 36 | 0 | 41400 | 41400
Lock Screen & Release latch |  | 16 | 16 | 0 | 18400 | 18400
Unlock & Summary & Location |  | 28 | 28 | 0 | 32200 | 32200
Maintenance Company & maintenance person | 18 |  |  | 20700 | 0 | 0
Assign devices & task to maintenance persons | 24 |  |  | 27600 | 0 | 0
Dashboard charts - Line / Bar / Pie | 81 |  |  | 93150 | 0 | 0
Usage & Statistics Drilldown Report & Log report | 36 |  |  | 41400 | 0 | 0
Bluetooth connectivity issues |  | 31 | 34 | 0 | 35650 | 39100
Cube Application - Cloud
Cube registration & login | 24 |  |  | 27600 | 0 | 0
Error Logging - API | 8 |  |  | 9200 | 0 | 0
Locking & Unlocking - API | 18 |  |  | 20700 | 0 | 0
Compose Hash - API | 8 |  |  | 9200 | 0 | 0
Cube Power On - API | 8 |  |  | 9200 | 0 | 0
Log Status - API | 8 |  |  | 9200 | 0 | 0
Log Photo - API | 8 |  |  | 9200 | 0 | 0
Action Query - API | 8 |  |  | 9200 | 0 | 0
Cube Login Module | 16 |  |  | 18400 | 0 | 0
Device Listing Page | 4 |  |  | 4600 | 0 | 0
Error Log Listing Page | 8 |  |  | 9200 | 0 | 0
Photos Display Page | 8 |  |  | 9200 | 0 | 0
Maintenance Dashboard | 18 |  |  | 20700 | 0 | 0
Testing & Support - Cube | 8
Additional Requirements
Battery Module Management & Chart | 16
Pie Chart | 16
Adding swipeable image in app screen | 8 | 16 | 16
Split hash key in app screen |  | 24 | 24
Maintenance Task Page a) Adding Area, Location, Landmark filter b) Adding boxes to show the device count c) Changing and adding additional columns in list | 16
Error Log Page a) Adding Area, Location, Landmark filter b) Adding boxes to various count c) Bar Charts to show various error count | 16
App User Page a) Adding boxes to device count b) Changing and adding additional columns in list | 8
Invoice generation for app users | 4 | 16 | 16
Cloud Modifications 1) Device Listing Page for Maintenance user Login 2) Search feature in Google map in Location Page 3) Display password of maintenance user in view page 4) Display total number boxes in Chart pages | 40
T O T A L | 943 | 1119 | 1076 | 932650 | 1185650 | 1136200
| 1046 Hours |  |  | 3254500