## Index
Document Issue Status
| Document ID |  | Project-Status-Report-Profield-Chat-v2
| Document Name |  | Project Status Report
| Latest Version |  | 2
| Created By | Creatred Date |  | Reviewd By | Reviewed Date |  | Approved By | Approved Date
| Mohandas | 2020-01-06 |  | Davis Sebastian | 2020-12-02 |  | Davis Sebastian | 2020-12-02
Profield Chat v2
Project Status Report
www.indocosmo.com | [5 empty] | All rights Reserved

## Jan 2nd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11
1 | Product add/delete in admin module | Midhun | Completed | 30% | 50% | 60% | 65% | 80% | 100%
2 | Product List with search and filter. | Joshy | Completed | 70% | 75% | 80% | 85% | 90% | 100%
3 | iOS functionality | Lithin | Progressing | 5% | 8% | 10% | 15% | 18% | 20%

## Jan 3rd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17
1 | Product update in admin module | Midhun | Completed | 50% | 100%
2 | Product owner and customer page and their functionality. | Joshy | Progressing | 10% | 15% | 25% | 30% | 40%
3 | Customer and category add/delete in admin module | Midhun | Progressing |  |  | 50% | 80% | 100%
4 | iOS functionality | Lithin | Progressing | 25% | 30% | 33% | 37% | 40%

## Jan 4th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25
1 | Customer and category update in admin module | Midhun | Completed | 50% | 100%
2 | Product owner and customer page and their functionality. | Joshy | Progressing | 50% | 65% | 70% | 80% | 85% | 90%
3 | View chat messages and deletion of messages - Category wise, Product wise and Customer wise. | Midhun | Progressing |  |  | 20% | 30% | 35% | 40%
4 | iOS functionality | Lithin | Progressing | 45% | 48% | 52% | 55% | 58% | 60%

## jan 5th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31
1 | View chat messages and deletion of messages - Category wise, Product wise and Customer wise. | Midhun | Completed | 50% | 80% | 90% | 100%
2 | Product owner and customer page and their functionality. | Joshy | Progressing | 96% | 98% | 100%
3 | Reply messages | Joshy | Progressing |  |  |  | 10% | 20%
4 | Reply messages | Midhun | Progressing |  |  |  |  | 10%
5 | API for iOS | Gana | Progressing |  | 10% | 20% | 30% | 40%
6 | iOS functionality | Lithin | Progressing | 65% | 68% | 74% | 78% | 80%

## Feb 2nd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08
1 | Reply messages | Midhun | Completed | 20% | 50% | 80% | 100%
2 | Reply messages | Joshy | Progressing | 40% | 70% | 100%
3 | API for iOS | Gana | Completed | 50% | 60% | 70% | 80% | 90% | 100%
4 | Application testing and bug fixing | Joshy | Progressing |  |  |  | 20% | 40% | 60%
5 | Application testing and bug fixing | Midhun | Progressing |  |  |  |  | 20% | 50%
6 | iOS functionality | Lithin | Progressing | 85% | 88% | 90% | 92% | 94% | 100%
7 | Customer feedback functionality | Gana | Completed | 10% | 40% | 60% | 80% | 100%

## Feb 3rd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13
1 | Application testing and bug fixing | Midhun/Digna/Joshy/Gana | Completed | 90% | 100% | 100% | 100%
2 | iOS functionality testing and bug fixing | Lithin | Completed | 60% | 100% | 100% | 100%