## Sheet1
HMS New Requirements Estimation
Created By | Ayana Dharman
Sl.No. | Module | Task | Task Name | Owner | Status | Estimated time(Hrs) | Start Date | End Date
1 | Request (DashBoard) | Special requests captured remains forever. These should be time bound and should be removed at checkout time. | Bug | Ayana | Open | 4 | 2021-02-01
2 | Reservation | Reservation data not getting updated - Blocked rooms are not getting marked as reserved. Message could be generated closer to check-in date to call and confirm the reservation. // Need to update the Room status on House Keeping screen | Bug | Ayana | Open | 2 | 2021-02-01
3 | DashBoard | Overall room status is not shown. Only category wise availability is being shown. Total availability should be shown. //Change from pie chart to list on the dashboard – home screen. Should also show total rooms available. | New Requirement | Ayana | Open | 4 | 2021-02-01
4 | Reception, Reservation | Receipt printing for advance payment need to be included // Nithin to check with Pradeep and confirm | New Requirement | Ayana | On hold | 24 | 2021-02-01
5 | Reception, Reservation | Advance payment received not reflected in revenue report // Nithin to check with Pradeep and confirm | Bug | Ayana | On hold | 4 | 2021-02-01
6 | Reception, Reservation | Check-in process should take care of the advance received automatically. This is handled manually. // Nithin to check with Pradeep and confirm | New Requirement | Ayana | On hold | 4 | 2021-02-01
7 | Reception, Reservation | GRC (Guest Registration Card) should include advance collected and the receipt number issued // Need to add receipt number in capture screen and report. GRC – reception; GRC for reservation confirmed with client | New Requirement | Ayana | Open | 16 | 2021-02-01
8 | Corporate Report | Corporate list is not working. //Fixed – but is slow – Ayana to review the stored procedure and tune SQL if possible. To notify the user about background process is happening – change button label content to “Click OK to continue”; | Bug | Ayana | Open | 2 | 2021-02-01
9 | Corporate Report | additionally a new report may be required. Format to be provided by Nithin | New Requirement | Ayana | On hold | 8 | 2021-02-01
10 | Petty Cash | Petty Cash -Item purchased and distributed is not getting handled. Need more clarity – Not fixed // Petty cash entry date is showing one day previous – needs to be fixed. | Bug | Ayana | Open | 3 | 2021-02-01
11 | Customer Outstanding Report | Payment collection towards Credits is not getting reflected. Customer wise payment outstanding report is needed. //To fix the current report – Niko to send a mail with all new requirements. Report exists in the system but giving an error | Bug | Ayana | Open | 16 | 2021-02-01
12 | Night Audit | Night auditing can now be done only using one user id (Nithin’s). This need to be made available to all other staff’s id too. | Bug | Ayana | On hold | 2 | 2021-02-01
13 | Room | .Rooms’ classification should be updated in HMS. Rooms 109, 110 and 111 should be removed from the room listing – //Need to update the count of rooms also (subtract deleted rooms from rooms available) | Bug | Ayana | Open | 2 | 2021-02-01
14 | DashBoard | Change Room availability to Green colour for all categories in Home screen | New Requirement | Ayana | Open | 1 | 2021-02-01
15 | Posting | On check-out time, some time transaction added as multiple entry – could be due to multiple mouse clicks | Bug | Ayana | Open | 4 | 2021-02-01
16 | Reception | Check-out payment screen. To allow to edit the payment mode // Admin user should be granted this privilege. | New Requirement | Ayana | Open | 16 | 2021-02-01
[5 empty] | TOTAL | 112