Project Closure Report - Profield Chat v1

Document Issue Status

| Document ID: |  | Document Issue No: Document Revision No: |  |
| --- | --- | --- | --- |
| Prepared by: | Suraj P | Prepared Date: | 24-Apr-2019 |
| Reviewed by: |  | Reviewed Date: |  |
| Approved by: |  | Approved Date: |  |
| Distribution list |  |  |  |

Document Amendment Record

| Sl. No. | Issue No. | Revision No. | Approved Date | Pages Modified | Remarks (Modifications) |
| --- | --- | --- | --- | --- | --- |

Contents

1.	Project Overview	4

1.1	Brief Description	4

1.2	Project Summary	4

1.3	Main Stakeholders	4

2.	Project Performance	5

2.1	Project Schedule Performance	5

3.	Milestone & Deliverable Performance	5

4.	Defects Reported	5

5.	Best Practices	5

6.	Lessons Learned	5

7.	Risk Management	6

8.	Maintenance	6

9.	Conclusion	6

10.	Appendices	6

# Project Overview

### Brief Description

Profield Chat is an online system created for The Profield Corporation, Japan, for people to interact, and exchange files with one another on the Internet. The system can be installed on the company’s own secure servers, helps to keep the chat data completely secure and private. The chat interactions are not allowed to the public.

This system includes three modules:

Admin Module (Administrator level): An Admin Module enables only the administrator to log in to it and manage the users in the chat application. He can create, edit, remove the users or delete the messages of an individual chat user.

Web app (User level): A responsive web application which will allow user to register and interact with other registered users in the chat application. Users can do individual and groups chat, text and voice chat, voice to text (Japanese) and send attachments.

IOS app (User level): A native IOS application which has all the features of a web application. The IOS app personalize the app for a user, which will help the users to keep chat app easily accessible by avoiding the login screen each time we access the app.

### Project Summary

| PROJECT CODE |  |
| --- | --- |
| PROJECT NAME | Profield Chat |
| START DATE | 01-Sep-2018 |
| END DATE | 31-Mar-2019 |
| TEAM SIZE | 7 |

### Main Stakeholders

| ROLE | NAME | EMAIL |
| --- | --- | --- |
| Customer Contact Person | HIROSHI UENO | hiroshi_u@profield.jp |
| Project Manager | Mohandas P M | mohandas@indocosmo.com |
| Project Lead | SURAJ PRABHAKARAN | suraj.prabhakaran@indocosmo.com |
| QC Manager | SAM | sam@indocosmo.com |

# Project Performance

### Project Schedule Performance

| Planned Start Date | 01-Sep-2018 |
| --- | --- |
| Planned End Date | 28-Feb-2019 |
| Actual Start Date | 01-Sep-2018 |
| Actual End Date | 31-Mar-2019 |

# Milestone & Deliverable Performance

| # | Deliverable | Planned Target Date | Actual Delivery Date | Delay in Days | Total Defects Reported | No. of Major Defects |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Web App | 08-Feb-2019 | Mar 08th 2019 | 20 | 0 | 0 |
| 2 | Web app + Admin + IOS | 22-Feb-2019 | Mar 25th 2019 | 20 | 1 | 0 |
| 3 | Full Release v1.0 | 28-Feb-2019 | Mar 31st 2019 | 20 | 0 | 0 |

# Defects Reported

| Total Bugs Reported (Internal Testing Team) | 124 |
| --- | --- |

# Best Practices

Project Management Tool: Redmine

# Lessons Learned

Plan our strategies that can reduce the risk of key personnel leaving too early in the project.

# Risk Management

| Risk Occurred | Risk Severity (L:Low, M:Medium, H:High) | Mitigation action or Contingency actions taken | Effectiveness of action taken |
| --- | --- | --- | --- |
| Only developer left in the middle of the project | High | Tried to recruit experienced resource | Resource not available |
|  |  | Then, allocated existing resource | Too less time got for learning, learn while development –Schedule slippage |

# Maintenance

Currently there is no AMC planned for this project.

# Conclusion

Project is in the completion stage.

# Appendices