## ics-hrmis
ICS- HRMIS |  | START | END
2020-07-08
LAST UPDATED ON: 07-Aug-2020
LAST UPDATED BY: Jeswin Chacko P A
Total time estimated : 760(hrs)
SLNo | SUBJECT | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END
1 | Announcement | PROGRESS | Anandpadmanabhan | 56 | 32 | 2020-08-04
2 | Document Upload(Employee CRUD) | PROGRESS | Ayana | 80 | 56 | 2020-07-31
3 | Design Issues | PROGRESS | Ayana/Jeswin/Anandpadmanabhan | 80 | 24 | 2020-08-04
4 | Default Loading in Load Pages |  | Ayana;Jeswin | 64
5 | All Employee in Reports |  | Ayana;Jeswin | 72
6 | Popup for Delete & Cancel |  | Ayana;Jeswin; Anandpadmanabhan | 80
7 | Panel/Tabs Creation(Employee CRUD) |  | Ayana;Jeswin; Anandpadmanabhan | 56
8 | Leave Calculation(avoid holidays) |  | Jeswin | 96
9 | Leave Calculation(calculation of sandwich leaves) |  | Jeswin | 96
10 | Leave Reports |  | Jeswin | 80
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
|  |  |  | 760 | 112