## Index
Document Issue Status
| Document ID |  | Project-Status-Report-Profield-AI-v1
| Document Name |  | Project Status Report
| Latest Version |  | 1
| Created By | Created Date |  | Reviewd By | Reviewed Date |  | Approved By | Approved Date
| Mohandas | 2020-02-20 |  | Davis Sebastian | 2020-01-06 |  | Davis Sebastian | 2020-01-06
Profield AI v1
Project Status Report
www.indocosmo.com | [5 empty] | All rights Reserved

## Feb 3rd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22
1 | Creating system prototype for client approval | Suraj | Completed | 75% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 50% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 50% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 1% | 2% | 3% | 4% | 5% | 6%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%

## Feb 4th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 2% | 4%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 2% | 4%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 2% | 4%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 7% | 8% | 9% | 10% | 11% | 12%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%

## March 1st week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | progress | 6% | 8% | 10% | 12% | 14%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | progress | 6% | 8% | 10% | 12% | 14%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | progress | 6% | 8% | 10% | 12% | 14%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 13% | 14% | 15% | 16% | 17%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%

## March 2nd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | progress | 16% | 18% | 20% | 22% | 24% | 26%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | progress | 16% | 18% | 20% | 22% | 24% | 26%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | progress | 16% | 18% | 20% | 22% | 24% | 26%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 18% | 19% | 20% | 21% | 22% | 23%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%

## March 3rd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | progress | 28% | 30% | 32% | 34% | 36%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | progress | 28% | 30% | 32% | 34% | 36%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | progress | 28% | 30% | 32% | 34% | 36%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 24% | 25% | 26% | 27% | 28%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | progress | 4% | 8% | 12% | 16% | 20%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%

## March 4th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | progress | 38% | 40% | 42% | 44% | 46% | 48%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | progress | 38% | 40% | 42% | 44% | 46% | 48%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | progress | 38% | 40% | 42% | 44% | 46% | 48%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 29% | 30% | 31% | 32% | 33% | 34%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | progress | 24% | 28% | 32 | 36 | 40 | 44
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%

## March 5th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | progress | 50% | 55% | 60% | 65% | 70%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | progress | 50% | 55% | 60% | 65% | 70%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | progress | 50% | 55% | 60% | 65% | 70%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 35% | 36% | 37% | 38% | 39%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | progress | 48% | 52% | 56% | 60% | 64%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%

## April 1st week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | progress | 75% | 80% | 85% | 90%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | progress | 75% | 80% | 85% | 90%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | progress | 75% | 80% | 85% | 90%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 40% | 41% | 42% | 43%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | progress | 68% | 72% | 76% | 80%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0%

## April 2nd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-04-13 | 2020-04-15 | 2020-04-16 | 2020-04-17
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 44% | 45% | 46% | 47%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 85% | 90% | 95% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 0%

## April 3rd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 48% | 49% | 50% | 51% | 52% | 53%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 2% | 4% | 6%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 0% | 0% | 0% | 2% | 4% | 6%

## April 4th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 54% | 55% | 56% | 57% | 58% | 59%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 8% | 10% | 12% | 14% | 16% | 18%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 8% | 10% | 12% | 14% | 16% | 18%

## May 1st week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 60% | 61% | 62% | 63% | 64% | 65%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 20% | 22% | 24% | 26% | 28% | 30%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 20% | 22% | 24% | 26% | 28% | 30%

## May 2nd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 66% | 67% | 68% | 69% | 70%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 32% | 34% | 36% | 38% | 40% | 42%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 32% | 34% | 36% | 38% | 40% | 42%

## May 3rd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 71% | 72% | 73% | 74% | 75% | 76%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 44% | 46% | 48% | 50% | 52% | 54%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 44% | 46% | 48% | 50% | 52% | 54%

## May 4th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 77% | 78% | 79% | 80% | 81% | 82%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 56% | 58% | 60% | 62% | 64% | 66%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 56% | 58% | 60% | 62% | 64% | 66%

## June 1st week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 83% | 84% | 85% | 86% | 87%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 68% | 70% | 72% | 74% | 76%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 68% | 70% | 72% | 74% | 76%

## June 2nd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 88% | 89% | 90% | 91% | 92% | 93%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 0% | 0% | 0% | 0% | 0% | 0%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 78% | 80% | 82% | 83% | 84% | 85%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 78% | 80% | 82% | 83% | 84% | 85%

## June 3rd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 94% | 95% | 96% | 96% | 96%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 5% | 10% | 15% | 20% | 25%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 86% | 87% | 88% | 89% | 90%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 86% | 87% | 88% | 89% | 90%

## June 4th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | progress | 96% | 96% | 96% | 96% | 96% | 96%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | progress | 30% | 35% | 40% | 50% | 55% | 60%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | progress | 91% | 92% | 93% | 94% | 96% | 97%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | progress | 91% | 92% | 93% | 94% | 96% | 97%

## June 5th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | Completed | 96% | 96% | 96% | 100% | 100%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | Completed | progress | 65% | 70% | 75% | 80%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | Completed | completed | 98% | 99% | 100% | 100%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | Completed | completed | 98% | 99% | 100% | 100%

## July 1st week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10
1 | Creating system prototype for client approval | Suraj | Completed | 100% | 100% | 100% | 100% | 100%
2 | Mapping the individual product images | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
3 | Classifying the images into various groups based on color | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
4 | Create additional images for training based on the existing image | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
5 | Preparing Dataset for training | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
6 | Manually plotting the co ordinates of images and creating text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
7 | comma-separated values file or CSV creation of text files | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
8 | Build and train AI model to identify objects in the image inside the block | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
9 | Extract object image, from the Block with its position,price and all other details | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
10 | Text extraction with its location details | Berlin/Blessy | completed | 85% | 87% | 90% | 95% | 100%
11 | Test samples and Evaluate the prediction and adjust the model to increase the accuracy parameters | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%
12 | Overall testing of all features with different cases | Amal/Berlin/Blessy | Completed | 100% | 100% | 100% | 100% | 100%