## Project Effort Estimate
Project Time Estimation
PROJECT TITLE |  | INDYGOIOT |  |  |  | COMPANY NAME | INDOCOSMO
PROJECT LEAD | [5 empty] | DATE
PROJECT MEMBERS |  | ARJUN R K, SHIMITHA, DEEPAK, NITHIN, ANJU |  |  |  | CLIENT
PHASE |  |  |  | DETAILS |  | Q1 |  | Q2
Estimated Hrs
1 | Project Conception and Initiation |  |  | : Knowledge transfer
: Plan Review
- Questionary
2 | Project Definition and Planning |  |  | : Scope and Goal Setting
|  |  |  | : MEAN stack recap |  | 8
|  |  |  | : Work Breakdown Schedule |  | 1
|  |  |  | : Github set up |  | 1
: Communication Plan
: Risk Management
3 | Project Launch & Execution |  |  | : Environment set up |  | 4
|  |  |  | :AWS Configuration |  | 40
|  |  |  | : Git versioning ¦ Branching |  | 1
|  |  |  | : DB Design |  | 24
|  |  |  | - Variable naming strategy |  | 1
|  |  |  | : Login & Registration |  | 24
|  |  |  | JointCompany |  | 120
|  |  |  | Company |  | 20
|  |  |  | Store |  | 129
|  |  |  | Device |  | 216
|  |  |  | DeviceCloud |  | 112
|  |  |  | Language Support |  | 24
4 | Project Performance & Control |  |  | : Checking variable naming |  | 16.125
|  |  |  | : Code quality checking |  | 16.125
|  |  |  | : Code reusability checking |  | 16.125
|  |  |  | : Total rewap |  | 16.125
5 | Other |  |  | - Documentation-Project close |  | 8
|  |  |  | - Weekly meetings |  | 66
|  |  |  | Total |  | 863.5
| Phases | %ge | Total |  | Meeting
| Development |  | 863.5 |  | 30
| Design(Template Design Modification) | 5 | 86 |  | 3
| Testing Documentation | 50 | 322.5 |  | 12
| Unit Testing | 60 | 387 |  | 12
| Integration Testing |  | 240 |  | 9
| User Acceptance Testing |  | 80
| PM | 10 | 197.9
| Buffer | 20 | 395.8
| Total hours |  | 2572.7
________

## ManPower
Human Power
PROJECT TITLE |  | INDYGOIOT |  | COMPANY NAME | INDOCOSMO
PROJECT LEAD |  |  |  | DATE
PROJECT MEMBERS |  |  |  | CLIENT | INDYGO
No | Members | Effort | Detials
1 | Arjun Rk | 100 | Full time
2 | Shimitha | 100 | Full time
3 | Nithin | 40 | 40 % per day
4 | Anju | 40 | Weekly 2 days
5 | Deepak | 50 | 50% per day