## Plan
AI -ML Image Recognition Project
OBJECT Detection based on custom dataset, extract and save into DB |  |  | Estimation |  |  | Final task list by client
|  |  | Time |  | Cost
| Sl. No. | Task | Days | Hours | @1150 INR
PHASE 1 | 1 | Create new images using Augmentation techniques & Dataset preparation | 25 | 200 | 230000 | 230000
| 2 | GUI for getting the Catalog Page image from the user | 5 | 40 | 46000 | Task cancelled by client
| 3 | Setting up Server and Deployment | 12 | 96 | 110400
| 4 | Build and train AI model to identify objects in the image inside the block | 25 | 200 | 230000 | 230000
| 5 | Extract object image, from the Block with its position, size (if model is okay) | 12 | 96 | 110400 | 110400
| 6 | GUI displaying the details and accept any changes in the content, and confirm the extracted details (Web) | 15 | 120 | 138000 | Task cancelled by client
| 7 | Save the extracted details into DB (web Service) | 4 | 32 | 36800
| 8 | Testing with available test samples | 10 | 80 | 92000 | 92000
| 9 | Test and Evaluate the prediction and adjust the model to increase the accuracy parameters | 15 | 120 | 138000 | 138000
| TOTAL - OBJECT DETECTION (MAN DAYS) |  | 87 | 696 |  | 800400
TEXT extraction - Identify and extract text from the image
| Sl. No. | Task | Days | Hours | @1150 INR
| 10 | Extract text in the Block with its position, size(Design and develop ML model) | 10 | 80 | 92000 | 92000
| 11 | Testing with available test samples and tuning in the model | 2 | 16 | 18400 | 18400
| TOTAL - TEXT EXTRACTION (MAN DAYS) |  | 12 | 96 | 110400 | 110400
|  | Task list | Days | Hours | COST INR
|  | OBJECT DETECTION | 87 | 696 | 800400
|  | TEXT EXTRACTION | 12 | 96 | 110400
|  | Total Man Days | 99 | 808 Hours | 9,10,800 INR
|  | TOTAL MAN MONTHS | 4.95