## Project Effort Estimate
Project Time Estimation
PROJECT TITLE |  | REPAIR MANAGEMENT APPLICATION |  |  | COMPANY NAME | INDOCOSMO
PROJECT LEAD |  | DEEPAK DEV |  |  | DATE | 2020-11-03
PROJECT MEMBERS |  | DEEPAK DEV | , UDHAYAN |  | CLIENT | BLACKWHITE
PHASE |  |  |  | DETAILS | Q1 |  | Q2
Estimated Hrs
1 | Project Conception and Initiation |  |  | : Knowledge transfer | 1
|  |  |  | : Plan Review | 2
|  |  |  | - Questionary | 1
2 | Project Definition and Planning |  |  | : Scope and Goal Setting | 1
|  |  |  | : MEAN stack recap | 16
|  |  |  | : Work Breakdown Schedule | 1
|  |  |  | : Github set up | 1
|  |  |  | : Communication Plan | 1
|  |  |  | : Risk Management | 2
3 | Project Launch & Execution |  |  | : Environment set up | 4
|  |  |  | : Git versioning ¦ Branching | 1
|  |  |  | : DB Design | 12
|  |  |  | - Variable naming strategy | 1
|  |  |  | : Login & Registration | 12
|  |  |  | : User module | 28
|  |  |  | :Technition module | 20
|  |  |  | : Admin module | 25
4 | Project Performance & Control |  |  | : Checking variable naming | 8
|  |  |  | : Code quality checking | 2
|  |  |  | : Code reusability checking | 2
|  |  |  | : Total rewap | 4
5 | Project Close |  |  | - Documentation | 8
|  |  |  | - Weekly meetings | 4
|  |  |  | - Report | 4
|  |  |  | Total | 161
| Phases | %ge | Total
| Development | 50 | 161
| Design | 5 | 16.1
| Testing | 30 | 96.6
| Documentation | 10 | 32.2
| PM | 5 | 16.1
| Total hours | 100 | 322