Project Closure Report - Profield Chat v2

Document Issue Status

| Document ID: |  | Document Issue No: Document Revision No: |  |
| --- | --- | --- | --- |
| Prepared by: | Midhun KC | Prepared Date: | 18-May-2020 |
| Reviewed by: |  | Reviewed Date: |  |
| Approved by: |  | Approved Date: |  |
| Distribution list |  |  |  |

Document Amendment Record

| Sl. No. | Issue No. | Revision No. | Approved Date | Pages Modified | Remarks (Modifications) |
| --- | --- | --- | --- | --- | --- |

Contents

1.	Project Overview	4

1.1	Brief Description	4

1.2	Project Summary	4

1.3	Main Stakeholders	4

2.	Project Performance	5

2.1	Project Schedule Performance	5

3.	Milestone & Deliverable Performance	5

4.	Defects Reported	5

5.	Best Practices	5

6.	Lessons Learned	5

7.	Risk Management	6

8.	Maintenance	6

9.	Conclusion	6

10.	Appendices	6

# Project Overview

### Brief Description

Customer support Profield Chat is an online system created for The Profield Corporation, Japan, for  assist customers in making cost effective and correct use of a product.Customers can interact, and exchange files with different kind of product owners on the Internet. The system can be installed on the company’s own secure servers, helps to keep the chat data completely secure and private.The chat interactions are not allowed to the public.

This system includes three modules:

Admin Module(Administrator level): An Admin Module enables only the administrator to log in to it and manage the category,product,product owners and users in the chat application. He can create, edit and delete categories, product, product owner and users, and delete messages from an individual chat user, and delete the chat message under all products.

Web app (User level): A responsive web application which will allow user to register and interact with other registered product owners in the chat application. Users can do  text and voice chat, voice to text (Japanese) and send attachments.

IOS app (User level): A native IOS application which has all the features of a web application. The IOS app personalize the app for a user, which will help the users to keep chat app easily accessible by avoiding the login screen each time we access the app.

### Project Summary

| PROJECT CODE |  |
| --- | --- |
| PROJECT NAME | Profield Chat v2 |
| START DATE | 01-June-2019 |
| END DATE | 30-sep-2019 |
| TEAM SIZE | 7 |

### Main Stakeholders

| ROLE | NAME | EMAIL |
| --- | --- | --- |
| Customer Contact Person | HIROSHI UENO | hiroshi_u@profield.jp |
| Project Manager | Mohandas P M | mohandas@indocosmo.com |
| Project Lead | SURAJ PRABHAKARAN | suraj.prabhakaran@indocosmo.com |
| QC Manager | SAM | sam@indocosmo.com |

# Project Performance

### Project Schedule Performance

| Planned Start Date | 01-June-2019 |
| --- | --- |
| Planned End Date | 19-Sep-2019 |
| Actual Start Date | 01-June-2019 |
| Actual End Date | 30-Sep-2019 |

# Milestone & Deliverable Performance

| # | Deliverable | Planned Target Date | Actual Delivery Date | Delay in Days | Total Defects Reported | No. of Major Defects |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Web App | 13-Aug-2019 | Aug 13th 2019 | 00 | 0 | 0 |
| 2 | Web app + Admin + IOS | 03-Sep-2019 | Sep 14th 2019 | 11 | 1 | 0 |
| 3 | Full Release v2.0 | 19-sep-2019 | Sep 30th 2019 | 10 | 0 | 0 |

# Defects Reported

| Total Bugs Reported (Internal Testing Team) | 124 |
| --- | --- |

# Best Practices

Project Management Tool: Redmine

# Lessons Learned

Support for different types of image, text, and video format on the web and iOS.

# Risk Management

| Risk Occurred | Risk Severity (L:Low, M:Medium, H:High) | Mitigation action or Contingency actions taken | Effectiveness of action taken |
| --- | --- | --- | --- |
| Only developer left in the middle of the project | High | Tried to recruit experienced resource | Resource not available |
|  |  | Then, allocated existing resource | Too less time got for learning, learn while development –Schedule slippage |

# Maintenance

Currently there is no AMC planned for this project.

# Conclusion

Project is in the completion stage.

# Appendices