## Sheet1
Project Work Schedule
Task |  | Assignee | Estimated Start | Estimated Finish | Estimated Work (In Hours)
1 | Creating system prototype for client approval | Renjith | 2018-10-03 | 2018-10-14 | 72
2 | Self user registeration,password change,login/logout | Renjith | 2018-10-15 | 2018-10-22 | 48
3 | Web GUI Design | Hashif | 2018-10-15 | 2018-10-21 | 40
4 | Sending text,voice and attachment messages | Renjith | 2018-12-22 | 2019-01-15 | 163
5 | Sending Voice to text messages | Renjith | 2019-01-29 | 2019-02-01 | 23
6 | Smiley emoji support in chat | Renjith | 2018-08-23 | 2018-08-25 | 17
7 | Manage friend request | Joshy/Midhun | 2019-02-01 | 2019-02-08 | 50
8 | Manage Group | Joshy/Midhun | 2019-02-09 | 2019-02-21 | 79
9 | Show Contact List Panel | Renjith | 2018-10-22 | 2018-10-30 | 59
10 | Contact list Panel - Show Online & Offline status with different color | Renjith | 2018-10-31 | 2018-11-02 | 21
11 | User Self deregistration | Joshy | 2019-02-22 | 2019-02-23 | 12
12 | Deletion of the messages | Joshy | 2019-02-23 | 2019-02-26 | 15
13 | Re registeration of user | Joshy | 2019-02-26 | 2019-03-04 | 40
14 | Reply messages | Joshy/Midhun | 2019-12-02 | 2020-01-03 | 96
15 | Admin panel : User creation/deletion/updation/listing/meaage deletion | Nayana | 2019-02-11 | 2019-02-19 | 59
16 | Implement WebSocket Server for iOS client communication | Renjith/Gibin | 2018-01-16 | 2018-01-22 | 36
17 | API for iOS | Gibin/Gana/Renjith | 2019-02-20 | 2019-03-01 | 67
18 | iOS functionality | Lithin | 2019-02-04 | 2019-03-30 | 345
19 | Application testing and bug fixing | Joshy/Midhun/Gana | 2019-03-13 | 2019-03-30 | 120