## Jan 2021
Date | Resource | Tasks | Hours
2021-01-01 | Udhayan | Completed UpdateUser Module-3.5 hrs Completed DeleteUser Module - 2 hrs Discussion with Savan and Team- 0.5 hr Email verification for the user- (in progress) -1.5 hrs | 8.25
| Deepak | 1. Weekly meeting call with Savan , Sony ,Udhayan , Santhosh = 20min 2. Project background discussion with Santhosh ,Sony =10 min 3. Server deployment and checking of the latest push =30 min | 1
| Sony | 1. Weekly meeting call with Savan , Sony ,Udhayan , Santhosh = 20min | 0.2
| Sumer | 1. Weekly meeting call with Savan , Sony ,Udhayan , Santhosh = 20min | 0.2
| Santhosh | 1. Weekly meeting call with Savan , Sony ,Udhayan , Santhosh = 20min | 0.2
2021-01-02 | Udhayan | Discussion with Savan and Team- 2 hrs Creating MOM - 0.5 hr Analysing the Changes in the existing user flow -1.5 hrs | 8
| Deepak | 1. Code review and project discussion with Savan = 2Hrs | 2
| Sony | project discussion with Savan | 2
| Sumer | project discussion with Savan | 2
| Santhosh | project discussion with Savan | 2
2021-01-04 | Udhayan | As per new table design, registration Module modification (completed) -4hrs login module modification (completed)-2hrs update user module(in progress)-2 hrs | 8
| Deepak | 1. Call with savan san for Front end design and GDPR issue :15min 2. GDPR Rule exploration =45mins | 1
2021-01-05 | Udhayan | Update user module(in progress)-2 hrs | 8
| Deepak | 1. Started to prepare Unit testing methodes in RMS application | 1
2021-01-06 | Udhayan | Add Phone number API- 2hrs Add Address API- 3hrs Add Email API- 2.5hrs | 8
| Deepak | 1. Discussion with savan about the form validations and front end design = 30min 2. RMS front end design implimentating into wireframe , exploring wireframe tools 3. Test cases preparation using karama | 3
2021-01-07 | Udhayan | Completed the follwing test case: Registration with Email-2 hrs Registration with Phone -2hrs Login-1.5hrs Add User Email-1.5hrs | 7
| Deepak | 1. Test cases preparation using karma | 4
2021-01-08 | Udhayan | Completed the follwing test case: Made Correction in existing test case -2.5 hrs Add user Phone - 1.5 hrs Add user Address -2 hrs Update User (Inprogress)-1 hr | 8
2021-01-09 | Udhayan | Completed the follwing test case: Update User -3 hrs Code modification based on test cases-3 hrs Analysis the Node logging for tracking the issues -2 hrs | 8
2021-01-11 | Udhayan | Absent | 0
| Deepak | 1. Exploring testing unit testing | 1
2021-01-12 | Udhayan | Code modification based on test cases- 4 hrs Analysis the Node logging for tracking the issues -3.5 hrs | 7.5
| Deepak | 1. Exploring testing unit testing | 1
|  | Total | 91.35
|  | Total work hours by Udhayan | 70.75 | Hrs
|  | Total work hours by Deepak | 14 | Hrs
|  | Total work hours by Sony | 2.2 | Hrs
|  | Total work hours by Sumer | 2.2 | Hrs
|  | Total work hours by Santhosh | 2.2 | Hrs

## Dec 2020
Date | Resource | Tasks | Hours
2020-12-01 | Udhayan | develop and insert some additional table | 7.5
| Deepak | Discussion with Sony sir ¦ Udayan | 0.5
| Sony | Discussion with Deepak ¦ Udayan | 0.5
2020-12-02 | Udhayan | Continue the development | 2
2020-12-03 | Udhayan | Discussion with Sumayar Gupta San, Had a weekly status call with Savan and Team and Started creating the the Requirement specification document | 7.5
2020-12-04 | Udhayan | Discussion with Sumayar Gupta San, and finished creating the the Requirement specification document | 8.5
2020-12-07 | Udhayan | MongoDb with node coneection | 8
2020-12-08 | Udhayan | Done User module with Email verification and had dicussion with Savaan and Team | 8
2020-12-09 | Udhayan | Create the mock user story for registration and login in user module | 5
2020-12-10 | Udhayan | Create Social Login Request and response Document and sent it to Savan ,Refresh the node skills | 7.5
| Deepak | Magento API documentation | 3
| Sumer | Whatsapp call | 0.2
2020-12-11 | Udhayan | Discussion with Sumayar Gupta San, and creating the MOM and also had discussion with Savan discussed the new table design | 8
| Sumer | whatsapp call | 0.2
| Deepak | Discussion with Savan ¦ Udayan for Db design of user module ¦ Magento APIs documentation | 4
2020-12-12 | Udhayan | Creating minutes ogf meeting doc and creating fucntionality document | 8
| Deepak | Flowchart ¦ Discussion notes ¦ Fuctions documentation | 4
2020-12-14 | Udhayan | Creating minutes ogf meeting doc and creating fucntionality document and had discussion with savan regarding table design | 7
| Deepak | Preparing for deployment server ¦ Registration module design started | 4
| Sumer | whatsapp call | 0.4
2020-12-15 | Udhayan | Today Activities: 1.Done some patch works for previous version of RMS-6.5 hrs 2.Had a discussion with Savan regarding table design-1.5 hrs | 8
| Deepak | Discussed with savan and confirmed the use MEAN stack. Redesigned Profile page ¦ Added lazy module | 4
2020-12-16 | Udhayan | Restart the user module: validate the registration feilds -2 hrs get the registration details and send to services-1 hr service will process data and transfer to server side through http client -1 hr Set the diffeent layout for header for different component-2hrs Get the details from client and process data-1.5 hrs | 7.5
| Deepak | Profile Design redeveloped ¦ Registration design redeveloped | 4
2020-12-17 | Udhayan | Restart the user module: Done the user registration module server side -6 hrs Had a discussion with Savan and Creare Minutes of Meeting Document for the same 1 hr | 7
| Deepak | Profile Design redeveloped ¦ Registration design redeveloped ¦ Disucssion with savan | 4
2020-12-18 | Udhayan | Today Activities: 1.Done some Frent end code modification for registration-1.5 2.Modify the Registration module code as per savan Requirement-5 | 6.5
2020-12-21 | Udhayan | On Leave | 0
| Deepak | API creation on going for user module ¦ discussion with savan ¦ Discussion with Sumer | 3
2020-12-22 | Udhayan | Avthentication Development- 6.5 hr Meeting With New Project Manager-1.5 hr | 8
| Deepak | Usermodule API flow chart completed | 1
2020-12-23 | Udhayan | Login Developemnt | 8
2020-12-24 | Udhayan | Regisration testing and rectify the result | 6
| Deepak | Crude functions for user module ¦ Login API error resolving ¦ Sequalize plugin exploration | 8
2020-12-26 | Udhayan | Regisration testing and rectify the result completed | 8
| Deepak | Completed Registration API ¦ Sequalize seeding ¦ Session handling ¦ Token generation | 8
2020-12-28 | Udhayan | On Leave | 0
2020-12-29 | Udhayan | Regisration test-2hrs Login Test -1 hr server deployment - 1hr error fixing -3.5hrs | 7.5
2020-12-30 | Udhayan | getAllUserFunction-7.5 | 7.5
2020-12-31 | Udhayan | getAllUserFunction-(completed)-2.5hrs, updateUsers(in-progress)-5hrs. | 7.5
|  | Total Hours | 207.3
|  | Total hours by Udhayan | 156.5
|  | Total hours by Deepak | 46.5
|  | Total hours by Sony | 2
|  | Total hours by Sumer | 1.5