## Tasks
Chat v1 Estimate
Module / Sub module | Estimation
| TIME (Hours) |  | COST (INR)
| Web App | iOS App | Web App | iOS App
Standard Per Hour Rate (Currency INR) |  |  | 1150
Misc. Works
R&D (WebSocket communication, Voice to Text Conversion, iOS push messaging, Voice message saving sending etc…) | 28 | 20 | 32200 | 23000
Graphics Design | 60 |  | 69000 | 0
Admin Module (WEB) |  |  | 0 | 0
Create a user & notify user through email | 31 |  | 35650 | 0
Change Password & send password changed email to user | 12 |  | 13800 | 0
Delete(logically)/Deactivate a user | 16 |  | 18400 | 0
Create Group by Admin | 15 |  | 17250 | 0
Delete Group by Admin | 11 |  | 12650 | 0
Add a User into Group, updates user's contact list and notifies through chat | 26 |  | 29900 | 0
Remove a user from Group, updates user's contact list and notifies through chat | 21 |  | 24150 | 0
Assign/Remove Group Admin right for a User | 16 |  | 18400 | 0
Delete Message individually/ of a Group/User | 13 |  | 14950 | 0
User Modules |  |  | 0 | 0
Self Service User Registration - with Email, userid, password & Upload photo is optional | 18 | 24 | 20700 | 27600
Self Service User Delete | 12 | 8 | 13800 | 9200
Self service Change Password | 8 | 12 | 9200 | 13800
Edit Profile photo | 6 | 6 | 6900 | 6900
User login/logout | 22 | 16 | 25300 | 18400
Create Group, creator becomes the Owner & Permanent Group Admin | 16 | 8 | 18400 | 9200
Delete Group (if User is a Owner) | 11 | 7 | 12650 | 8050
Invite a User for joining into Group (if assignee is a Group Admin) | 15 | 17 | 17250 | 19550
Remove a user from Group (if assignee is a Group Admin) | 12 | 10 | 13800 | 11500
Assign/Remove Group Admin right for a User (if assignor User is a Group Admin) | 10 | 8 | 11500 | 9200
Send and Receive Text message to individual users | 32 | 17 | 36800 | 19550
Convert Voice and Show as Text | 23 | 18 | 26450 | 20700
Send and Receive Group messaging (text) | 20 | 17 | 23000 | 19550
Delete Message by Sender/ Group Owner/ Group Admin | 15 | 15 | 17250 | 17250
Send and Receive audio message to individual & group | 59 | 23 | 67850 | 26450
Show the audio message to the individual receiver/group | 26 | 24 | 29900 | 27600
Request to add a User into Contact list | 26 | 15 | 29900 | 17250
Accept or Reject Contact request | 24 | 24 | 27600 | 27600
Show Contact list sorted based on recent messages on top | 33 | 25 | 37950 | 28750
Show online or offline status of the user in the contact list | 21 | 10 | 24150 | 11500
Image/Documents send to the individual or group chat | 26 | 15 | 29900 | 17250
Smiley emoji support in chat | 17 | 6 | 19550 | 6900
T O T A L | 701 | 345 | 806150 | 396750
| 1046 Hours |  | 12,02,900 INR