## Version 1.0
Slno | Project | EPIC | Feature | Task | Duration (Hrs) | Resource Name | Start Date | End Date | Status | Risks | Mitigation | Notes
1 | HRMIS | Redesign | User Login | Centralise the login pop up | 1 | Eldhose Scaria |  |  | Pending
2 | HRMIS | Redesign | User Login | Move forgot password to first box as a link | 1 | Eldhose Scaria |  |  | Pending
3 | HRMIS | Redesign | User Login | Change placeholder text as USER NAME/EMPLOYEE ID and PASSWORD | 1 | Eldhose Scaria |  |  | Pending
4 | HRMIS | Redesign | User Login | Forgot password popup | 6 | Eldhose Scaria |  |  | Pending
5 | HRMIS | Redesign | Dashboard - Common | Make a top pannel | 2 | Eldhose Scaria |  |  | Pending
6 | HRMIS | Redesign | Dashboard - Common | Move User Details, Change Password, and Sign out to Top Pannel | 2 | Eldhose Scaria |  |  | Pending
7 | HRMIS | Redesign | Dashboard - Common | Include User profile picture in the top pannel | 4 | Eldhose Scaria |  |  | Pending
8 | HRMIS | Redesign | Dashboard - Common | Add down carot and list sign out and change password as drop down | 4 | Eldhose Scaria |  |  | Pending
9 | HRMIS | Redesign | Dashboard - Common | Make a time stamp in top bar and when it click a popup calendar opens | 8 | Eldhose Scaria |  |  | Pending
10 | HRMIS | Redesign | Dashboard - Common | Calendar redesign with Present or Absent marking in days and company holidays | 8 | Eldhose Scaria |  |  | Pending
11 | HRMIS | Redesign | Dashboard - Common | Notification button in top bar with number of notifications highlighted | 4 | Eldhose Scaria |  |  | Pending
12 | HRMIS | Redesign | Dashboard - Common | Notification dropdown and popup | 4 | Eldhose Scaria |  |  | Pending
13 | HRMIS | Redesign | Dashboard - Common | Move Leave allocation from Lookup Table to Main Menu second position | 1 | Eldhose Scaria |  |  | Pending
14 | HRMIS | Redesign | Dashboard - Common | Add a common Copyright line in bottom position of Main menu strip - Left | 3 | Eldhose Scaria |  |  | Pending
15 | HRMIS | Redesign | Common Inner page style issues | Add page name in page header | 2 | Eldhose Scaria |  |  | Pending
16 | HRMIS | Redesign | Common Inner page style issues | Alignment correction of borders, buttons, and search | 3 | Eldhose Scaria |  |  | Pending
17 | HRMIS | Redesign | Common Inner page style issues | Change button styling and alignment | 3 | Eldhose Scaria |  |  | Pending
18 | HRMIS | Redesign | Common Inner page style issues | Change Button name Delete to Hide and Remove Reset Button | 4 | Eldhose Scaria |  |  | Pending
19 | HRMIS | Redesign | Common Inner page style issues | Add a Notification popup for the successful updation of Add, Delete, Hide, and all the Updations | 8 | Eldhose Scaria |  |  | Pending
20 | HRMIS | Redesign | Common Inner page style issues | Add Cancel Button in each page | 2 | Eldhose Scaria |  |  | Pending
21 | HRMIS | Redesign | Common Inner page style issues | Remove copyright line page contents | 1 | Eldhose Scaria |  |  | Pending
22 | HRMIS | Redesign | Menu - Employees | Make TAB view for the three sections - Employee details, Project, and Approver | 16 | Eldhose Scaria |  |  | Pending
23 | HRMIS | Redesign | Menu - Employees | Make add/edit Employee popup | 8 | Eldhose Scaria |  |  | Pending
24 | HRMIS | Redesign | Menu - Employees | Make add/edit Project popup | 8 | Eldhose Scaria |  |  | Pending
25 | HRMIS | Redesign | Menu - Employees | Make add/edit Approver popup | 8 | Eldhose Scaria |  |  | Pending
26 | HRMIS | Redesign | Menu - Employees | Add prrint button for employee list | 4 | Eldhose Scaria |  |  | Pending
27 | HRMIS | Redesign | Menu - Employees | Common Style issues | 4 | Eldhose Scaria |  |  | Pending
28 | HRMIS | Redesign | Menu - Lookup table - Designation | Make add/edit Designation popup | 8 | Eldhose Scaria |  |  | Pending
29 | HRMIS | Redesign | Menu - Lookup table - Designation | Remove Reset button from sub page(popup) | 2 | Eldhose Scaria |  |  | Pending
30 | HRMIS | Redesign | Menu - Lookup table - Designation | Common Style issues | 4 | Eldhose Scaria |  |  | Pending
31 | HRMIS | Redesign | Menu - Lookup table - Location | Common Style issues | 4 | Eldhose Scaria |  |  | Pending
32 | HRMIS | Redesign | Menu - Lookup table - Location | Add location and Edit location popup | 16 | Eldhose Scaria |  |  | Pending
33 | HRMIS | Redesign | Menu - Lookup table - Location | Remove Reset button from sub page(popup) | 2 | Eldhose Scaria |  |  | Pending
34 | HRMIS | Redesign | Menu - Lookup table - Client | Add and Edit Client popup | 16 | Eldhose Scaria |  |  | Pending
35 | HRMIS | Redesign | Menu - Lookup table - Client | Common Style issues | 4 | Eldhose Scaria |  |  | Pending
36 | HRMIS | Redesign | Menu - Lookup table - Client | Remove Reset button from sub page(popup) | 2 | Eldhose Scaria |  |  | Pending
37 | HRMIS | Redesign | Menu - Lookup table - Client | Add TAB for Project and Project Manager in Client Edit page | 16 | Eldhose Scaria |  |  | Pending
38 | HRMIS | Redesign | Menu - Lookup table - Holiday | Make Popup for Edit, Import and Add Holiday | 12 | Eldhose Scaria |  |  | Pending
39 | HRMIS | Redesign | Menu - Lookup table - Holiday | Common Style issues | 4 | Eldhose Scaria |  |  | Pending
40 | HRMIS | Redesign | Menu - Lookup table - Announcements | Make Popup for Add Announcement | 12 | Eldhose Scaria |  |  | Pending
41 | HRMIS | Redesign | Menu - Lookup table - Announcements | Common Style issues | 4 | Eldhose Scaria |  |  | Pending
42 | HRMIS | Redesign | Menu - Lookup table - Announcements | Clolumn size correction | 4 | Eldhose Scaria |  |  | Pending
43 | HRMIS | Redesign | Menu - Lookup table - Announcements | Button sizing | 2 | Eldhose Scaria |  |  | Pending
44 | HRMIS | Redesign | Menu - Lookup table - Announcements | Send mail tag name should change to Compose and re structure the template | 4 | Eldhose Scaria |  |  | Pending
45 | HRMIS | Redesign | Menu - Lookup table - Leave type | Change the menu name as LEAVE STRUCTURE | 2 | Eldhose Scaria |  |  | Pending
46 | HRMIS | Redesign | Menu - Lookup table - Leave type | Common Style issues | 8 | Eldhose Scaria |  |  | Pending
47 | HRMIS | Redesign | Menu - Lookup table - Leave type | Make Add Leave Structure in a popup | 4 | Eldhose Scaria |  |  | Pending
48 | HRMIS | Redesign | Leave Allocation | Move Leave Allocation from Lookup Table to main menu as in the second position under Employee | 8 | Eldhose Scaria |  |  | Pending
49 | HRMIS | Redesign | Leave Allocation | Beautify the Table and stylize the columns and make it as a popup | 8 | Eldhose Scaria |  |  | Pending
50 | HRMIS | Redesign | Leave Allocation | Common style issues | 4 | Eldhose Scaria |  |  | Pending
51 | HRMIS | Redesign | Project History | Common style issues | 4 | Eldhose Scaria |  |  | Pending
52 | HRMIS | Redesign | Project History | Include Print Button | 4 | Eldhose Scaria |  |  | Pending
53 | HRMIS | Redesign | Leave Reports | Common style issues | 4 | Eldhose Scaria |  |  | Pending
54 | HRMIS | Redesign | Leave Reports | Include Print Button | 4 | Eldhose Scaria |  |  | Pending
55 | HRMIS | Redesign | Leave Reports | Beautify form content | 4 | Eldhose Scaria |  |  | Pending
56 | HRMIS | Redesign | Work Reports | Common style issues | 4 | Eldhose Scaria |  |  | Pending
57 | HRMIS | Redesign | Work Reports | Include Print Button | 4 | Eldhose Scaria |  |  | Pending
58 | HRMIS | Redesign | Work Reports | Load button open in a popup | 4 | Eldhose Scaria |  |  | Pending
59 | HRMIS | Redesign | Work Reports | Add Work Upload should open in a popup | 4 | Eldhose Scaria |  |  | Pending
60 | HRMIS | Redesign | HR Login | HR Dash Board in TAB view | 8 | Eldhose Scaria |  |  | Pending
61 | HRMIS | Redesign | Personal Information | Make TAB view in personal information | 8 | Eldhose Scaria |  |  | Pending
62 | HRMIS | Redesign | Apply Leave | Beautify Form and remove Get available leave button | 8 | Eldhose Scaria |  |  | Pending
63 | HRMIS | Redesign | Leave History | Include File upload button for medical certificate upload | 8 | Eldhose Scaria |  |  | Pending
64 | HRMIS | Redesign | Employee Log in | Make Employee dashboard in TAB view | 8 | Eldhose Scaria |  |  | Pending
|  |  |  | Total | 277 | 35 Days
Pending

## Sample
Slno | Project | EPIC | Feature | Task | Duration (Hrs) | Resource Name | Start Date | End Date | Status | Risks | Mitigation | Notes
1 | Init Dine | KOT Printing | Printing Setup | Design the Printing format | 5 | Person1 | 2020-08-11 | 2020-08-11 | WIP | Printer device not available | Need to take the help of system admin
|  |  |  | Allign the data | 2 | Person2
|  |  | Item Aknowledge | Validation in the coding | 8 | Person3
|  |  |  | Database communication | 4 | Person1
Barcode Generation