## Index
Document Issue Status
| Document ID |  | Project-Status-Report-Profield-Chat-v1
| Document Name |  | Project Status Report
| Latest Version |  | 1
| Created By | Creatred Date |  | Reviewd By | Reviewed Date |  | Approved By | Approved Date
| Mohandas | 2019-12-01 |  | Davis Sebastian | 2020-01-06 |  | Davis Sebastian | 2020-01-06
Profield Chat v1
Project Status Report
www.indocosmo.com | [5 empty] | All rights Reserved

## Dec 1st week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2019-12-02 | 2019-12-03 | 2019-12-04 | 0 | 2019-12-06
1 | Creating system prototype for client approval | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
2 | Self user registeration,password change,login/logout | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
3 | Web GUI Design | Hashif | Completed | 100% | 100% | 100% | 100% | 100%
4 | Sending text,voice and attachment messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
5 | Sending Voice to text messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
6 | Smiley emoji support in chat | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
7 | Manage friend request | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100%
8 | Manage Group | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100%
9 | Show Contact List Panel | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
10 | Contact list Panel - Show Online & Offline status with different color | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
11 | User Self deregistration | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
12 | Deletion of the messages | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
13 | Re registeration of user | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
14 | Admin panel : User creation/deletion/ updation/ listing/ meaage deletion | Nayana | Completed | 100% | 100% | 100% | 100% | 100%
15 | Implement WebSocket Server for iOS client communication | Renjith/Gibin | Completed | 100% | 100% | 100% | 100% | 100%
16 | API for iOS | Gibin/Gana/Renjith | Completed | 100% | 100% | 100% | 100% | 100%
17 | iOS functionality | Lithin | Completed | 100% | 100% | 100% | 100% | 100%
18 | Reply messages web side-gui functionalities | Midhun | progress | 20% | 20% | 30% | 40% | 50%
19 | Reply message IOS development | lithin | progress | 8% | 12% | 16% | 20% | 24%
20 | Reply messages web side-server side development | Joshy | progress | 10% | 15% | 20% | 25% | 30%
21 | Reply messages delete gui development | Midhun | progress
22 | Reply messages delete server side development | joshy | progress
23 | Reply message API development | Joshy/Midhun/Gana/lithin | progress
24 | Application testing and bug fixing | Joshy/Midhun/Gana/lithin | progress

## Dec 2nd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14
1 | Creating system prototype for client approval | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Self user registeration,password change,login/logout | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Web GUI Design | Hashif | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Sending text,voice and attachment messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Sending Voice to text messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Smiley emoji support in chat | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | Manage friend request | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Manage Group | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100% | 100%
9 | Show Contact List Panel | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Contact list Panel - Show Online & Offline status with different color | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
11 | User Self deregistration | Joshy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
12 | Deletion of the messages | Joshy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
13 | Re registeration of user | Joshy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
14 | Admin panel : User creation/deletion/ updation/ listing/ meaage deletion | Nayana | Completed | 100% | 100% | 100% | 100% | 100% | 100%
15 | Implement WebSocket Server for iOS client communication | Renjith/Gibin | Completed | 100% | 100% | 100% | 100% | 100% | 100%
16 | API for iOS | Gibin/Gana/Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
17 | iOS functionality | Lithin | Completed | 100% | 100% | 100% | 100% | 100% | 100%
18 | Reply messages web side-gui functionalities | Midhun | progress | 60% | 70% | 80% | 90% | 99% | 99%
19 | Reply message IOS development | lithin | progress | 28% | 32% | 36% | 40% | 44% | 48%
20 | Reply messages web side-server side development | Joshy | progress | 35% | 40% | 45% | 50% | 55% | 60%
21 | Reply messages delete gui development | Midhun | progress | [5 empty] | 10%
22 | Reply messages delete server side development | joshy | progress
23 | Reply message API development | Joshy/Midhun/Gana/lithin | progress
24 | Application testing and bug fixing | Joshy/Midhun/Gana/lithin | progress

## Dec 3rd week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20
1 | Creating system prototype for client approval | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
2 | Self user registeration,password change,login/logout | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
3 | Web GUI Design | Hashif | Completed | 100% | 100% | 100% | 100% | 100%
4 | Sending text,voice and attachment messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
5 | Sending Voice to text messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
6 | Smiley emoji support in chat | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
7 | Manage friend request | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100%
8 | Manage Group | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100%
9 | Show Contact List Panel | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
10 | Contact list Panel - Show Online & Offline status with different color | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
11 | User Self deregistration | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
12 | Deletion of the messages | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
13 | Re registeration of user | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
14 | Admin panel : User creation/deletion/ updation/ listing/ meaage deletion | Nayana | Completed | 100% | 100% | 100% | 100% | 100%
15 | Implement WebSocket Server for iOS client communication | Renjith/Gibin | Completed | 100% | 100% | 100% | 100% | 100%
16 | API for iOS | Gibin/Gana/Renjith | Completed | 100% | 100% | 100% | 100% | 100%
17 | iOS functionality | Lithin | Completed | 100% | 100% | 100% | 100% | 100%
18 | Reply messages web side-gui functionalities | Midhun | progress | 99% | 99% | 99% | 99% | 99%
19 | Reply message IOS development | lithin | progress | 52% | 54% | 58% | 62% | 66%
20 | Reply messages web side-server side development | Joshy | progress | 65% | 70% | 75% | 80% | 85%
21 | Reply messages delete gui development | Midhun | progress | 20% | 30% | 40% | 50% | 60%
22 | Reply messages delete server side development | joshy | progress
23 | Reply message API development | Joshy/Midhun/Gana/lithin | progress
24 | Application testing and bug fixing | Joshy/Midhun/Gana/lithin | progress

## Dec 4th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28
1 | Creating system prototype for client approval | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
2 | Self user registeration,password change,login/logout | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
3 | Web GUI Design | Hashif | Completed | 100% | 100% | 100% | 100% | 100% | 100%
4 | Sending text,voice and attachment messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
5 | Sending Voice to text messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
6 | Smiley emoji support in chat | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
7 | Manage friend request | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100% | 100%
8 | Manage Group | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100% | 100%
9 | Show Contact List Panel | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
10 | Contact list Panel - Show Online & Offline status with different color | Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
11 | User Self deregistration | Joshy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
12 | Deletion of the messages | Joshy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
13 | Re registeration of user | Joshy | Completed | 100% | 100% | 100% | 100% | 100% | 100%
14 | Admin panel : User creation/deletion/ updation/ listing/ meaage deletion | Nayana | Completed | 100% | 100% | 100% | 100% | 100% | 100%
15 | Implement WebSocket Server for iOS client communication | Renjith/Gibin | Completed | 100% | 100% | 100% | 100% | 100% | 100%
16 | API for iOS | Gibin/Gana/Renjith | Completed | 100% | 100% | 100% | 100% | 100% | 100%
17 | iOS functionality | Lithin | Completed | 100% | 100% | 100% | 100% | 100% | 100%
18 | Reply messages web side-gui functionalities | Midhun | progress | 99% | 99% | 99% | 99% | 99% | 99%
19 | Reply message IOS development | lithin | progress | 70% | 74% | 78% | 82% | 86% | 90%
20 | Reply messages web side-server side development | Joshy | progress | 90% | 95% | 99% | 99% | 99% | 99%
21 | Reply messages delete gui development | Midhun | progress | 70% | 80% | 99% | 99% | 99% | 99%
22 | Reply messages delete server side development | joshy | progress |  |  |  | 25% | 55% | 99%
23 | Reply message API development | Joshy/Midhun/Gana/lithin | progress |  |  |  | 8% | 16% | 24%
24 | Application testing and bug fixing | Joshy/Midhun/Gana/lithin | progress

## Dec 5th week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03
1 | Creating system prototype for client approval | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
2 | Self user registeration,password change,login/logout | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
3 | Web GUI Design | Hashif | Completed | 100% | 100% | 100% | 100% | 100%
4 | Sending text,voice and attachment messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
5 | Sending Voice to text messages | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
6 | Smiley emoji support in chat | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
7 | Manage friend request | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100%
8 | Manage Group | Joshy/Midhun | Completed | 100% | 100% | 100% | 100% | 100%
9 | Show Contact List Panel | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
10 | Contact list Panel - Show Online & Offline status with different color | Renjith | Completed | 100% | 100% | 100% | 100% | 100%
11 | User Self deregistration | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
12 | Deletion of the messages | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
13 | Re registeration of user | Joshy | Completed | 100% | 100% | 100% | 100% | 100%
14 | Admin panel : User creation/deletion/ updation/ listing/ meaage deletion | Nayana | Completed | 100% | 100% | 100% | 100% | 100%
15 | Implement WebSocket Server for iOS client communication | Renjith/Gibin | Completed | 100% | 100% | 100% | 100% | 100%
16 | API for iOS | Gibin/Gana/Renjith | Completed | 100% | 100% | 100% | 100% | 100%
17 | iOS functionality | Lithin | Completed | 100% | 100% | 100% | 100% | 100%
18 | Reply messages web side-gui functionalities | Midhun | progress | 99% | 99% | 99% | 99% | 99%
19 | Reply message IOS development | lithin | progress | 94% | 98% | 99% | 99% | 99%
20 | Reply messages web side-server side development | Joshy | progress | 99% | 99% | 99% | 99% | 99%
21 | Reply messages delete gui development | Midhun | progress | 99% | 99% | 99% | 99% | 99%
22 | Reply messages delete server side development | joshy | progress | 99% | 99% | 99% | 99% | 99%
23 | Reply message API development | Joshy/Midhun/Gana/lithin | progress | 56% | 72% | 88% | 99% | 99%
24 | Application testing and bug fixing | Joshy/Midhun/Gana/lithin | progress |  |  | 5% | 30% | 70%

## Jan 1st week
Project Status Report
Sl.No | Assigned Works | Assignee | Status | 2020-01-05 | 2020-01-06
1 | Creating system prototype for client approval | Renjith | Completed | 100% | 100%
2 | Self user registeration,password change,login/logout | Renjith | Completed | 100% | 100%
3 | Web GUI Design | Hashif | Completed | 100% | 100%
4 | Sending text,voice and attachment messages | Renjith | Completed | 100% | 100%
5 | Sending Voice to text messages | Renjith | Completed | 100% | 100%
6 | Smiley emoji support in chat | Renjith | Completed | 100% | 100%
7 | Manage friend request | Joshy/Midhun | Completed | 100% | 100%
8 | Manage Group | Joshy/Midhun | Completed | 100% | 100%
9 | Show Contact List Panel | Renjith | Completed | 100% | 100%
10 | Contact list Panel - Show Online & Offline status with different color | Renjith | Completed | 100% | 100%
11 | User Self deregistration | Joshy | Completed | 100% | 100%
12 | Deletion of the messages | Joshy | Completed | 100% | 100%
13 | Re registeration of user | Joshy | Completed | 100% | 100%
14 | Admin panel : User creation/deletion/ updation/ listing/ meaage deletion | Nayana | Completed | 100% | 100%
15 | Implement WebSocket Server for iOS client communication | Renjith/Gibin | Completed | 100% | 100%
16 | API for iOS | Gibin/Gana/Renjith | Completed | 100% | 100%
17 | iOS functionality | Lithin | Completed | 100% | 100%
18 | Reply messages web side-gui functionalities | Midhun | progress | 99% | 100%
19 | Reply message IOS development | lithin | progress | 99% | 100%
20 | Reply messages web side-server side development | Joshy | progress | 99% | 100%
21 | Reply messages delete gui development | Midhun | progress | 99% | 100%
22 | Reply messages delete server side development | joshy | progress | 99% | 100%
23 | Reply message API development | Joshy/Midhun/Gana/lithin | progress | 99% | 100%
24 | Application testing and bug fixing | Joshy/Midhun/Gana/lithin | progress | 99% | 100%