## Project Events
MONTH | DATE | EVENT
2019-10-01 | 2019-10-25 | Proposal
2019-11-01 | 2019-11-01 | Project Estimation Plan - Initial
| 2019-11-29 | SRS Document
| 2019-11-29 | Project Estimation Plan - Revised
2019-12-01 | 2019-12-09 | First Level Prototype - Excel Document
| 2019-12-20 | Client meeting - Design modifications
| 2019-12-28 | UI Design - Theme Color
2020-01-01 | 2020-01-03 | Requested the following details to client through Hirayama San 1. Payment gateway admin access. 2. Mobile SDKs for both iOS and Android platforms. 3. Test Card details to try out the transactions. 4. Locker Device as well to integrate the same with the mobile apps for development along with the documents.
| 2020-01-08 | Project Delivery Plan
| 2020-01-10 | UI Design Prototype - Screen Flow - With different theme color
| 2020-01-15 | Payment Integration document received from Carry Park
| 2020-01-21 | Screen Flow Document 1 - Initial Screen Flow
| 2020-01-28 | Client Confirmation - Theme Color
| 2020-01-29 | Screen Flow Document 2 - Theme Changed
2020-02-01 | 2020-02-04 | UI Design Prototype - Screen Flow (with selected Theme Color)
| 2020-02-06 | Screen Flow Document 3 - Operational Changes
| 2020-02-14 | User Registration development completed - First Level
| 2020-02-24 | Locking & Unlocking development completed - First Level
| 2020-02-26 | Security Implementation - Akira San joined
| 2020-02-26 | Release - Released for UAT with Screen Flow
| 2020-02-26 | Client Meeting - Security Implementation
2020-03-01 | 2020-03-02 | Payment Integration - Communication
| 2020-03-06 | Payment Integration Issues - Invalid API
| 2020-03-12 | Payment Integration - New API received
| 2020-03-16 | Client Meeting - Security Implementation
| 2020-03-17 | Client Meeting - Security Implementation
| 2020-03-20 | Payment Integration development completed - Staging
| 2020-03-21 | Testing the operations using FW version0.20
| 2020-03-24 | Release - Test Flight (User Registration, Locking & Unlocking)
| 2020-03-24 | Client requirement for the following items: 1. Device Location 2. Device status report 3. Battery status 4. Usage & Revenue statistics
| 2020-03-30 | Release - Test Flight (User Registration, Locking, Unlocking & Payment)
2020-04-01 | 2020-04-03 | Create new schedule plan for client requirements
| 2020-04-06 | Release - Test Flight (Modifications after 30-Mar-20 release)
| 2020-04-06 | Screen Flow Document 4 - Changes required by client
| 2020-04-07 | New Schedule document send to client
| 2020-04-15 | Release - Test Flight (Modifications after 06-Apr-20 release)
| 2020-04-16 | Screen Flow Document 5 - Changes required by client
| 2020-04-16 | Received Client requirements about multiple mode payments
| 2020-04-19 | Release - Test Flight (Modifications after 16-Apr-20 release)
| 2020-04-20 | Testing started with FW Version0.31 with BLE app
| 2020-04-21 | Release - Test Flight (Modifications after 19-Apr-20 release)
| 2020-04-22 | Screen Flow Document 6 - Changes required by client
| 2020-04-27 | Security Implementation - Started
| 2020-04-27 | Completed language resource changes & updates
| 2020-04-28 | Release - Test Flight (Modifications after 21-Apr-20 release)
| 2020-04-28 | Screen Flow Document 7 - Changes required by client
| 2020-04-30 | Received Universal Payment API documentation
2020-05-01 | 2020-05-03 | Testing completed with FW Version0.31 with BLE app
| 2020-05-04 | Security Implementation using FW Version0.31
| 2020-05-11 | Release - Test Flight (Modifications after 28-Apr-20 & Security Implementation release)
| 2020-05-12 | First Demo with Security implementation feature using FW Version0.31 - Failed
| 2020-05-20 | Second Demo with Security implementation feature using FW Version0.31 - Succeeded

## Screen Changes History
CHANGE HISTORY - DATE WISE
| WELCOME - 21-JANUARY-2020 |  |  |  | 29-JANUARY-2020 |  | 16-APRIL-2020 |  | 22-APRIL-2020 |  | 01-MAY-2020
8.5
[5 empty] | 1 | Screen theme color has been changed | 1 | Changed the language selection from dropdown to radion button - For Android
[9 empty] | 1 | Show the language selection during the first time login only - For Android | 1 | Changes in the Japanese captions
[5 empty] | 2 | Japanese screens has been created | 2 | Mobile device language will be taken as the app language - For iOS
[7 empty] | 3 | MAC Id will be taken as an unique key to identify the authorized user
| USER REGISTRATION - 21-JANUARY-2020 |  |  |  | 29-JANUARY-2020 |  | 06-APRIL-2020 |  | 16-APRIL-2020 |  | 22-APRIL-2020 |  | 28-APRIL-2020 |  | 01-MAY-2020
[5 empty] | 1 | Transfer Account has been removed | 1 | Mail alert has been added while creating the user account | 1 | Added the Terms & Conditions Link for Usage & Payment in Registration screen | 1 | Removed the Terms & Conditions Link for Payment from Registration screen | 1 | Detailed OTP message has been displayed | 1 | Japanese caption changes
[5 empty] | 2 | Username input screen has been merged to new registration screen | 2 | User registration summary screen has been removed | 2 | Popup message has been modified to show detailed message after registration | 2 | Terms & Conditions Link for Payment will be provided during the Locking process | 2 | Japanese caption changes | 2 | Checkbox added to the terms and conditions
[5 empty] | 3 | Password Removed and PIN generation created | 3 | A link has been added to "Login as different User" - Multiple users login in same device |  |  | 3 | Popup message has been modified to show detailed message after registration | 3 | Resend PIN has been added
[5 empty] | 4 | Date of Birth added as additional field to identify the authorised user | 4 | User account will be validated using the mobile MAC Id |  |  |  |  | 4 | OTP screen added supported payment Methods
[13 empty] | 5 | "Login in new device" and "Forgot PIN" separated
| FORGOT PIN - 21-JANUARY-2020 |  |  |  | 29-JANUARY-2020 |  | 16-APRIL-2020 |  | 01-MAY-2020
[5 empty] | 1 | Password has been changed to PIN | 1 | Add a button to "Login as different user / Forgot Pin" option | 1 | Japanese caption changes
[5 empty] | 2 | When click "forgot password" the new PIN will send to mail
| EXISITNG USER - 21-JANUARY-2020 |  |  |  | 29-JANUARY-2020 |  | LOGIN AS DIFFERENT USER - 06-APRIL-2020 |  | 16-APRIL-2020 |  | NEW DEVICE - 28-APRIL-2020
[5 empty] | 1 | Registered users can login using another device in case of lost mobile | 1 | "Existing user login" changed to "Login as different user" | 1 | "Login as different user" - User can create a new account with his new emailid | 1 | User lost his mobile and setup a new mobile and access his account.
[He can login using his registration information]
[5 empty] | 2 | Email address and PIN will be provided | 2 | Registered users can login using another registered user mobile | 2 | Search device location link has been added |  | OR
[He can create a new account with new email address]
[5 empty] | 3 | Forget PIN screen also has been added here | 3 | Email address, Date of Birth and PIN will be provided | 3 | Confirmation message will be displayed to for the mobile device change.
[10 empty] | (This will update the MacID in the database) | 2 | One user is only allowed for One device
[7 empty] | 4 | Registered users can login using another device in case of lost mobile
| TRANSFER ACCOUNT - 21-JANUARY-2020 |  |  |  | CHANGE PIN - 29-JANUARY-2020 |  | 06-APRIL-2020 |  | 01-MAY-2020
This has been removed in the Initial Stage
[5 empty] | 1 | Created new screen for "Change PIN" | 1 | Provided New PIN and Confirm PIN | 1 | Japanese caption changes
[7 empty] | 2 | PIN Changed summary screen has been removed
[7 empty] | 3 | Alert will be displayed after the PIN change
[7 empty] | 4 | "Change Language" button has been removed
DEVICE LOCKING - 21-JANUARY-2020
29-JANUARY-2020
| 1 |  | User Login using the Email Address, Date of Birth & PIN
| 2 |  | Email address, Date of Birth and PIN will be provided
| 3 |  | Forget PIN screen also has been added here
| 4 |  | Inlcuded supported Card images
| 5 |  | Added additional screen for showing the locking video
06-FEBRUARY-2020
| 1 |  | Login changed using the PIN only
06-APRIL-2020
| 1 |  | Payment Integration done
| 2 |  | Payment mode moved to Take Me Pay
| 3 |  | New Screen for Initiating the Lock process
16-APRIL-2020
| 1 |  | Search device location link has been added
| 2 |  | Animated GIF for manual locking process
| 3 |  | Security implementation process started
22-APRIL-2020
| 1 |  | Additional screen has been added for payment terms & conditions
| 2 |  | Security implementation process started
| 3 |  | Prelock Screen - Establish the Bluetooth connectivity
| 4 |  | Prelock Screen - Animated gif will be displayed showing Manual locking process.
| 5 |  | Prelock Screen - On button click the Latch will be released for locking
28-APRIL-2020
| 1 |  | Scan button has been added to open the Camera
| 2 |  | Japanese caption changes
| 3 |  | Supported debit/credit card images has been added
| 4 |  | Security implementation process progressing
| 5 |  | Lock handle signals is managed after "Lock" initiate screen
01-MAY-2020
| 1 |  | Japanese caption changes
| 2 |  | Checkbox added to terms & conditions
| 3 |  | Rate Information added in the In Use screen
| 4 |  | Security implementation process progressing - Bluetooth connection is establishing before the "Lock" screen
| 5 |  | Content changes in initial payment & device locking screen and summary screen
DEVICE UNLOCKING - 21-JANUARY-2020
29-JANUARY-2020
| 1 |  | Screen design changes - captions
| 2 |  | Inlcuded Start Time and End Time
| 3 |  | Added additional screen for showing the locking video
2
06-FEBRUARY-2020
| 1 |  | Added new screen to Establish the Bluetooth connectivity
06-APRIL-2020
|  | 1 | Payment Integration using Take me pay url
|  | 2 | Payment type will be selected in Take me pay screen
|  | 3 | Screen design and content has been changed
|  | 4 | Additional screen to Initiate the Unlock process
16-APRIL-2020
| 1 |  | When user login for Unlocking, In Use screen will be displayed with two buttons:
| 2 |  | Scan button - Navigate to Camera for Scanning
| 4 |  | Get Direction button - Brings the google map directions
| 5 |  | After Scan navigate to the payment screen
28-APRIL-2020
|  | 1 |  | Login screen changes
|  | 2 |  | Japanese caption changes
|  | 3 |  | Scan button has been added to open the Camera
|  | 4 |  | Payment details - Content changes
|  | 5 |  | Security Implementation process progressing
| 01-MAY-2020 |  |  |  | 01-MAY-2020
| 1 |  | Japanese caption changes
| 2 |  | Screen for unlocking operation
| 3 |  | Scan button has been added to open the Camera
| 4 |  | Bluetooth connectivity establishes on the "In Use" screen
| 5 |  | Security Implementation process progressing
For Android
For iOS
For Android
For iOS