## July23
ICS- HRMIS |  | PHASE | START | END
|  | 1 | 2020-03-01 | 31/7/2020
LAST UPDATED ON: 23-Jul-2020
LAST UPDATED BY: Naveen
Total time estimated : 1124(hrs)
Total time elapsed : 1380(hrs)
Total percentage of completion : 95%
Total variation percentage : 15%
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-07-30 | 2020-07-29 | 2020-07-28 | 2020-07-27 | 2020-07-25 | 2020-07-24 | 2020-07-23 | 2020-07-22 | 2020-07-21 | 2020-07-20 | 2020-07-17 | 2020-07-16 | 2020-07-15 | 2020-07-14 | 2020-07-13 | 2020-07-11 | 2020-07-10 | 2020-07-09 | 2020-07-08 | 2020-07-07 | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-15 | 2020-05-14 | 2020-05-13 | 2020-05-12 | 2020-05-11 | 2020-05-09 | 2020-05-08 | 2020-05-07 | 2020-05-06 | 2020-05-05 | 2020-05-04 | 2020-04-30 | 2020-04-29 | 2020-04-28 | 2020-04-27 | 2020-04-25 | 2020-04-24 | 2020-04-23 | 2020-04-22 | 2020-04-21 | 2020-04-20 | 2020-04-17 | 2020-04-16 | 2020-04-15 | 2020-04-13
1 | Create SDD | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-06 | 2020-05-12 | [63 empty] | 100% | 90% | 80% | 80% | 60% | 60% | [8 empty] | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60%
2 | Create SRS | 1 | COMPLETED | Naveen | 28 | 36 | 2020-04-15 | 2020-04-25 | [75 empty] | 100% | 80% | 80% | 80% | 80% | 80% | 60% | 40% | 20%
3 | HTML Mockup | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-24 | 2020-05-05 | [69 empty] | 100% | 90% | 80% | 70% | 60% | 40% | 20% | 10%
4 | Forget Password | 1 | COMPLETED | Ayana | 28 | 46 | 2020-07-15 | 2020-07-22 | [7 empty] | 100% | 80% | 60% | 40% | 30% | 10% | [49 empty] | 10%
5 | Employee CRUD operation - document upload | 1 | IN PROGRESS | Jeswin/Ayana | 64 | 80 | 2020-05-13 |  | 85% | [20 empty] | 80% | 60% | 50% |  |  |  |  | 40% | 40% | 30% | 30% | 20% | 20% | [27 empty] | 10% | 10%
6 | Holiday CRUD operation | 1 | COMPLETED | Jeswin | 64 | 80 | 2020-06-01 | 2020-06-13 | [37 empty] | 100% | 90% | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
7 | LeaveType CRUD operation | 1 | COMPLETED | Ayana | 56 | 58 | 2020-05-13 | 2020-06-12 | [39 empty] | 100% |  |  | 90% | 70% | 50% | [10 empty] | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
8 | Client CRUD Operation | 1 | COMPLETED | Ayana | 64 | 40 | 2020-07-09 | [7 empty] | 50% | [6 empty] | 50% | 40% | 30% | 20% | 10%
9 | Approver CRUD operation | 1 | COMPLETED | Jeswin | 56 | 64 | 2020-05-15 | 2020-05-25 | [53 empty] | 100% | 80% | 60% | 50% | 40% | 30% | 20% | 10%
10 | Mail Notification for Approvers and Announcements | 1 | COMPLETED | Ayana/Jeswin | 56 | 104 | 2020-06-12 | 2020-07-22 | [7 empty] | 100% | 90% | 90% | 90% | 90% | 90% | [5 empty] | 80% | 70% | 60% | [13 empty] | 40% | 30% |  | 20% | 10%
11 | Employee Project CRUD operation | 1 | COMPLETED | Jeswin | 56 | 56 | 2020-07-23 | 2020-07-30 | 100% | 90% | 75% | 60% | 45% | 30% | 10%
12 | Leave Definition and Allocation | 1 | COMPLETED | Ayana | 56 | 76 | 2020-05-22 | 2020-06-04 | [46 empty] | 80% | 70% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
13 | Leave Application - Employee | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 56 | 60 | 2020-05-13 | 2020-06-12 | [38 empty] | 100% | 90% | [11 empty] | 80% | 70% | 60% | 50% | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
14 | Dashboard - Calendar | 1 | COMPLETED | Jeswin | 40 | 48 | 2020-05-26 | 2020-06-01 | [47 empty] | 100% | 90% | 70% | 50% | 30% | 10%
15 | Dashboard - Approval List | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 80 | 104 | 2020-05-28 | 2020-06-22 | [31 empty] | 100% | 90% | 80% |  |  | 70% | 70% | [6 empty] | 70% | 50% | 40% | 40% | 30% | 20% | 10%
16 | Dashboard - Pending Leaves | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 64 | 72 | 2020-06-05 | 2020-06-25 | [28 empty] | 100% | 90% | 80% |  |  |  | 70% | 70% |  |  | 70% | 50% |  |  | 30% | 10%
17 | Dashboard - Announcement - crud, view | 1 |  | Anandpadmanabhan | 48
18 | Dashboard - Workreports | 1 | COMPLETED | Ayana | 48 | 48 | 2020-06-26 | 2020-07-02 | [22 empty] | 100% | 80% | 70% | 50% | 30% | 10%
19 | Leave Reports | 1 | COMPLETED | Jeswin | 48 | 48 | 2020-06-26 | 2020-07-02 | [22 empty] | 100% | 80% | 70% | 50% | 30% | 10%
20 | Work Reports | 1 | COMPLETED | Ayana | 48 | 48 | 2020-06-18 | 2020-06-25 | [21 empty] | 100% | [6 empty] | 80% | 60% | 40% | 30% | 10%
21 | Project History | 1 | COMPLETED | Ayana | 64 | 48 | 2020-07-23 | 2020-07-29 |  | 100% | 95% | 85% | 65% | 50% | 10%
22 | Leave History | 1 | COMPLETED | Jeswin | 80 | 32 | 2020-06-30 | 2020-07-02 | [6 empty] | 70% | [14 empty] | 70% | 50% | 30% | 10%
23 | Code Integration | 1 | IN PROGRESS | Ayana | 16 | 32 | 2020-06-09 | [41 empty] | 30% | 10%
24 | Integration Testing | 1 |  | Ayana; Anandpadmanabhan | 8
25 | Deployment into Server | 1 |  | Anu; Naveen | 8
26 | UAT - Verification | 1 |  | Roshn | 16
[5 empty] | 1124 | 1308

## July16
ICS- HRMIS |  | PHASE | START | END
|  | 1 | 2020-03-01 | 31/7/2020
LAST UPDATED ON: 16-Jul-2020
LAST UPDATED BY: Naveen
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-07-16 | 2020-07-15 | 2020-07-14 | 2020-07-13 | 2020-07-11 | 2020-07-10 | 2020-07-09 | 2020-07-08 | 2020-07-07 | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-15 | 2020-05-14 | 2020-05-13 | 2020-05-12 | 2020-05-11 | 2020-05-09 | 2020-05-08 | 2020-05-07 | 2020-05-06 | 2020-05-05 | 2020-05-04 | 2020-04-30 | 2020-04-29 | 2020-04-28 | 2020-04-27 | 2020-04-25 | 2020-04-24 | 2020-04-23 | 2020-04-22 | 2020-04-21 | 2020-04-20 | 2020-04-17 | 2020-04-16 | 2020-04-15 | 2020-04-13
1 | Create SDD | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-06 | 2020-05-12 | [52 empty] | 100% | 90% | 80% | 80% | 60% | 60% | [8 empty] | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60%
2 | Create SRS | 1 | COMPLETED | Naveen | 28 | 36 | 2020-04-15 | 2020-04-25 | [64 empty] | 100% | 80% | 80% | 80% | 80% | 80% | 60% | 40% | 20%
3 | HTML Mockup | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-24 | 2020-05-05 | [58 empty] | 100% | 90% | 80% | 70% | 60% | 40% | 20% | 10%
4 | Forget Password | 1 | PROGRESS | Ayana | 28 | 14 | 2020-07-15 |  | 30% | 10% | [49 empty] | 10%
5 | Employee CRUD operation | 1 | PROGRESS | Jeswin/Anandpadmanabhan | 64 | 80 | 2020-05-13 | [11 empty] | 80% | 60% | 50% |  |  |  |  | 40% | 40% | 30% | 30% | 20% | 20% | [27 empty] | 10% | 10%
6 | Holiday CRUD operation | 1 | COMPLETED | Jeswin | 64 | 80 | 2020-06-01 | 2020-06-13 | [26 empty] | 100% | 90% | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
7 | LeaveType CRUD operation | 1 | COMPLETED | Ayana | 56 | 58 | 2020-05-13 | 2020-06-12 | [28 empty] | 100% |  |  | 90% | 70% | 50% | [10 empty] | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
8 | Client CRUD Operation | 1 | PROGRESS | Ayana | 64 | 40 | 2020-07-09 |  |  |  | 50% | 40% | 30% | 20% | 10%
9 | Approver CRUD operation | 1 | COMPLETED | Jeswin | 56 | 64 | 2020-05-15 | 2020-05-25 | [42 empty] | 100% | 80% | 60% | 50% | 40% | 30% | 20% | 10%
10 | Mail Notification for Approvers and Announcements | 1 | PROGRESS | Ayana/Jeswin | 56 | 64 | 2020-06-12 |  | 90% | 90% | [5 empty] | 80% | 70% | 60% | [13 empty] | 40% | 30% |  | 20% | 10%
11 | Employee Project CRUD operation | 1 |  | Jeswin | 56
12 | Leave Definition and Allocation | 1 | COMPLETED | Ayana | 56 | 76 | 2020-05-22 | 2020-06-04 | [35 empty] | 80% | 70% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
13 | Leave Application - Employee | 1 | COMPLETED | Anandpadmanabhan | 56 | 60 | 2020-05-13 | 2020-06-12 | [27 empty] | 100% | 90% | [11 empty] | 80% | 70% | 60% | 50% | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
14 | Dashboard - Calendar | 1 | COMPLETED | Jeswin | 40 | 48 | 2020-05-26 | 2020-06-01 | [36 empty] | 100% | 90% | 70% | 50% | 30% | 10%
15 | Dashboard - Approval List | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 80 | 104 | 2020-05-28 | 2020-06-22 | [20 empty] | 100% | 90% | 80% |  |  | 70% | 70% | [6 empty] | 70% | 50% | 40% | 40% | 30% | 20% | 10%
16 | Dashboard - Pending Leaves | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 64 | 72 | 2020-06-05 | 2020-06-25 | [17 empty] | 100% | 90% | 80% |  |  |  | 70% | 70% |  |  | 70% | 50% |  |  | 30% | 10%
17 | Dashboard - Announcement | 1 |  | Anandpadmanabhan | 48
18 | Dashboard - Workreports | 1 | COMPLETED | Ayana | 48 | 48 | 2020-06-26 | 2020-07-02 | [11 empty] | 100% | 80% | 70% | 50% | 30% | 10%
19 | Leave Reports | 1 | COMPLETED | Jeswin | 48 | 48 | 2020-06-26 | 2020-07-02 | [11 empty] | 100% | 80% | 70% | 50% | 30% | 10%
20 | Work Reports | 1 | COMPLETED | Ayana | 48 | 48 | 2020-06-18 | 2020-06-25 | [10 empty] | 100% | [6 empty] | 80% | 60% | 40% | 30% | 10%
21 | Project History | 1 |  | Ayana | 64
22 | Leave History | 1 | COMPLETED | Jeswin | 80 | 32 | 2020-06-30 | 2020-07-02 | [10 empty] | 70% | 50% | 30% | 10%
23 | Code Integration | 1 |  | Ayana; Anandpadmanabhan | 16 | 32 | 2020-06-09 | [30 empty] | 30% | 10%
24 | Integration Testing | 1 |  | Ayana; Anandpadmanabhan | 8
25 | Deployment into Server | 1 |  | Anu; Naveen | 8
26 | UAT - Verification | 1 |  | Roshn | 16
1124

## July11
ICS- HRMIS |  | PHASE | START | END
|  | 1 | 2020-03-01 | 31/7/2020
LAST UPDATED ON: 11-Jul-2020
LAST UPDATED BY: Naveen
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-07-10 | 2020-07-09 | 2020-07-08 | 2020-07-07 | 2020-07-06 | 2020-07-03 | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-15 | 2020-05-14 | 2020-05-13 | 2020-05-12 | 2020-05-11 | 2020-05-09 | 2020-05-08 | 2020-05-07 | 2020-05-06 | 2020-05-05 | 2020-05-04 | 2020-04-30 | 2020-04-29 | 2020-04-28 | 2020-04-27 | 2020-04-25 | 2020-04-24 | 2020-04-23 | 2020-04-22 | 2020-04-21 | 2020-04-20 | 2020-04-17 | 2020-04-16 | 2020-04-15 | 2020-04-13
1 | Create SDD | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-06 | 2020-05-12 | [47 empty] | 100% | 90% | 80% | 80% | 60% | 60% | [8 empty] | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60%
2 | Create SRS | 1 | COMPLETED | Naveen | 28 | 36 | 2020-04-15 | 2020-04-25 | [59 empty] | 100% | 80% | 80% | 80% | 80% | 80% | 60% | 40% | 20%
3 | HTML Mockup | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-24 | 2020-05-05 | [53 empty] | 100% | 90% | 80% | 70% | 60% | 40% | 20% | 10%
4 | Forget Password | 1 |  | Jeswin | 28 | [49 empty] | 10%
5 | Employee CRUD operation | 1 | PROGRESS | Jeswin/Anandpadmanabhan | 64 | 80 | 2020-05-13 | [6 empty] | 80% | 60% | 50% |  |  |  |  | 40% | 40% | 30% | 30% | 20% | 20% | [27 empty] | 10% | 10%
6 | Holiday CRUD operation | 1 | COMPLETED | Jeswin | 64 | 80 | 2020-06-01 | 2020-06-13 | [21 empty] | 100% | 90% | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
7 | LeaveType CRUD operation | 1 | COMPLETED | Ayana | 56 | 58 | 2020-05-13 | 2020-06-12 | [23 empty] | 100% |  |  | 90% | 70% | 50% | [10 empty] | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
8 | Client CRUD Operation | 1 | PROGRESS | Ayana | 64 | 16 | 2020-07-09 |  | 20% | 10%
9 | Approver CRUD operation | 1 | COMPLETED | Jeswin | 56 | 64 | 2020-05-15 | 2020-05-25 | [37 empty] | 100% | 80% | 60% | 50% | 40% | 30% | 20% | 10%
10 | Mail Notification for Approvers and Announcements | 1 | PROGRESS | Ayana | 56 | 64 | 2020-06-12 |  |  |  | 80% | 70% | 60% | [13 empty] | 40% | 30% |  | 20% | 10%
11 | Employee Project CRUD operation | 1 |  | Jeswin | 56
12 | Leave Definition and Allocation | 1 | COMPLETED | Ayana | 56 | 76 | 2020-05-22 | 2020-06-04 | [30 empty] | 80% | 70% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
13 | Leave Application - Employee | 1 | COMPLETED | Anandpadmanabhan | 56 | 60 | 2020-05-13 | 2020-06-12 | [22 empty] | 100% | 90% | [11 empty] | 80% | 70% | 60% | 50% | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
14 | Dashboard - Calendar | 1 | COMPLETED | Jeswin | 40 | 48 | 2020-05-26 | 2020-06-01 | [31 empty] | 100% | 90% | 70% | 50% | 30% | 10%
15 | Dashboard - Approval List | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 80 | 104 | 2020-05-28 | 2020-06-22 | [15 empty] | 100% | 90% | 80% |  |  | 70% | 70% | [6 empty] | 70% | 50% | 40% | 40% | 30% | 20% | 10%
16 | Dashboard - Pending Leaves | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 64 | 72 | 2020-06-05 | 2020-06-25 | [12 empty] | 100% | 90% | 80% |  |  |  | 70% | 70% |  |  | 70% | 50% |  |  | 30% | 10%
17 | Dashboard - Announcement | 1 | PROGRESS | Anandpadmanabhan | 48
18 | Dashboard - Workreports | 1 | COMPLETED | Ayana | 48 | 48 | 2020-06-26 | 2020-07-02 | [6 empty] | 100% | 80% | 70% | 50% | 30% | 10%
19 | Leave Reports | 1 | COMPLETED | Jeswin | 48 | 48 | 2020-06-26 | 2020-07-02 | [6 empty] | 100% | 80% | 70% | 50% | 30% | 10%
20 | Work Reports | 1 | COMPLETED | Ayana | 48 | 48 | 2020-06-18 | 2020-06-25 | [5 empty] | 100% | [6 empty] | 80% | 60% | 40% | 30% | 10%
21 | Project History | 1 |  | Ayana | 64
22 | Leave History | 1 | COMPLETED | Jeswin | 80 | 32 | 2020-06-30 | [6 empty] | 70% | 50% | 30% | 10%
23 | Code Integration | 1 |  | Ayana; Anandpadmanabhan | 16 | 32 | 2020-06-09 | [25 empty] | 30% | 10%
24 | Integration Testing | 1 |  | Ayana; Anandpadmanabhan | 8
25 | Deployment into Server | 1 |  | Anu; Naveen | 8
26 | UAT - Verification | 1 |  | Roshn | 16
1124

## July02
ICS- HRMIS |  | PHASE | START | END
|  | 1 | 2020-03-01 | 31/7/2020
LAST UPDATED ON: 02-Jul-2020
LAST UPDATED BY: Naveen
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-07-02 | 2020-07-01 | 2020-06-30 | 2020-06-29 | 2020-06-27 | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-15 | 2020-05-14 | 2020-05-13 | 2020-05-12 | 2020-05-11 | 2020-05-09 | 2020-05-08 | 2020-05-07 | 2020-05-06 | 2020-05-05 | 2020-05-04 | 2020-04-30 | 2020-04-29 | 2020-04-28 | 2020-04-27 | 2020-04-25 | 2020-04-24 | 2020-04-23 | 2020-04-22 | 2020-04-21 | 2020-04-20 | 2020-04-17 | 2020-04-16 | 2020-04-15 | 2020-04-13
1 | Create SDD | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-06 | 2020-05-12 | [41 empty] | 100% | 90% | 80% | 80% | 60% | 60% | [8 empty] | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60%
2 | Create SRS | 1 | COMPLETED | Naveen | 28 | 36 | 2020-04-15 | 2020-04-25 | [53 empty] | 100% | 80% | 80% | 80% | 80% | 80% | 60% | 40% | 20%
3 | HTML Mockup | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-24 | 2020-05-05 | [47 empty] | 100% | 90% | 80% | 70% | 60% | 40% | 20% | 10%
4 | Forget Password | 1 |  | Jeswin | 28 | [43 empty] | 10%
5 | Employee CRUD operation | 1 | IN PROGRESS | Jeswin/Anandpadmanabhan | 64 | 72 | 2020-05-13 |  | 60% | 50% |  |  |  |  | 40% | 40% | 30% | 30% | 20% | 20% | [27 empty] | 10% | 10%
6 | Holiday CRUD operation | 1 | COMPLETED | Jeswin | 64 | 80 | 2020-06-01 | 2020-06-13 | [15 empty] | 100% | 90% | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
7 | LeaveType CRUD operation | 1 | COMPLETED | Ayana | 56 | 58 | 2020-05-13 | 2020-06-12 | [17 empty] | 100% |  |  | 90% | 70% | 50% | [10 empty] | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
8 | Client CRUD Operation | 1 |  | Ayana | 64
9 | Approver CRUD operation | 1 | COMPLETED | Jeswin | 56 | 64 | 2020-05-15 | 2020-05-25 | [31 empty] | 100% | 80% | 60% | 50% | 40% | 30% | 20% | 10%
10 | Mail Notification for Approvers and Announcements | 1 | IN PROGRESS | Ayana | 56 | 40 | 2020-06-12 | [13 empty] | 40% | 30% |  | 20% | 10%
11 | Employee Project CRUD operation | 1 |  | Jeswin | 56
12 | Leave Definition and Allocation | 1 | COMPLETED | Ayana | 56 | 76 | 2020-05-22 | 2020-06-04 | [24 empty] | 80% | 70% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
13 | Leave Application - Employee | 1 | COMPLETED | Anandpadmanabhan | 56 | 60 | 2020-05-13 | 2020-06-12 | [16 empty] | 100% | 90% | [11 empty] | 80% | 70% | 60% | 50% | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
14 | Dashboard - Calendar | 1 | COMPLETED | Jeswin | 40 | 48 | 2020-05-26 | 2020-06-01 | [25 empty] | 100% | 90% | 70% | 50% | 30% | 10%
15 | Dashboard - Approval List | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 80 | 104 | 2020-05-28 | 2020-06-22 | [9 empty] | 100% | 90% | 80% |  |  | 70% | 70% | [6 empty] | 70% | 50% | 40% | 40% | 30% | 20% | 10%
16 | Dashboard - Pending Leaves | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 64 | 72 | 2020-06-05 | 2020-06-25 | [6 empty] | 100% | 90% | 80% |  |  |  | 70% | 70% |  |  | 70% | 50% |  |  | 30% | 10%
17 | Dashboard - Announcement | 1 |  | Anandpadmanabhan | 48
18 | Dashboard - Workreports | 1 | COMPLETED | Ayana | 48 | 48 | 2020-06-26 | 2020-07-02 | 100% | 80% | 70% | 50% | 30% | 10%
19 | Leave Reports | 1 | COMPLETED | Jeswin | 48 | 48 | 2020-06-26 | 2020-07-02 | 100% | 80% | 70% | 50% | 30% | 10%
20 | Work Reports | 1 | COMPLETED | Ayana | 48 | 48 | 2020-06-18 | 2020-06-25 | [6 empty] | 80% | 60% | 40% | 30% | 10%
21 | Project History | 1 |  | Ayana | 64
22 | Leave History | 1 | IN PROGRESS | Jeswin | 80 | 24 | 2020-06-30 |  | 50% | 30% | 10%
23 | Code Integration | 1 |  | Ayana; Anandpadmanabhan | 16 | 32 | 2020-06-09 | [19 empty] | 30% | 10%
24 | Integration Testing | 1 |  | Ayana; Anandpadmanabhan | 8
25 | Deployment into Server | 1 |  | Anu; Naveen | 8
26 | UAT - Verification | 1 |  | Roshn | 16
1124

## June25
ICS- HRMIS |  | PHASE | START | END
|  | 1 | 2020-03-01 | 31/7/2020
LAST UPDATED ON: 25-June-2020
LAST UPDATED BY: Naveen
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-06-26 | 2020-06-25 | 2020-06-24 | 2020-06-23 | 2020-06-22 | 2020-06-19 | 2020-06-18 | 2020-06-17 | 2020-06-16 | 2020-06-15 | 2020-06-13 | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-15 | 2020-05-14 | 2020-05-13 | 2020-05-12 | 2020-05-11 | 2020-05-09 | 2020-05-08 | 2020-05-07 | 2020-05-06 | 2020-05-05 | 2020-05-04 | 2020-04-30 | 2020-04-29 | 2020-04-28 | 2020-04-27 | 2020-04-25 | 2020-04-24 | 2020-04-23 | 2020-04-22 | 2020-04-21 | 2020-04-20 | 2020-04-17 | 2020-04-16 | 2020-04-15 | 2020-04-13
1 | Create SDD | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-06 | 2020-05-12 | [36 empty] | 100% | 90% | 80% | 80% | 60% | 60% | [8 empty] | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60%
2 | Create SRS | 1 | COMPLETED | Naveen | 28 | 36 | 2020-04-15 | 2020-04-25 | [48 empty] | 100% | 80% | 80% | 80% | 80% | 80% | 60% | 40% | 20%
3 | HTML Mockup | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-24 | 2020-05-05 | [42 empty] | 100% | 90% | 80% | 70% | 60% | 40% | 20% | 10%
4 | Forget Password | 1 |  | Jeswin | 28 | [38 empty] | 10%
5 | Employee CRUD operation | 1 | PROGRESS | Jeswin/Anandpadmanabhan | 64 | 56 | 2020-05-13 |  |  | 40% | 40% | 30% | 30% | 20% | 20% | [27 empty] | 10% | 10%
6 | Holiday CRUD operation | 1 | COMPLETED | Jeswin | 64 | 80 | 2020-06-01 | 2020-06-13 | [10 empty] | 100% | 90% | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
7 | LeaveType CRUD operation | 1 | COMPLETED | Ayana | 56 | 58 | 2020-05-13 | 2020-06-12 | [12 empty] | 100% |  |  | 90% | 70% | 50% | [10 empty] | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
8 | Client CRUD Operation | 1 |  | Ayana | 64
9 | Approver CRUD operation | 1 | COMPLETED | Jeswin | 56 | 64 | 2020-05-15 | 2020-05-25 | [26 empty] | 100% | 80% | 60% | 50% | 40% | 30% | 20% | 10%
10 | Mail Notification for Approvers and Announcements | 1 | PROGRESS | Ayana | 56 | 40 | 2020-06-12 | [8 empty] | 40% | 30% |  | 20% | 10%
11 | Employee Project CRUD operation | 1 |  | Jeswin | 56
12 | Leave Definition and Allocation | 1 | COMPLETED | Ayana | 56 | 76 | 2020-05-22 | 2020-06-04 | [19 empty] | 80% | 70% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
13 | Leave Application - Employee | 1 | COMPLETED | Anandpadmanabhan | 56 | 60 | 2020-05-13 | 2020-06-12 | [11 empty] | 100% | 90% | [11 empty] | 80% | 70% | 60% | 50% | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
14 | Dashboard - Calendar | 1 | COMPLETED | Jeswin | 40 | 48 | 2020-05-26 | 2020-06-01 | [20 empty] | 100% | 90% | 70% | 50% | 30% | 10%
15 | Dashboard - Approval List | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 80 | 104 | 2020-05-28 | 2020-06-22 |  |  |  |  | 100% | 90% | 80% |  |  | 70% | 70% | [6 empty] | 70% | 50% | 40% | 40% | 30% | 20% | 10%
16 | Dashboard - Pending Leaves | 1 | COMPLETED | Jeswin/Anandpadmanabhan | 64 | 72 | 2020-06-05 | 2020-06-25 |  | 100% | 90% | 80% |  |  |  | 70% | 70% |  |  | 70% | 50% |  |  | 30% | 10%
17 | Dashboard - Announcement | 1 |  | Anandpadmanabhan | 48
18 | Dashboard - Workreports | 1 |  | Ayana | 48
19 | Leave Reports | 1 |  | Jeswin | 48
20 | Work Reports | 1 | PROGRESS | Ayana | 48 | 48 | 2020-06-18 |  |  | 80% | 60% | 40% | 30% | 10%
21 | Project History | 1 |  | Ayana | 64
22 | Leave History | 1 |  | Jeswin | 80
23 | Code Integration | 1 |  | Ayana; Anandpadmanabhan | 16 | 32 | [15 empty] | 30% | 10%
24 | Integration Testing | 1 |  | Ayana; Anandpadmanabhan | 8
25 | Deployment into Server | 1 |  | Anu; Naveen | 8
26 | UAT - Verification | 1 |  | Roshn | 16
1124

## June12
ICS- HRMIS |  | PHASE | START | END
|  | 1 | 2020-03-01 | 31/7/2020
LAST UPDATED ON: 12-June-2020
LAST UPDATED BY: Naveen
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-06-12 | 2020-06-11 | 2020-06-10 | 2020-06-09 | 2020-06-08 | 2020-06-05 | 2020-06-04 | 2020-06-03 | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-15 | 2020-05-14 | 2020-05-13 | 2020-05-12 | 2020-05-11 | 2020-05-09 | 2020-05-08 | 2020-05-07 | 2020-05-06 | 2020-05-05 | 2020-05-04 | 2020-04-30 | 2020-04-29 | 2020-04-28 | 2020-04-27 | 2020-04-25 | 2020-04-24 | 2020-04-23 | 2020-04-22 | 2020-04-21 | 2020-04-20 | 2020-04-17 | 2020-04-16 | 2020-04-15 | 2020-04-13
1 | Create SDD | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-06 | 2020-05-12 | [25 empty] | 100% | 90% | 80% | 80% | 60% | 60% | [8 empty] | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60%
2 | Create SRS | 1 | COMPLETED | Naveen | 28 | 36 | 2020-04-15 | 2020-04-25 | [37 empty] | 100% | 80% | 80% | 80% | 80% | 80% | 60% | 40% | 20%
3 | HTML Mockup | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-24 | 2020-05-05 | [31 empty] | 100% | 90% | 80% | 70% | 60% | 40% | 20% | 10%
4 | Forget Password | 1 |  | Jeswin | 28 | [27 empty] | 10%
5 | Employee CRUD operation | 1 | PROGRESS | Jeswin | 64 | 8 | 2020-05-13 | [24 empty] | 10% | 10%
6 | Holiday CRUD operation | 1 | PROGRESS | Jeswin | 64 | 72 | 2020-06-01 |  | 90% | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
7 | LeaveType CRUD operation | 1 | COMPLETED | Ayana | 56 | 58 | 2020-05-13 | 2020-06-12 |  | 100% |  |  | 90% | 70% | 50% | [10 empty] | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
8 | Client CRUD Operation | 1 |  | Ayana | 64
9 | Approver CRUD operation | 1 | COMPLETED | Jeswin | 56 | 64 | 2020-05-15 | 2020-05-25 | [15 empty] | 100% | 80% | 60% | 50% | 40% | 30% | 20% | 10%
10 | Mail Notification for Approvers and Announcements | 1 | PROGRESS | Ayana | 56
11 | Employee Project CRUD operation | 1 |  | Jeswin | 56 |  |  |  | 100%
12 | Leave Definition and Allocation | 1 | COMPLETED | Ayana | 56 | 76 | 2020-05-22 | 2020-06-04 | [8 empty] | 80% | 70% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
13 | Leave Application - Employee | 1 | COMPLETED | Anandpadmanabhan | 56 | 60 | 2020-05-13 | 2020-06-12 | 100% | 90% | [11 empty] | 80% | 70% | 60% | 50% | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
14 | Dashboard - Calendar | 1 | COMPLETED | Jeswin | 40 | 48 | 2020-05-26 | 2020-06-01 | [9 empty] | 100% | 90% | 70% | 50% | 30% | 10%
15 | Dashboard - Approval List | 1 | PROGRESS | Anandpadmanabhan | 80 | 56 | 2020-05-28 | [7 empty] | 70% | 50% | 40% | 40% | 30% | 20% | 10%
16 | Dashboard - Pending Leaves | 1 | PROGRESS | Anandpadmanabhan | 64 | 32 | 2020-06-05 |  | 70% | 50% |  |  | 30% | 10%
17 | Dashboard - Announcement | 1 |  | Anandpadmanabhan | 48
18 | Dashboard - Workreports | 1 |  | Ayana | 48
19 | Leave Reports | 1 |  | Anandpadmanabhan | 48
20 | Work Reports | 1 |  | Ayana | 48
21 | Project History | 1 |  | Ayana | 64
22 | Leave History | 1 |  | Anandpadmanabhan | 80
23 | Code Integration | 1 |  | Ayana; Anandpadmanabhan | 16 | 32 |  |  |  |  | 30% | 10%
24 | Integration Testing | 1 |  | Ayana; Anandpadmanabhan | 8
25 | Deployment into Server | 1 |  | Anu; Naveen | 8
26 | UAT - Verification | 1 |  | Roshn | 16
1124

## June02
ICS- HRMIS |  | PHASE | START | END
|  | 1 | 2020-03-01 | 31/7/2020
LAST UPDATED ON: 02-June-2020
LAST UPDATED BY: Naveen
SLNo | SUBJECT | PHASE | STATUS | ASSIGNEE | EST. HRS | ACT. HRS | ACT. START | ACT. END | 2020-06-02 | 2020-06-01 | 2020-05-30 | 2020-05-29 | 2020-05-28 | 2020-05-27 | 2020-05-26 | 2020-05-25 | 2020-05-23 | 2020-05-22 | 2020-05-21 | 2020-05-20 | 2020-05-19 | 2020-05-18 | 2020-05-15 | 2020-05-14 | 2020-05-13 | 2020-05-12 | 2020-05-11 | 2020-05-09 | 2020-05-08 | 2020-05-07 | 2020-05-06 | 2020-05-05 | 2020-05-04 | 2020-04-30 | 2020-04-29 | 2020-04-28 | 2020-04-27 | 2020-04-25 | 2020-04-24 | 2020-04-23 | 2020-04-22 | 2020-04-21 | 2020-04-20 | 2020-04-17 | 2020-04-16 | 2020-04-15 | 2020-04-13
1 | Create SDD | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-06 | 2020-05-12 | [17 empty] | 100% | 90% | 80% | 80% | 60% | 60% | [8 empty] | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60%
2 | Create SRS | 1 | COMPLETED | Naveen | 28 | 36 | 2020-04-15 | 2020-04-25 | [29 empty] | 100% | 80% | 80% | 80% | 80% | 80% | 60% | 40% | 20%
3 | HTML Mockup | 1 | COMPLETED | Ayana; Anandpadmanabhan | 48 | 64 | 2020-04-24 | 2020-05-05 | [23 empty] | 100% | 90% | 80% | 70% | 60% | 40% | 20% | 10%
4 | Forget Password | 1 |  | Jeswin | 28 | [19 empty] | 10%
5 | Employee CRUD operation | 1 | PROGRESS | Jeswin | 64 | 8 | 2020-05-13 | [16 empty] | 10% | 10%
6 | Holiday CRUD operation | 1 |  | Jeswin | 64 | 16 | 2020-06-01 |  | 20% | 10%
7 | LeaveType CRUD operation | 1 | PROGRESS | Ayana | 56 | 28 | 2020-05-13 | [10 empty] | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
8 | Client CRUD Operation | 1 |  | Ayana | 64
9 | Approver CRUD operation | 1 |  | Jeswin | 56 | 60 | 2020-05-15 | [8 empty] | 80% | 80% | 60% | 50% | 40% | 30% | 20% | 10%
10 | Mail Notification for Approvers and Announcements | 1 |  | Jeswin | 56
11 | Employee Project CRUD operation | 1 |  | Jeswin | 56
12 | Leave Definition and Allocation | 1 | PROGRESS | Ayana | 56 | 68 | 2020-05-22 |  | 80% | 70% | 70% | 60% | 50% | 40% | 30% | 20% | 10%
13 | Leave Application - Employee | 1 | PROGRESS | Anandpadmanabhan | 56 | 60 | 2020-05-13 | [6 empty] | 80% | 70% | 60% | 50% | 40% | 40% | 30% | 30% | 20% | 20% | 10% | 10%
14 | Dashboard - Calendar | 1 | PROGRESS | Jeswin | 40 | 40 |  |  |  |  | 90% | 70% | 50% | 30% | 10%
15 | Dashboard - Approval List | 1 | PROGRESS | Anandpadmanabhan | 80 | 32 | 2020-05-28 |  | 40% | 40% | 30% | 20% | 10%
16 | Dashboard - Pending Leaves | 1 |  | Anandpadmanabhan | 64
17 | Dashboard - Announcement | 1 |  | Anandpadmanabhan | 48
18 | Dashboard - Workreports | 1 |  | Ayana | 48
19 | Leave Reports | 1 |  | Anandpadmanabhan | 48
20 | Work Reports | 1 |  | Ayana | 48
21 | Project History | 1 |  | Ayana | 64
22 | Leave History | 1 |  | Anandpadmanabhan | 80
23 | Code Integration | 1 |  | Anitha | 16
24 | Integration Testing | 1 |  | Ayana; Anandpadmanabhan | 8
25 | Deployment into Server | 1 |  | Anu; Naveen | 8
26 | UAT - Verification | 1 |  | Roshn | 16
1124